## 2024 PPMP BDU Rev 2 (hidden)
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
END-USER/UNIT: RDD-CDABUS
Charged to: “Functional Philippine Camouflage Fabric for Field Service Uniform(FSU)/ Battle Dress Unifom(BDU) Application”
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ |  | UNIT OF MEASURE | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE | [6 empty] | Jan | Feb | Mar | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
OPS
| Customized Corporate Polo Shirt with Logo Embroidery | 40 pcs. | 40 | pcs | 800 | 32000 | Negotiated Procurement |  | 40
| Printing Services (Camouflage Print 2) | 1 lot | 1 | lot | 33000 | 33000 | Negotiated Procurement |  | 1
| Sewing Services for the Battle Dress Uniform | 10 lots | 10 | lots | 3000 | 30000 | Negotiated Procurement |  | 10
| Professional Weaving Services (Natural Textile Fiber (NTF) blended yarns) | 200 lots | 200 | lots | 150 | 30000 | Negotiated Procurement
| Abrasion Resistance | 3 samples | 3 | samples | 800 | 2400 | Agency to Agency |  | 3
| Strength and Elongation (single strand, ASTM D 2256 / ASTM D 2256 M) | 3 samples | 3 | samples | 700 | 2100 | Agency to Agency |  | 3
| Evenness (ASTM D 1425 / ASTM D 1425M) | 3 samples | 3 | samples | 1100 | 3300 | Agency to Agency |  | 3
| Hairiness (ASTM D 5647) | 3 samples | 3 | samples | 1100 | 3300 | Agency to Agency |  | 3
| Yarn shrinkage (oven, ASTM D 2259 single yarns) | 3 samples | 3 | samples | 700 | 2100 | Agency to Agency |  | 3
| Yarn number (Skein, ASTM D 1907) | 3 samples | 3 | samples | 400 | 1200 | Agency to Agency |  | 3
| Yarn twist (single, ASTM D 1423) | 3 samples | 3 | samples | 700 | 2100 | Agency to Agency |  | 3
| FESEM Imaging | 25 samples | 25 | samples | 8000 | 200000 | Agency to Agency |  |  | 25
| Thermogravimetric Analysis | 25 samples | 25 | samples | 3500 | 87500 | Agency to Agency |  |  | 25
| Differential Scanning Calorimetry | 25 samples | 25 | samples | 3000 | 75000 | Agency to Agency |  |  | 25
Laboratory Supplies Expenses
| Sodium Hydroxide,CAS # 1310-73-2, AR grade, 1 kg/bottle | 15 btls | 15 | btls | 3000 | 45000 | Small Value Procurement |  | 8
| Sodium Sulfite, anhydrous, AR grade, CAS # 7757-83-7, 500 g/bottle | 15 btls | 15 | btls | 2000 | 30000 | Small Value Procurement |  | 6
| Acetone, CAS # 67-64-1, AR Grade, 2.5 L/bottle | 10 btls | 10 | btls | 4999 | 49990 | Small Value Procurement |  |  | 10
| Other Supplies and Materials Expenses |  |  | #N/A
| Customized Certificate Holder | 20 pcs | 20 | pcs | 500 | 10000 | Small Value Procurement |  | 20
| Bag Tag | 20 pcs | 20 | pcs | 300 | 6000 | Small Value Procurement |  | 20
| Upgraded Box Packaging | 20 pcs | 20 | pcs | 200 | 4000 | Small Value Procurement |  | 20
| Infinity scarf | 10 pcs | 10 | pcs | 500 | 5000 | Small Value Procurement |  | 10
| Headband belt | 10 pcs | 10 | pcs | 450 | 4500 | Small Value Procurement |  | 10
| Bamboo Lei | 20 pcs | 20 | pcs | 430 | 8600 | Small Value Procurement |  | 20
| Corrugated Box | 10 pcs | 10 | pcs | 65 | 650 | Small Value Procurement |  | 10
| Sign Pen, Blue, 0.5mm | 30 pcs | 30 | pcs | 150 | 4500 | Small Value Procurement |  | 30
| Mobile Prepaid Load Cards (Smart – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960 | Small Value Procurement |  | 40
| Mobile Prepaid Load Cards (Globe – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960 | Small Value Procurement |  | 40
| P.E. Plastic Bag (20x30 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 2000 | 4000 | Small Value Procurement |  | 2
| P.E. Plastic Bag (25x50 inches, 0.002 inches (thickness) 50pcs/pack | 10 packs | 10 | packs | 2500 | 5000 | Small Value Procurement |  | 2
| P.E. Plastic Bag (40x60 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 3000 | 6000 | Small Value Procurement |  | 2
| Nitrile Gloves (Medium) | 10 boxes | 10 | boxes | 300 | 3000 | Small Value Procurement |  | 10
| Nitrile Gloves (Large) | 10 boxes | 10 | boxes | 300 | 3000 | Small Value Procurement |  | 10
| Labgown (Medium) | 6 pcs | 6 | pcs | 500 | 1000 | Small Value Procurement |  | 2
| Labgown (Large) | 6 pcs | 6 | pcs | 500 | 1000 | Small Value Procurement |  | 2
| Mask | 10 boxes | 10 | boxes | 200 | 2000 | Small Value Procurement |  | 10
| Facial Tissue | 10 packs | 10 | packs | 200 | 2000 | Small Value Procurement |  | 10
| Rolled Tissue | 10 packs | 10 | packs | 200 | 2000 | Small Value Procurement |  | 10
| Parafilm | 10 rolls | 10 | rolls | 4000 | 40000 | Small Value Procurement |  |  | 10
| Ziplock (Small) | 10 packs | 10 | packs | 200 | 2000 | Small Value Procurement |  | 10
| Ziplock (Medium) | 10 packs | 10 | packs | 250 | 2500 | Small Value Procurement |  | 10
| Ziplock (Large) | 10 packs | 10 | packs | 350 | 3500 | Small Value Procurement |  | 10
| Ziplock (Extra Large) | 10 packs | 10 | packs | 400 | 4000 | Small Value Procurement |  | 10
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
| Office Equipment |  |  | #N/A
#N/A
#N/A
#N/A
#N/A
| Laboratory Equipment |  |  | #N/A
#N/A
#N/A
#N/A
| Customized stainless bucket with cover and water tap | 6 pcs | 6 | pcs | 7000 | 4200 | Small Value Procurement |  | 6
| Industrial filter paper, 60x60 cm | 5 packs | 5 | packs | 9999 | 49995 | Small Value Procurement |  |  | 10
| Electrical Cables; Royal Cord, 3 Core | 2 units | 2 | units | 7200 | 14400 | Small Value Procurement |  | 2
| Electrical Breaker | 6 units | 6 | units | 500 | 3000 | Small Value Procurement
| Uninterruptible Power Supply | 2 units | 2 | units | 10000 | 10000 | Small Value Procurement |  | 1
| Gooch Glass Filter | 24 pcs | 24 | pcs | 2500 | 60000 | Small Value Procurement
| Beakers, borosilicate glass, 2L | 20 pcs | 20 | pcs | 1300 | 31200 | Small Value Procurement
| Beakers, borosilicate glass, 1L | 15 pcs | 15 | pcs | 800 | 16000 | Small Value Procurement
| Beakers, borosilicate glass, 500 mL | 15 pcs | 15 | pcs | 250 | 3750 | Small Value Procurement
| Glass Cylinders |  |  | pcs |  |  | Small Value Procurement
| SSD external hard drive | 3 pcs | 3 | pcs | 10000 | 30000 | Small Value Procurement |  |  | 3
| Brown cones |  |  | pcs |  |  | Small Value Procurement
<-- INSERT ROW IF NEEDED
TOTAL BUDGET: |  | 850755
+ 10% Provision for Inflation |  | 85075.5
+ 10% Contingency |  | 85075.5
TOTAL ESTIMATED BUDGET: |  | 1020906
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  | Reviewed by: | [7 empty] | Recommending Approval: | [7 empty] | Approved by:
________________________ |  | MARILOU G. AGUSTIN | [7 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  | Head, Property, Procurement and General Services Section | [7 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  | Date: ______________________ | [7 empty] | Date: ______________________ | [7 empty] | Date: ______________________

## 2024 PPMP BDU 1 (hidden)
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
END-USER/UNIT: RDD-CDABUS
Charged to: “Functional Philippine Camouflage Fabric for Field Service Uniform(FSU)/ Battle Dress Unifom(BDU) Application”
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | QUANTITY/ | UNIT OF MEASURE | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE | SIZE | [5 empty] | Jan | Feb | Mar | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
OPS
| Customized Corporate Polo Shirt with Logo Embroidery | 40 pcs. | 40 | pcs | 800 | 32000 | Negotiated Procurement |  | 40
| Printing Services (Camouflage Print 2) | 1 lot | 1 | lot | 33000 | 33000 | Negotiated Procurement |  | 1
| Sewing Services for the Battle Dress Uniform | 10 lots | 10 | lots | 3000 | 30000 | Negotiated Procurement |  | 10
| Professional Weaving Services (Natural Textile Fiber (NTF) blended yarns) | 200 lots | 200 | lots | 150 | 30000 | Negotiated Procurement |  | 200
| Abrasion Resistance | 3 samples | 3 | samples | 800 | 2400 | Agency to Agency |  | 3
| Strength and Elongation (single strand, ASTM D 2256 / ASTM D 2256 M) | 3 samples | 3 | samples | 700 | 2100 | Agency to Agency |  | 3
| Evenness (ASTM D 1425 / ASTM D 1425M) | 3 samples | 3 | samples | 1100 | 3300 | Agency to Agency |  | 3
| Hairiness (ASTM D 5647) | 3 samples | 3 | samples | 1100 | 3300 | Agency to Agency |  | 3
| Yarn shrinkage (oven, ASTM D 2259 single yarns) | 3 samples | 3 | samples | 700 | 2100 | Agency to Agency |  | 3
| Yarn number (Skein, ASTM D 1907) | 3 samples | 3 | samples | 400 | 1200 | Agency to Agency |  | 3
| Yarn twist (single, ASTM D 1423) | 3 samples | 3 | samples | 700 | 2100 | Agency to Agency |  | 3
| FESEM Imaging | 25 samples | 25 | samples | 8000 | 200000 | Agency to Agency |  |  | 25
| Thermogravimetric Analysis | 25 samples | 25 | samples | 3500 | 87500 | Agency to Agency |  |  | 25
| Differential Scanning Calorimetry | 25 samples | 25 | samples | 3000 | 75000 | Agency to Agency |  |  | 25
Laboratory Supplies Expenses
| Sodium Hydroxide,CAS # 1310-73-2, AR grade, 1 kg/bottle | 15 btls | 15 | btls | 3000 | 45000 | Small Value Procurement |  |  | 15
| Sodium Sulfite, anhydrous, AR grade, CAS # 7757-83-7, 500 g/bottle | 15 btls | 15 | btls | 2000 | 30000 | Small Value Procurement |  |  | 15
| Acetone, CAS # 67-64-1, AR Grade, 2.5 L/bottle | 10 btls | 10 | btls | 4999 | 49990 | Small Value Procurement |  |  | 10
| Nitrile Gloves (Medium) | 10 boxes | 10 | boxes | 300 | 3000 | Small Value Procurement |  |  | 10
| Nitrile Gloves (Large) | 10 boxes | 10 | boxes | 300 | 3000 | Small Value Procurement |  |  | 10
| Labgown (Medium) | 6 pcs | 6 | pcs | 500 | 3000 | Small Value Procurement |  |  | 2
| Labgown (Large) | 6 pcs | 6 | pcs | 500 | 3000 | Small Value Procurement |  |  | 2
| Beakers, borosilicate glass, 2L | 20 pcs | 20 | pcs | 1300 | 26000 | Small Value Procurement |  |  | 20
| Beakers, borosilicate glass, 1L | 15 pcs | 15 | pcs | 800 | 12000 | Small Value Procurement |  |  | 15
| Beakers, borosilicate glass, 500 mL | 15 pcs | 15 | pcs | 250 | 3750 | Small Value Procurement |  |  | 15
| Graduated cylinder, borosilicate glass, 1L |  | 10 | pcs | 2400 | 24000 | Small Value Procurement |  |  | 10
| Graduated cylinder, borosilicate glass, 500 mL |  | 10 | pcs | 2000 | 20000 | Small Value Procurement |  |  | 10
| Graduated cylinder, borosilicate glass, 100 mL |  | 10 | pcs | 1000 | 10000 | Small Value Procurement |  |  | 10
| Gooch Glass Filter | 24 pcs | 24 | pcs | 2500 | 60000 | Small Value Procurement |  |  | 24
Other Supplies and Materials Expenses
| Office Partition |  | 2 | lots | 20000 | 40000 | Small Value Procurement |  | 2
| Customized Certificate Holder | 20 pcs | 20 | pcs | 500 | 10000 | Small Value Procurement |  | 20
| Bag Tag | 20 pcs | 20 | pcs | 300 | 6000 | Small Value Procurement |  | 20
| Upgraded Box Packaging | 20 pcs | 20 | pcs | 200 | 4000 | Small Value Procurement |  | 20
| Infinity scarf | 10 pcs | 10 | pcs | 500 | 5000 | Small Value Procurement |  | 10
| Headband belt | 10 pcs | 10 | pcs | 450 | 4500 | Small Value Procurement |  | 10
| Bamboo Lei | 20 pcs | 20 | pcs | 430 | 8600 | Small Value Procurement |  | 20
| Corrugated Box | 10 pcs | 10 | pcs | 65 | 650 | Small Value Procurement |  | 10
| Sign Pen, Blue, 0.5mm | 30 pcs | 30 | pcs | 150 | 4500 | Small Value Procurement |  | 30
| Mobile Prepaid Load Cards (Smart – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960 | Small Value Procurement |  | 40
| Mobile Prepaid Load Cards (Globe – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960 | Small Value Procurement |  | 40
| P.E. Plastic Bag (20x30 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 2000 | 20000 | Small Value Procurement |  | 2
| P.E. Plastic Bag (25x50 inches, 0.002 inches (thickness) 50pcs/pack | 10 packs | 10 | packs | 2500 | 25000 | Small Value Procurement |  | 2
| P.E. Plastic Bag (40x60 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 3000 | 30000 | Small Value Procurement |  | 2
| Mask | 10 boxes | 10 | boxes | 200 | 2000 | Small Value Procurement |  | 10
| Facial Tissue | 10 packs | 10 | packs | 200 | 2000 | Small Value Procurement |  | 10
| Rolled Tissue | 10 packs | 10 | packs | 200 | 2000 | Small Value Procurement |  | 10
| Ziplock (Small) | 10 packs | 10 | packs | 200 | 2000 | Small Value Procurement |  | 10
| Ziplock (Medium) | 10 packs | 10 | packs | 250 | 2500 | Small Value Procurement |  | 10
| Ziplock (Large) | 10 packs | 10 | packs | 350 | 3500 | Small Value Procurement |  | 10
| Ziplock (Extra Large) | 10 packs | 10 | packs | 400 | 4000 | Small Value Procurement |  | 10
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
| Office Equipment |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
| Laboratory Equipment |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
| Electrical Cables; Royal Cord, 3 Core | 2 units | 2 | units | 7200 | 14400 | Small Value Procurement |  |  | 2
| Electrical Breaker | 6 units | 6 | units | 500 | 3000 | Small Value Procurement |  |  | 6
| Uninterruptible Power Supply | 2 units | 2 | units | 10000 | 20000 | Small Value Procurement |  |  | 1
| Brown cones |  | 600 | pcs | 80 | 48000 | Small Value Procurement |  |  | 600
| SSD external hard drive | 3 pcs | 3 | pcs | 10000 | 30000 | Small Value Procurement |  |  | 3
| Industrial air compressor |  | 1 | lot | 49000 | 49000 | Small Value Procurement |  |  | 1
| Industrial filter paper, 60x60 cm | 5 packs | 5 | packs | 9999 | 49995 | Small Value Procurement |  |  | 10
| Parafilm | 10 rolls | 10 | rolls | 4000 | 40000 | Small Value Procurement |  |  | 10
| Customized stainless bucket with cover and water tap | 6 pcs | 6 | pcs | 7000 | 42000 | Small Value Procurement |  |  | 6
TOTAL BUDGET: |  | 1285305
+ 10% Provision for Inflation |  | 128530.5
+ 10% Contingency |  | 128530.5
TOTAL ESTIMATED BUDGET: |  | 1542366
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: | [6 empty] | Recommending Approval: | [7 empty] | Approved by:
________________________ |  |  | MARILOU G. AGUSTIN | [6 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, Property, Procurement and General Services Section | [6 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  |  | Date: ______________________ | [6 empty] | Date: ______________________ | [7 empty] | Date: ______________________

## PPMP BDU 1 as of March 7, 2024 (hidden)
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
END-USER/UNIT: RDD-CDABUS
Charged to: “Functional Philippine Camouflage Fabric for Field Service Uniform(FSU)/ Battle Dress Unifom(BDU) Application”
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | QUANTITY/ | UNIT OF MEASURE | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE | SIZE | [5 empty] | Jan | Feb | Mar | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
Other Professional Services
| Customized Corporate Polo Shirt with Logo Embroidery | 40 pcs. | 40 | pcs | 800 | 32000 | Shopping | 20-calendar days 30-calendar days 30-calendar days 30-calendar days 30-calendar days 30-calendar days 30-calendar days 30-calendar days 5-10 working days upon reeived of PO | 40
| Printing Services (Camouflage Print 2) | 1 lot | 1 | lot | 33000 | 33000 | Shopping |  | 1
| Sewing Services for the Battle Dress Uniform | 10 lots | 10 | lots | 3000 | 30000 | Shopping |  | 10
| Professional Weaving Services (Natural Textile Fiber (NTF) blended yarns) | 200 lots | 200 | lots | 150 | 30000 | Shopping |  | 200
| Abrasion Resistance | 3 samples | 3 | samples | 800 | 2400 | Agency to Agency | 20-calendar days | 3
| Strength and Elongation (single strand, ASTM D 2256 / ASTM D 2256 M) | 3 samples | 3 | samples | 700 | 2100 |  |  | 3
| Evenness (ASTM D 1425 / ASTM D 1425M) | 3 samples | 3 | samples | 1100 | 3300 |  |  | 3
| Hairiness (ASTM D 5647) | 3 samples | 3 | samples | 1100 | 3300 |  |  | 3
| Yarn shrinkage (oven, ASTM D 2259 single yarns) | 3 samples | 3 | samples | 700 | 2100 |  |  | 3
| Yarn number (Skein, ASTM D 1907) | 3 samples | 3 | samples | 400 | 1200 |  |  | 3
| Yarn twist (single, ASTM D 1423) | 3 samples | 3 | samples | 700 | 2100 |  |  | 3
| 10 Raw data files |  | 3 | samples | 600 | 1800
| FESEM Imaging | 25 samples | 6 | samples | 8000 | 48000 |  | 30-calendar days |  | 25
| Thermogravimetric Analysis | 25 samples | 6 | samples | 3500 | 21000 |  |  |  | 25
| Differential Scanning Calorimetry | 25 samples | 6 | samples | 3000 | 18000 |  |  |  | 25
Laboratory Supplies Expenses
| Office Partition |  | 2 | lots | 20000 | 40000 | Shopping | 30-calendar days | 2
| Sodium Hydroxide,CAS # 1310-73-2, AR grade, 1 kg/bottle | 15 btls | 15 | btls | 3000 | 45000 | Negotaited - Small Value Procurement | 30-calendar days |  | 15
| Sodium Sulfite, anhydrous, AR grade, CAS # 7757-83-7, 500 g/bottle | 15 btls | 15 | btls | 2000 | 30000 |  |  |  | 15
| Acetone, CAS # 67-64-1, AR Grade, 2.5 L/bottle | 10 btls | 10 | btls | 4999 | 49990 | Negotaited - Small Value Procurement | 30-calendar days |  | 10
| Nitrile Gloves (Medium) | 10 boxes | 10 | boxes | 300 | 3000 | Shopping | 30-calendar days |  | 10
| Nitrile Gloves (Large) | 10 boxes | 10 | boxes | 300 | 3000 |  |  |  | 10
| Labgown (Medium) | 6 pcs | 6 | pcs | 500 | 3000 |  |  |  | 2
| Labgown (Large) | 6 pcs | 6 | pcs | 500 | 3000 |  |  |  | 2
| Beakers, borosilicate glass, 2L | 20 pcs | 20 | pcs | 1300 | 26000 | Negotaited - Small Value Procurement | 30-calendar days |  | 20
| Beakers, borosilicate glass, 1L | 15 pcs | 15 | pcs | 800 | 12000 |  |  |  | 15
| Beakers, borosilicate glass, 500 mL | 15 pcs | 15 | pcs | 250 | 3750 |  |  |  | 15
| Graduated cylinder, borosilicate glass, 1L |  | 10 | pcs | 2400 | 24000 |  |  |  | 10
| Graduated cylinder, borosilicate glass, 500 mL |  | 10 | pcs | 2000 | 20000 |  |  |  | 10
| Graduated cylinder, borosilicate glass, 100 mL |  | 10 | pcs | 1000 | 10000 |  |  |  | 10
| Gooch Glass Filter | 24 pcs | 24 | pcs | 2500 | 60000 |  |  |  | 24
Other Supplies and Materials Expenses
| Customized Certificate Holder | 20 pcs | 20 | pcs | 500 | 10000 | Shopping | 30-calendar days | 20
| Bag Tag | 20 pcs | 20 | pcs | 300 | 6000 |  |  | 20
| Upgraded Box Packaging | 20 pcs | 20 | pcs | 200 | 4000 |  |  | 20
| Infinity scarf | 10 pcs | 10 | pcs | 500 | 5000 |  |  | 10
| Headband belt | 10 pcs | 10 | pcs | 450 | 4500 |  |  | 10
| Bamboo Lei | 20 pcs | 20 | pcs | 430 | 8600 |  |  | 20
| Corrugated Box | 10 pcs | 10 | pcs | 65 | 650 |  |  | 10
| Sign Pen, Blue, 0.5mm | 30 pcs | 30 | pcs | 150 | 4500 | Shopping | 30-calendar days | 30
| Mobile Prepaid Load Cards (Smart – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960 | Shopping / Direct Retail | 30-calendar days | 40
| Mobile Prepaid Load Cards (Globe – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960 |  |  | 40
| P.E. Plastic Bag (20x30 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 2000 | 20000 | Negotiated Procurement-Small Value Procurement | 30-calendar days | 2
| P.E. Plastic Bag (25x50 inches, 0.002 inches (thickness) 50pcs/pack | 10 packs | 10 | packs | 2500 | 25000 |  |  | 2
| P.E. Plastic Bag (40x60 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 3000 | 30000 |  |  | 2
| Mask | 10 boxes | 10 | boxes | 200 | 2000 | Shopping | 30-calendar days | 10
| Facial Tissue | 10 packs | 10 | packs | 200 | 2000 |  |  | 10
| Rolled Tissue | 10 packs | 10 | packs | 200 | 2000 |  |  | 10
| Ziplock (Small) | 10 packs | 10 | packs | 200 | 2000 |  |  | 10
| Ziplock (Medium) | 10 packs | 10 | packs | 250 | 2500 |  |  | 10
| Ziplock (Large) | 10 packs | 10 | packs | 350 | 3500 |  |  | 10
| Ziplock (Extra Large) | 10 packs | 10 | packs | 400 | 4000 |  |  | 10
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
| Office Equipment |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
| Laboratory Equipment |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
| Paper fastener, 2" thick, metal, 70mm between prongs |  | 30 | boxes | 100 | 3000 | Shopping | 30-calendar days |  |  | 30
| Sticky Note, 2"x3" size, color yellow |  | 20 | pcs. | 30 | 600 |  |  |  |  | 20
| Sticky Note, 3"x3" size, color yellow |  | 20 | pcs. | 50 | 1000 |  |  |  |  | 20
| Folder with tab legal, 100pcs/pack |  | 2 | packs | 400 | 800 |  |  |  |  | 2
| Rubber band, No. 18 |  | 2 | boxes | 200 | 400 |  |  |  |  | 2
| Pressboard folder, 100pcs/box |  | 1 | box | 800 | 800 |  |  |  |  | 1
| DATA FOLDER, made of chipboard, taglia lock |  | 40 | pcs. | 150 | 6000 |  |  |  |  | 40
| Office Supply and Equipment | Office Supply and Equipment
| Customized Corporate Polo Shirt with Logo Embroidery Material: Honeycomb Logo Embroidery: COMBATex Program Logo, PTRI Fabric Color: Battle Green/Army Green Various Sizes: -Small: Six (6) pieces -Medium: Twelve (12) pieces -Large: Eleven (11) pieces -Extra Large: Eight (8) pieces -Double Extra Large: Three (3) pieces Delivery Period: 30 Calendar days | Customized Corporate Polo Shirt with Logo Embroidery Material: Honeycomb Logo Embroidery: COMBATex Program Logo, PTRI Fabric Color: Battle Green/Army Green Various Sizes: -Small: Six (6) pieces -Medium: Twelve (12) pieces -Large: Eleven (11) pieces -Extra Large: Eight (8) pieces -Double Extra Large: Three (3) pieces Delivery Period: 30 Calendar days | 40 | pcs. | 800 | 32000 | [5 empty] | 24/02-0048 dtd. 2-16-2024 | 0210-24 dtd. 2-16-2024
| Office Services | Office Supply and Equipment |  |  | 0
| Sewing Services for the Battle Dress Uniform Inclusions: Pattern/ cut/ sewn complete set of military uniform (jacket, pants, and ball cap) Material: Lyocell/Bamboo fabrics Turn Around Time: 10 calendar days |  | 1 | lot | 3000 | 3000
| Laboratory Equipment | Laboratory Equipment |  |  | 0
| Electrical Cables; Royal Cord, 3 Core | 2 units | 2 | units | 7200 | 14400 | Small Value Procurement |  |  | 2
| Electrical Breaker | 6 units | 6 | units | 500 | 3000 | Small Value Procurement |  |  | 6
| Uninterruptible Power Supply | 2 units | 2 | units | 10000 | 20000 | Small Value Procurement |  |  | 1
| Brown cones |  | 600 | pcs | 80 | 48000 | Small Value Procurement |  |  | 600
| SSD external hard drive | 3 pcs | 3 | pcs | 10000 | 30000 | Small Value Procurement |  |  | 3
| Industrial air compressor |  | 1 | lot | 49000 | 49000 | Small Value Procurement |  |  | 1
| Industrial filter paper, 60x60 cm | 5 packs | 5 | packs | 9999 | 49995 | Small Value Procurement |  |  | 10
| Parafilm | 10 rolls | 10 | rolls | 4000 | 40000 | Small Value Procurement |  |  | 10
| Customized stainless bucket with cover and water tap | 6 pcs | 6 | pcs | 7000 | 42000 | Small Value Procurement |  |  | 6
Cash Advance
| Courier Fee -From: DOST-PTRI, Bicutan, Taguig City To: BIG PIX Graphics System, 8837 Sampaloc St., San Antonio Village, Makati City | Courier Fee -From: DOST-PTRI, Bicutan, Taguig City To: BIG PIX Graphics System, 8837 Sampaloc St., San Antonio Village, Makati City | 1 lot | 200 | 200 | Cash Advance |  |  | 1 |  | 24/01 0046 dtd. 01-23-2024
| Courier Fee From: BIG PIX Graphics System, 8837 Sampaloc St., San Antonio Village, Makati City To: DOST-PTRI, Bicutan, Taguig City | Courier Fee From: BIG PIX Graphics System, 8837 Sampaloc St., San Antonio Village, Makati City To: DOST-PTRI, Bicutan, Taguig City | 1 lot | 200 | 200 | Cash Advance
| Courier Fee -From: DOST-PTRI, Bicutan, Taguig City To: Research and Development Center, Army Support Command, Philippine Army Address: Camp Alejandro Melchor Sr., Libis, Quezon | Courier Fee -From: DOST-PTRI, Bicutan, Taguig City To: Research and Development Center, Army Support Command, Philippine Army Address: Camp Alejandro Melchor Sr., Libis, Quezon | 1 lot | 200 | 200 | Cash Advance |  |  | 1 |  | 24/02 0056 dtd. 02-07-2024
| Black Ink BTD60 for HL-T4000DW printer (Ink bottle twin pack) | Black Ink BTD60 for HL-T4000DW printer (Ink bottle twin pack) | 1 pack | 680 | 680 | Petty Cash Fund
| Sewing Services for the Battle Dress Uniform | Sewing Services for the Battle Dress Uniform | 1 lot | 3000 | 3000 | Petty Cash Fund |  |  | 1
| Payment for the Application Fee of Waiver under PD 1466 to DTI-FTEB | Payment for the Application Fee of Waiver under PD 1466 to DTI-FTEB | 1 lot | 330 | 330 | Petty Cash Fund |  |  |  |  | 24/02 055 dtd. 02-07-2023
| AM Snacks Date: February 16, 2024 Event: Meeting with PNP-EOD/K9 Group Time: 10:00 AM to 12:00 PM Place: TELA Conference, DOST-PTRI | AM Snacks Date: February 16, 2024 Event: Meeting with PNP-EOD/K9 Group Time: 10:00 AM to 12:00 PM Place: TELA Conference, DOST-PTRI | 20 pax | 100 | 2000 | Cash Advance |  |  |  |  | 2402/0073 dtd. 02-16-2024
| Meals Lunch Date: February 16, 2024 Event: Meeting with PNP-EOD/K9 Group Time: 10:00 AM to 12:00 PM Place: TELA Conference, DOST-PTRI | Meals Lunch Date: February 16, 2024 Event: Meeting with PNP-EOD/K9 Group Time: 10:00 AM to 12:00 PM Place: TELA Conference, DOST-PTRI | 20 pax | 150 | 3000
| Transportation and Delivery Expense -To conduct facility visit and stakeholder engagement with Philippine Army -Date: 21 February 2024, Wednesday -From: DOST-PTRI, General Santos Avenue, Bicutan, Taguig City -To: Research and Development Center, Army Support Command, Philippine Army Camp Alejandro Melchor Sr., Libis, Quezon City -Vice Versa Passengers: 1. Gilbert E. Bueno 2. Paul Angelo C. Manlapaz 3. Arnold S. Hermosura | Transportation and Delivery Expense -To conduct facility visit and stakeholder engagement with Philippine Army -Date: 21 February 2024, Wednesday -From: DOST-PTRI, General Santos Avenue, Bicutan, Taguig City -To: Research and Development Center, Army Support Command, Philippine Army Camp Alejandro Melchor Sr., Libis, Quezon City -Vice Versa Passengers: 1. Gilbert E. Bueno 2. Paul Angelo C. Manlapaz 3. Arnold S. Hermosura | 1 lot | 2000 | 2000 | Cash Advance |  |  | 1 |  | 2402/0079 dtd. 02-21-2024 | n/a |  |  | n/a | n/a | GRAB CAR | 1275
| Ammonium Iron (II) Sulfate Hexahydrate, 500 g, AR, CAS # 7783-85-9 1, 10-Phenanthroline Monohydrate, 5g, AR, 5144-89-8 | Ammonium Iron (II) Sulfate Hexahydrate, 500 g, AR, CAS # 7783-85-9 1, 10-Phenanthroline Monohydrate, 5g, AR, 5144-89-8 | 10 bottles 10 bottles | 3,000.00 1,800.00 | 48000 | Shopping | 5-10 working days upon reeived of PO |  |  |  | 2309-2131 dtd. 09-22-2023 | 2183-23 dtd. 09-26-2023 |  |  | 23-1006 dtd. 11-8-2023 | 2311-1230 dtd. 11-28-2023 | ALDERCHEM TRADING | 20000 | 20000
TOTAL BUDGET: |  | 1059205
+ 10% Provision for Inflation |  | 105920.5
+ 10% Contingency |  | 105920.5
TOTAL ESTIMATED BUDGET: |  | 1271046
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: | [6 empty] | Recommending Approval: | [7 empty] | Approved by:
________________________ |  |  | MARILOU G. AGUSTIN | [6 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, Property, Procurement and General Services Section | [6 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  |  | Date: ______________________ | [6 empty] | Date: ______________________ | [7 empty] | Date: ______________________

## JAN - MARCH 2024 (hidden)
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
END-USER/UNIT: RDD-CDABUS
Charged to: “Functional Philippine Camouflage Fabric for Field Service Uniform(FSU)/ Battle Dress Unifom(BDU) Application”
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | QUANTITY/ | UNIT OF MEASURE | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE | SIZE | [5 empty] | Jan | Feb | Mar | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
Other Professional Services
| Customized Corporate Polo Shirt with Logo Embroidery | 40 pcs. | 40 | pcs | 800 | 32000 | Shopping | 20-calendar days 30-calendar days 30-calendar days 30-calendar days 30-calendar days 30-calendar days 30-calendar days 30-calendar days 5-10 working days upon reeived of PO | 40
| Printing Services (Camouflage Print 2) | 1 lot | 1 | lot | 33000 | 33000 | Shopping |  | 1
| Sewing Services for the Battle Dress Uniform | 10 lots | 10 | lots | 3000 | 30000 | Shopping |  | 10
| Professional Weaving Services (Natural Textile Fiber (NTF) blended yarns) | 200 lots | 200 | lots | 150 | 30000 | Shopping |  | 200
| Abrasion Resistance | 3 samples | 3 | samples | 800 | 2400 | Agency to Agency | 20-calendar days | 3
| Strength and Elongation (single strand, ASTM D 2256 / ASTM D 2256 M) | 3 samples | 3 | samples | 700 | 2100 |  |  | 3
| Evenness (ASTM D 1425 / ASTM D 1425M) | 3 samples | 3 | samples | 1100 | 3300 |  |  | 3
| Hairiness (ASTM D 5647) | 3 samples | 3 | samples | 1100 | 3300 |  |  | 3
| Yarn shrinkage (oven, ASTM D 2259 single yarns) | 3 samples | 3 | samples | 700 | 2100 |  |  | 3
| Yarn number (Skein, ASTM D 1907) | 3 samples | 3 | samples | 400 | 1200 |  |  | 3
| Yarn twist (single, ASTM D 1423) | 3 samples | 3 | samples | 700 | 2100 |  |  | 3
| 10 Raw data files |  | 3 | samples | 600 | 1800
| FESEM Imaging | 25 samples | 6 | samples | 8000 | 48000 |  | 30-calendar days |  | 25
| Thermogravimetric Analysis | 25 samples | 6 | samples | 3500 | 21000 |  |  |  | 25
| Differential Scanning Calorimetry | 25 samples | 6 | samples | 3000 | 18000 |  |  |  | 25
Laboratory Supplies Expenses
| Office Partition |  | 2 | lots | 20000 | 40000 | Shopping | 30-calendar days | 2
| Sodium Hydroxide,CAS # 1310-73-2, AR grade, 1 kg/bottle | 15 btls | 15 | btls | 3000 | 45000 | Negotaited - Small Value Procurement | 30-calendar days |  | 15
| Sodium Sulfite, anhydrous, AR grade, CAS # 7757-83-7, 500 g/bottle | 15 btls | 15 | btls | 2000 | 30000 |  |  |  | 15
| Acetone, CAS # 67-64-1, AR Grade, 2.5 L/bottle | 10 btls | 10 | btls | 4999 | 49990 | Negotaited - Small Value Procurement | 30-calendar days |  | 10
| Nitrile Gloves (Medium) | 10 boxes | 10 | boxes | 300 | 3000 | Shopping | 30-calendar days |  | 10
| Nitrile Gloves (Large) | 10 boxes | 10 | boxes | 300 | 3000 |  |  |  | 10
| Labgown (Medium) | 6 pcs | 6 | pcs | 500 | 3000 |  |  |  | 2
| Labgown (Large) | 6 pcs | 6 | pcs | 500 | 3000 |  |  |  | 2
| Beakers, borosilicate glass, 2L | 20 pcs | 20 | pcs | 1300 | 26000 | Negotaited - Small Value Procurement | 30-calendar days |  | 20
| Beakers, borosilicate glass, 1L | 15 pcs | 15 | pcs | 800 | 12000 |  |  |  | 15
| Beakers, borosilicate glass, 500 mL | 15 pcs | 15 | pcs | 250 | 3750 |  |  |  | 15
| Graduated cylinder, borosilicate glass, 1L |  | 10 | pcs | 2400 | 24000 |  |  |  | 10
| Graduated cylinder, borosilicate glass, 500 mL |  | 10 | pcs | 2000 | 20000 |  |  |  | 10
| Graduated cylinder, borosilicate glass, 100 mL |  | 10 | pcs | 1000 | 10000 |  |  |  | 10
| Gooch Glass Filter | 24 pcs | 24 | pcs | 2500 | 60000 |  |  |  | 24
Other Supplies and Materials Expenses
| Customized Certificate Holder | 20 pcs | 20 | pcs | 500 | 10000 | Shopping | 30-calendar days | 20
| Bag Tag | 20 pcs | 20 | pcs | 300 | 6000 |  |  | 20
| Upgraded Box Packaging | 20 pcs | 20 | pcs | 200 | 4000 |  |  | 20
| Infinity scarf | 10 pcs | 10 | pcs | 500 | 5000 |  |  | 10
| Headband belt | 10 pcs | 10 | pcs | 450 | 4500 |  |  | 10
| Bamboo Lei | 20 pcs | 20 | pcs | 430 | 8600 |  |  | 20
| Corrugated Box | 10 pcs | 10 | pcs | 65 | 650 |  |  | 10
| Sign Pen, Blue, 0.5mm | 30 pcs | 30 | pcs | 150 | 4500 | Shopping | 30-calendar days | 30
| Mobile Prepaid Load Cards (Smart – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960 | Shopping / Direct Retail | 30-calendar days | 40
| Mobile Prepaid Load Cards (Globe – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960 |  |  | 40
| P.E. Plastic Bag (20x30 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 2000 | 20000 | Negotiated Procurement-Small Value Procurement | 30-calendar days | 2
| P.E. Plastic Bag (25x50 inches, 0.002 inches (thickness) 50pcs/pack | 10 packs | 10 | packs | 2500 | 25000 |  |  | 2
| P.E. Plastic Bag (40x60 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 3000 | 30000 |  |  | 2
| Mask | 10 boxes | 10 | boxes | 200 | 2000 | Shopping | 30-calendar days | 10
| Facial Tissue | 10 packs | 10 | packs | 200 | 2000 |  |  | 10
| Rolled Tissue | 10 packs | 10 | packs | 200 | 2000 |  |  | 10
| Ziplock (Small) | 10 packs | 10 | packs | 200 | 2000 |  |  | 10
| Ziplock (Medium) | 10 packs | 10 | packs | 250 | 2500 |  |  | 10
| Ziplock (Large) | 10 packs | 10 | packs | 350 | 3500 |  |  | 10
| Ziplock (Extra Large) | 10 packs | 10 | packs | 400 | 4000 |  |  | 10
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
| Office Equipment |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
| Laboratory Equipment |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
|  |  |  | #N/A |  | 0
| Paper fastener, 2" thick, metal, 70mm between prongs |  | 30 | boxes | 100 | 3000 | Shopping | 30-calendar days |  |  | 30
| Sticky Note, 2"x3" size, color yellow |  | 20 | pcs. | 30 | 600 |  |  |  |  | 20
| Sticky Note, 3"x3" size, color yellow |  | 20 | pcs. | 50 | 1000 |  |  |  |  | 20
| Folder with tab legal, 100pcs/pack |  | 2 | packs | 400 | 800 |  |  |  |  | 2
| Rubber band, No. 18 |  | 2 | boxes | 200 | 400 |  |  |  |  | 2
| Pressboard folder, 100pcs/box |  | 1 | box | 800 | 800 |  |  |  |  | 1
| DATA FOLDER, made of chipboard, taglia lock |  | 40 | pcs. | 150 | 6000 |  |  |  |  | 40
| Office Supply and Equipment | Office Supply and Equipment
| Customized Corporate Polo Shirt with Logo Embroidery Material: Honeycomb Logo Embroidery: COMBATex Program Logo, PTRI Fabric Color: Battle Green/Army Green Various Sizes: -Small: Six (6) pieces -Medium: Twelve (12) pieces -Large: Eleven (11) pieces -Extra Large: Eight (8) pieces -Double Extra Large: Three (3) pieces Delivery Period: 30 Calendar days | Customized Corporate Polo Shirt with Logo Embroidery Material: Honeycomb Logo Embroidery: COMBATex Program Logo, PTRI Fabric Color: Battle Green/Army Green Various Sizes: -Small: Six (6) pieces -Medium: Twelve (12) pieces -Large: Eleven (11) pieces -Extra Large: Eight (8) pieces -Double Extra Large: Three (3) pieces Delivery Period: 30 Calendar days | 40 | pcs. | 800 | 32000 | [5 empty] | 24/02-0048 dtd. 2-16-2024 | 0210-24 dtd. 2-16-2024
| Office Services | Office Supply and Equipment |  |  | 0
| Sewing Services for the Battle Dress Uniform Inclusions: Pattern/ cut/ sewn complete set of military uniform (jacket, pants, and ball cap) Material: Lyocell/Bamboo fabrics Turn Around Time: 10 calendar days |  | 1 | lot | 3000 | 3000
| Laboratory Equipment | Laboratory Equipment |  |  | 0
| Electrical Cables; Royal Cord, 3 Core | 2 units | 2 | units | 7200 | 14400 | Small Value Procurement |  |  | 2
| Electrical Breaker | 6 units | 6 | units | 500 | 3000 | Small Value Procurement |  |  | 6
| Uninterruptible Power Supply | 2 units | 2 | units | 10000 | 20000 | Small Value Procurement |  |  | 1
| Brown cones |  | 600 | pcs | 80 | 48000 | Small Value Procurement |  |  | 600
| SSD external hard drive | 3 pcs | 3 | pcs | 10000 | 30000 | Small Value Procurement |  |  | 3
| Industrial air compressor |  | 1 | lot | 49000 | 49000 | Small Value Procurement |  |  | 1
| Industrial filter paper, 60x60 cm | 5 packs | 5 | packs | 9999 | 49995 | Small Value Procurement |  |  | 10
| Parafilm | 10 rolls | 10 | rolls | 4000 | 40000 | Small Value Procurement |  |  | 10
| Customized stainless bucket with cover and water tap | 6 pcs | 6 | pcs | 7000 | 42000 | Small Value Procurement |  |  | 6
Cash Advance
| Courier Fee -From: DOST-PTRI, Bicutan, Taguig City To: BIG PIX Graphics System, 8837 Sampaloc St., San Antonio Village, Makati City | Courier Fee -From: DOST-PTRI, Bicutan, Taguig City To: BIG PIX Graphics System, 8837 Sampaloc St., San Antonio Village, Makati City | 1 lot | 200 | 200 | Cash Advance |  |  | 1 |  | 24/01 0046 dtd. 01-23-2024
| Courier Fee From: BIG PIX Graphics System, 8837 Sampaloc St., San Antonio Village, Makati City To: DOST-PTRI, Bicutan, Taguig City | Courier Fee From: BIG PIX Graphics System, 8837 Sampaloc St., San Antonio Village, Makati City To: DOST-PTRI, Bicutan, Taguig City | 1 lot | 200 | 200 | Cash Advance
| Courier Fee -From: DOST-PTRI, Bicutan, Taguig City To: Research and Development Center, Army Support Command, Philippine Army Address: Camp Alejandro Melchor Sr., Libis, Quezon | Courier Fee -From: DOST-PTRI, Bicutan, Taguig City To: Research and Development Center, Army Support Command, Philippine Army Address: Camp Alejandro Melchor Sr., Libis, Quezon | 1 lot | 200 | 200 | Cash Advance |  |  | 1 |  | 24/02 0056 dtd. 02-07-2024
| Black Ink BTD60 for HL-T4000DW printer (Ink bottle twin pack) | Black Ink BTD60 for HL-T4000DW printer (Ink bottle twin pack) | 1 pack | 680 | 680 | Petty Cash Fund
| Sewing Services for the Battle Dress Uniform | Sewing Services for the Battle Dress Uniform | 1 lot | 3000 | 3000 | Petty Cash Fund |  |  | 1
| Payment for the Application Fee of Waiver under PD 1466 to DTI-FTEB | Payment for the Application Fee of Waiver under PD 1466 to DTI-FTEB | 1 lot | 330 | 330 | Petty Cash Fund |  |  |  |  | 24/02 055 dtd. 02-07-2023
| AM Snacks Date: February 16, 2024 Event: Meeting with PNP-EOD/K9 Group Time: 10:00 AM to 12:00 PM Place: TELA Conference, DOST-PTRI | AM Snacks Date: February 16, 2024 Event: Meeting with PNP-EOD/K9 Group Time: 10:00 AM to 12:00 PM Place: TELA Conference, DOST-PTRI | 20 pax | 100 | 2000 | Cash Advance |  |  |  |  | 2402/0073 dtd. 02-16-2024
| Meals Lunch Date: February 16, 2024 Event: Meeting with PNP-EOD/K9 Group Time: 10:00 AM to 12:00 PM Place: TELA Conference, DOST-PTRI | Meals Lunch Date: February 16, 2024 Event: Meeting with PNP-EOD/K9 Group Time: 10:00 AM to 12:00 PM Place: TELA Conference, DOST-PTRI | 20 pax | 150 | 3000
| Transportation and Delivery Expense -To conduct facility visit and stakeholder engagement with Philippine Army -Date: 21 February 2024, Wednesday -From: DOST-PTRI, General Santos Avenue, Bicutan, Taguig City -To: Research and Development Center, Army Support Command, Philippine Army Camp Alejandro Melchor Sr., Libis, Quezon City -Vice Versa Passengers: 1. Gilbert E. Bueno 2. Paul Angelo C. Manlapaz 3. Arnold S. Hermosura | Transportation and Delivery Expense -To conduct facility visit and stakeholder engagement with Philippine Army -Date: 21 February 2024, Wednesday -From: DOST-PTRI, General Santos Avenue, Bicutan, Taguig City -To: Research and Development Center, Army Support Command, Philippine Army Camp Alejandro Melchor Sr., Libis, Quezon City -Vice Versa Passengers: 1. Gilbert E. Bueno 2. Paul Angelo C. Manlapaz 3. Arnold S. Hermosura | 1 lot | 2000 | 2000 | Cash Advance |  |  | 1 |  | 2402/0079 dtd. 02-21-2024 | n/a |  |  | n/a | n/a | GRAB CAR | 1275
TOTAL BUDGET: |  | 1059205
+ 10% Provision for Inflation |  | 105920.5
+ 10% Contingency |  | 105920.5
TOTAL ESTIMATED BUDGET: |  | 1271046
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: | [6 empty] | Recommending Approval: | [7 empty] | Approved by:
________________________ |  |  | MARILOU G. AGUSTIN | [6 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, Property, Procurement and General Services Section | [6 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  |  | Date: ______________________ | [6 empty] | Date: ______________________ | [7 empty] | Date: ______________________

## APRIL - JUNE 2024
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
END-USER/UNIT: RDD-CDABUS
Charged to: “Functional Philippine Camouflage Fabric for Field Service Uniform(FSU)/ Battle Dress Unifom(BDU) Application”
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | QUANTITY/ | UNIT OF MEASURE | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE | SIZE | [5 empty] | Apr | May | Jun | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
Other Professional Services
| FESEM Imaging | 19 | 25 | sample | 8000 | 200000 | Agency to Agency | 30-calendar days
| Thermogravimetric Analysis | 19 | 25 | sample | 3500 | 87500
| Differential Scanning Calorimetry | 19 | 25 | sample | 3000 | 75000
| Abrasion Resistance | 3 samples | 15 | samples | 800 | 12000 | Agency to Agency
| Strength and Elongation (single strand, ASTM D 2256 / ASTM D 2256 M) | 3 samples | 15 | samples | 700 | 10500
| Evenness (ASTM D 1425 / ASTM D 1425M) | 3 samples | 15 | samples | 1100 | 16500
| Hairiness (ASTM D 5647) | 3 samples | 15 | samples | 1100 | 16500
| Yarn shrinkage (oven, ASTM D 2259 single yarns) | 3 samples | 15 | samples | 700 | 10500
| Yarn number (Skein, ASTM D 1907) | 3 samples | 15 | samples | 400 | 6000
| Yarn twist (single, ASTM D 1423) | 3 samples | 15 | samples | 700 | 10500
| Raw data files |  | 15 | samples | 600 | 9000
| Printing Services (Camouflage Print) | 1 lot | 1 | lot | 33000 | 33000 | Negotaited Procurement | 30-calendar days
| Printing Services (DTF/DTG Print) |  | 40 | yards | 3000 | 120000 | Negotaited Procurement | 30-calendar days
| Sewing Services for the Battle Dress Uniform | 10 lots | 10 | lots | 3000 | 30000 | Shopping | 30-calendar days
| Professional Weaving Services (Natural Textile Fiber (NTF) blended yarns) | 200 lots | 200 | lots | 150 | 30000 | Shopping | 30-calendar days
| Abrasion Resistance (ASTM D 3885) - 1st 10,000 |  | 10 | samples | 1000 | 10000 | Agency to Agency | 30-calendar days
| Breaking Strength (ISO 13934-2 / ASTM D5034) |  | 10 | samples | 800 | 8000
| Type of Weave or Knit (ISO 3572) |  | 10 | samples | 500 | 5000
| Yarn Number (ISO 7211/5, ASTM D1059) - Short Length |  | 10 | samples | 700 | 7000
| Thread Count (ASTM D 3775) |  | 10 | samples | 400 | 4000
| Fabric Weight / Mass Per Unit Area (ISO 3801, ASTM D 3776/D 3776M) |  | 10 | samples | 500 | 5000
| Piling Resistance (ASTM D 3512, ASTM D 3512M) - Random Tumble |  | 10 | samples | 800 | 8000
| Thickness (ISO 5084, ASTM D 1777) |  | 10 | samples | 600 | 6000
| Fiber Composition (AATCC TM 20A) |  | 10 | samples | 1600 | 16000
| Colorfastness to Rubbing for Fabrics (ISO 105-X12, AATCC TM8) |  | 10 | samples | 600 | 6000
| Colorfastness to Laundering (ISO 105-CO6, AATCC TM 61, JIS L 0844); per additional color |  | 10 | samples | 1100 | 11000
| Colorfastness to Perspiration (ISO 105-EO4, AATCC TM 15, JIS L 0848); per additional color |  | 10 | samples | 1200 | 12000
| Color Difference (AATCC EP 6) |  | 10 | samples | 600 | 6000
| Color Quality (AATCC EP 6) |  | 10 | samples | 600 | 6000
| Dimensional Change ISO 6330 : 2012 |  | 10 | samples | 800 | 8000
| Tearing Strength ASTM D2261-13 |  | 10 | samples | 1600 | 16000
| Sewing Services for the ROTC Fatigue Uniform |  | 2 | lot | 5000 | 10000
Laboratory Supplies Expenses
| Iron (II) Sulfate Heptahydrate, AR 500g per bottle. CAS No. 7782-63-0 |  | 3 | bottles | 3500 | 10500 | Small Value Procurement | 30-calendar days
| 1,10-Phenanthroline AR 500g, CAS No. 66-71-7 |  | 3 | bottles | 4000 | 12000
| Ferrous Ammonium Sulfate, AR Grade 500g per bottle, CAS No. 7783-85-9 |  | 5 | bottles | 3500 | 17500
| Sodium Thiosulfate, AR 500g per bottle, CAS No. 7772-98-7 |  | 3 | bottles | 3500 | 10500
| Pottasium Iodide, AR 500g per bottle, CAS No. 7681-11-0 |  | 3 | bottles | 3000 | 9000
| Sodium Chloride, AR Grade, CAS No. 7758-19-2, 500g per bottle |  | 80 | Bottle | 3000 | 240000
| Pottasium Dichromate, AR 500g per bottel, CAS No. 7778-50-9 |  | 3 | bottles | 3000 | 9000
| Pottasium Hydrogen Phosphate, AR Grade 500g per bottle, CAS No. 7778-77-0 |  | 3 | bottles | 2500 | 7500
| Phenolphthalein, AR Grade 500g per bottle, CAS No. 77-09-8 |  | 2 | bottles | 2500 | 5000
| Sodium Hydroxide, liquid, 48-50%, TG, 25-30 kg/carbuoy |  | 100 | cby | 2500 | 250000 | Small Value Procurement | 30-calendar days
| Sodium Silicate, TG, 20 L/carbuoy |  | 60 | cby | 3000 | 180000
| Sodium Metabisulfite, TG, 25 kg/bag |  | 60 | bag | 5000 | 300000
| Glacial Acetic Acid, TG, 30 kg/carbuoy |  | 60 | cby | 6500 | 390000
| Hydrogen Peroxide, TG, 30 kg/carbuoy |  | 60 | cby | 6500 | 390000 | Small Value Procurement | 30-calendar days
| Sulfuric Acid, 95-98%, AR Grade, 2.5 L per bottle |  | 6 | Bottle | 2500 | 15000
| Acetone, CAS # 67-64-1, AR Grade, 2.5 L/bottle | 10 btls | 30 | btls | 5500 | 165000
| Hydrochloric Acid, 36%, AR Grade, 2.5 L per bottle |  | 6 | Bottle | 2500 | 15000
| Bleaching solution |  | 80 | gallons | 500 | 40000 | Small Value Procurement | 30-calendar days
| Non-ionic wetting agent |  | 100 | gallons | 800 | 80000
| Fabric Softener |  | 50 | sack | 1200 | 60000
| Liquid Handsoap |  | 20 | Bottle | 500 | 10000
| Disinfectant Spray |  | 30 | Bottle | 800 | 24000
| Sodium Carbonate, AR Grade, 500 g per bottle |  | 20 | Bottle | 2500 | 50000 | Small Value Procurement | 30-calendar days
| Sodium Bicarbonate, AR Grade, 500 g per bottle |  | 20 | Bottle | 2000 | 40000
| Sodium Hydroxide,CAS # 1310-73-2, AR grade, 1 kg/bottle | 15 btls | 60 | btls | 4000 | 240000
| Sodium Sulfite, anhydrous, AR grade, CAS # 7757-83-7, 500 g/bottle | 15 btls | 60 | btls | 2500 | 150000
| Pectinase Enzyme, 1 L per Bottle |  | 50 | btls | 5500 | 275000 | Agency to Agency | 30-calendar days
| Xylanase Enzyme, 1 L per Bottle |  | 50 | btls | 5500 | 275000
| Beakers, borosilicate glass, 2L | 20 pcs | 20 | pcs | 1300 | 26000 | Negotaited - Small Value Procurement | 30-calendar days
| Beakers, borosilicate glass, 1L | 15 pcs | 15 | pcs | 800 | 12000
| Beakers, borosilicate glass, 500 mL | 15 pcs | 15 | pcs | 250 | 3750
| Graduated cylinder, borosilicate glass, 1L |  | 10 | pcs | 2400 | 24000
| Graduated cylinder, borosilicate glass, 500 mL |  | 10 | pcs | 2000 | 20000
| Graduated cylinder, borosilicate glass, 100 mL |  | 10 | pcs | 1000 | 10000
| Gooch Glass Filter | 24 pcs | 24 | pcs | 2500 | 60000
| Reagent bottle, clear, borosilicate glass, 1L |  | 15 | pcs | 1000 | 15000
| Reagent bottle, clear, borosilicate glass, 500 mL |  | 15 | pcs | 2000 | 30000
| Reagent bottle, amber, borosilicate glass, 1L |  | 15 | pcs | 1000 | 15000
| Reagent bottle, amber, borosilicate glass, 500 mL |  | 15 | pcs | 2000 | 30000
| Vacuum pump |  | 5 | pcs | 10000 | 50000 | Small Value Procurement | 30-calendar days
| Vacuum Desiccator, borosilicate glass |  | 2 | pcs | 25000 | 50000
| Set of Calibration Weights with Certificate and Case |  | 1 | set | 50000 | 50000 | Small Value Procurement | 30-calendar days
| LPG Tank/Fuel |  | 20 | tank | 5000 | 100000 | Small Value Procurement | 30-calendar days
| Lint-free wipes, Kimwipes |  | 30 | boxes | 500 | 15000 | Small Value Procurement | 30-calendar days
| Nitrile Gloves (Medium) | 10 boxes | 10 | boxes | 300 | 3000
| Nitrile Gloves (Large) | 10 boxes | 10 | boxes | 300 | 3000
Other Supplies and Materials Expenses
| Wi-Fi Duplex Wide-format All-in-One Ink Tank Printer |  | 2 | units | 40000 | 80000 | Small Value Procurement | 30-calendar days
| Office Partition |  | 6 | pcs | 20000 | 120000 | Small Value Procurement | 30-calendar days
| Ergonomic Mesh Chair |  | 12 | pcs | 7000 | 84000 |  | 30-calendar days
| Hair dryer/blower |  | 1 | pc | 3000 | 3000 |  | 30-calendar days
| Pull-up Tissue |  | 10 | boxes | 1100 | 11000 |  | 30-calendar days
| Customized Certificate Holder, legal size |  | 20 | pcs | 700 | 14000 |  | 30-calendar days
| Mannequin, Glass Fiber, with bag |  | 10 | pcs | 15000 | 150000 |  | 30-calendar days
| Transcriber |  | 3 | pcs | 2000 | 6000 | Shopping / Direct Retail | 30-calendar days
| Decorticated Banana Fibers |  | 300 | kg | 300 | 90000 | Small Value Procurement | 30-calendar days
| Raw Bamboo Fibers |  | 300 | kg | 300 | 90000 | Small Value Procurement | 30-calendar days
| Sign Pen, Blue, 0.5mm | 30 pcs | 30 | pcs | 150 | 4500 | Shopping | 30-calendar days
| Mobile Prepaid Load Cards (Smart – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960 | Shopping / Direct Retail | 30-calendar days
| Mobile Prepaid Load Cards (Globe – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960
| P.E. Plastic Bag (20x30 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 2000 | 20000 | Small Value Procurement | 30-calendar days
| P.E. Plastic Bag (25x50 inches, 0.002 inches (thickness) 50pcs/pack | 10 packs | 10 | packs | 2500 | 25000
| P.E. Plastic Bag (40x60 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 3000 | 30000
Training Expenses
| Registration Fee on APAM PAASE |  | 4 | pax | 5000 | 20000 | Shopping / Direct Retail
| Seminar on GHS Labelling, Storage, and Risk Assessment |  | 3 | pax | 2688 | 8064 | Shopping / Direct Retail
| Office Supply and Equipment | Office Supply and Equipment
| Name Plate Holder |  | 30 | pcs | 400 | 12000 | Shopping | 30-calendar days
| Laboratory Equipment | Laboratory Equipment
| Air Compressor |  | 1 | lot | 150000 | 150000
| Uninterruptible Power Supply |  | 2 | unit | 49999 | 99998 | Small Value Procurement
| Heavy-Duty Electrical Cable Wire, 14/2C, 1.5 sq. mm, 75-100m |  | 1 | roll | 8000 | 8000 | Small Value Procurement | 30-calendar days
| Heavy-Duty Electrical Cable Wire, 8/3C, 75-100m |  | 1 | roll | 8000 | 8000
| 60A Circuit Breaker, industrial type, automatic, three (3) phase |  | 4 | pc | 8000 | 32000
| 30A Circuit Breaker, industrial type, automatic, one (1) phase |  | 4 | pc | 5000 | 20000
| Polyurethane Air Pneumatic Hose, 75-100m |  | 1 | roll | 8000 | 8000
| PVC Pipe 1 1/2 in or 2 diameter inches |  | 6 | pc | 250 | 1500
| Heavy-Duty Electrical Cable Wire No. 8 |  | 3 | box | 8000 | 24000
| PVC Pipe Connector |  | 5 | pc | 100 | 500
| Electrical Tape |  | 2 | box | 1000 | 2000
| Clamp |  | 3 | pc | 100 | 300
| Lock nut for breaker |  | 3 | pc | 150 | 450
| Customized stainless bucket with cover and water tap | 6 pcs | 6 | pcs | 7000 | 42000 | Shopping | 30-calendar days
| Multi-Station Magnetic Hot Plate Stirrer |  | 2 | pcs | 150000 | 300000 | Small Value Procurement | 30-calendar days
| Brown cones |  | 2000 | pcs | 80 | 160000 | Small Value Procurement | 30-calendar days
| Laboratory Refrigerator |  | 1 | unit | 200000 | 200000 | Small Value Procurement | 30-calendar days
| Repair and Mentainance Expenses | Laboratory Equipment
| Repair and Mentainance Services |  | 1 | lot | 5000 | 5000 | Negotaited Procurement
TOTAL BUDGET: |  | 6442982
+ 10% Provision for Inflation |  | 644298.2
+ 10% Contingency |  | 644298.2
TOTAL ESTIMATED BUDGET: |  | 7731578.4
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: | [6 empty] | Recommending Approval: | [7 empty] | Approved by:
KIMBERLY P. VIRON |  |  | MARILOU G. AGUSTIN | [6 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, Property, Procurement and General Services Section | [6 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  |  | Date: ______________________ | [6 empty] | Date: ______________________ | [7 empty] | Date: ______________________

## Copy of APRIL - JUNE 2024 (hidden)
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
END-USER/UNIT: RDD-CDABUS
Charged to: “Functional Philippine Camouflage Fabric for Field Service Uniform(FSU)/ Battle Dress Unifom(BDU) Application”
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | QUANTITY/ | UNIT OF MEASURE | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE | SIZE | [5 empty] | Apr | May | Jun | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
Other Professional Services
| FESEM Imaging | 19 | 25 | sample | 8000 | 200000 | Agency to Agency | 30-calendar days
| Thermogravimetric Analysis | 19 | 25 | sample | 3500 | 87500
| Differential Scanning Calorimetry | 19 | 25 | sample | 3000 | 75000
| Abrasion Resistance | 3 samples | 15 | samples | 800 | 12000 | Agency to Agency
| Strength and Elongation (single strand, ASTM D 2256 / ASTM D 2256 M) | 3 samples | 15 | samples | 700 | 10500
| Evenness (ASTM D 1425 / ASTM D 1425M) | 3 samples | 15 | samples | 1100 | 16500
| Hairiness (ASTM D 5647) | 3 samples | 15 | samples | 1100 | 16500
| Yarn shrinkage (oven, ASTM D 2259 single yarns) | 3 samples | 15 | samples | 700 | 10500
| Yarn number (Skein, ASTM D 1907) | 3 samples | 15 | samples | 400 | 6000
| Yarn twist (single, ASTM D 1423) | 3 samples | 15 | samples | 700 | 10500
| Raw data files |  | 15 | samples | 600 | 9000
| Printing Services (Camouflage Print) | 1 lot | 1 | lot | 33000 | 33000 | Negotaited Procurement | 30-calendar days
| Printing Services (DTF/DTG Print) |  | 40 | yards | 3000 | 120000 | Negotaited Procurement | 30-calendar days
| Sewing Services for the Battle Dress Uniform | 10 lots | 10 | lots | 3000 | 30000 | Shopping | 30-calendar days
| Professional Weaving Services (Natural Textile Fiber (NTF) blended yarns) | 200 lots | 200 | lots | 150 | 30000 | Shopping | 30-calendar days
| Abrasion Resistance (ASTM D 3885) - 1st 10,000 |  | 10 | samples | 1000 | 10000 | Agency to Agency | 30-calendar days
| Breaking Strength (ISO 13934-2 / ASTM D5034) |  | 10 | samples | 800 | 8000
| Type of Weave or Knit (ISO 3572) |  | 10 | samples | 500 | 5000
| Yarn Number (ISO 7211/5, ASTM D1059) - Short Length |  | 10 | samples | 700 | 7000
| Thread Count (ASTM D 3775) |  | 10 | samples | 400 | 4000
| Fabric Weight / Mass Per Unit Area (ISO 3801, ASTM D 3776/D 3776M) |  | 10 | samples | 500 | 5000
| Piling Resistance (ASTM D 3512, ASTM D 3512M) - Random Tumble |  | 10 | samples | 800 | 8000
| Thickness (ISO 5084, ASTM D 1777) |  | 10 | samples | 600 | 6000
| Fiber Composition (AATCC TM 20A) |  | 10 | samples | 1600 | 16000
| Colorfastness to Rubbing for Fabrics (ISO 105-X12, AATCC TM8) |  | 10 | samples | 600 | 6000
| Colorfastness to Laundering (ISO 105-CO6, AATCC TM 61, JIS L 0844); per additional color |  | 10 | samples | 1100 | 11000
| Colorfastness to Perspiration (ISO 105-EO4, AATCC TM 15, JIS L 0848); per additional color |  | 10 | samples | 1200 | 12000
| Color Difference (AATCC EP 6) |  | 10 | samples | 600 | 6000
| Color Quality (AATCC EP 6) |  | 10 | samples | 600 | 6000
| Dimensional Change ISO 6330 : 2012 |  | 10 | samples | 800 | 8000
| Tearing Strength ASTM D2261-13 |  | 10 | samples | 1600 | 16000
| Sewing Services for the ROTC Fatigue Uniform |  | 2 | lot | 5000 | 10000
Laboratory Supplies Expenses
| Iron (II) Sulfate Heptahydrate, AR 500g per bottle. CAS No. 7782-63-0 |  | 3 | bottles | 3500 | 10500 | Small Value Procurement | 30-calendar days
| 1,10-Phenanthroline AR 500g, CAS No. 66-71-7 |  | 3 | bottles | 4000 | 12000
| Ferrous Ammonium Sulfate, AR Grade 500g per bottle, CAS No. 7783-85-9 |  | 5 | bottles | 3500 | 17500
| Sodium Thiosulfate, AR 500g per bottle, CAS No. 7772-98-7 |  | 3 | bottles | 3500 | 10500
| Pottasium Iodide, AR 500g per bottle, CAS No. 7681-11-0 |  | 3 | bottles | 3000 | 9000
| Sodium Chloride, AR Grade, CAS No. 7758-19-2, 500g per bottle |  | 80 | Bottle | 3000 | 240000
| Pottasium Dichromate, AR 500g per bottel, CAS No. 7778-50-9 |  | 3 | bottles | 3000 | 9000
| Pottasium Hydrogen Phosphate, AR Grade 500g per bottle, CAS No. 7778-77-0 |  | 3 | bottles | 2500 | 7500
| Phenolphthalein, AR Grade 500g per bottle, CAS No. 77-09-8 |  | 2 | bottles | 2500 | 5000
| Sodium Hydroxide, liquid, 48-50%, TG, 25-30 kg/carbuoy |  | 100 | cby | 2500 | 250000 | Small Value Procurement | 30-calendar days
| Sodium Silicate, TG, 20 L/carbuoy |  | 60 | cby | 3000 | 180000
| Sodium Metabisulfite, TG, 25 kg/bag |  | 60 | bag | 5000 | 300000
| Glacial Acetic Acid, TG, 30 kg/carbuoy |  | 60 | cby | 6500 | 390000
| Hydrogen Peroxide, TG, 30 kg/carbuoy |  | 60 | cby | 6500 | 390000 | Small Value Procurement | 30-calendar days
| Sulfuric Acid, 95-98%, AR Grade, 2.5 L per bottle |  | 6 | Bottle | 2500 | 15000
| Acetone, CAS # 67-64-1, AR Grade, 2.5 L/bottle | 10 btls | 30 | btls | 5500 | 165000
| Hydrochloric Acid, 36%, AR Grade, 2.5 L per bottle |  | 6 | Bottle | 2500 | 15000
| Bleaching solution |  | 80 | gallons | 500 | 40000 | Small Value Procurement | 30-calendar days
| Non-ionic wetting agent |  | 100 | gallons | 800 | 80000
| Fabric Softener |  | 50 | sack | 1200 | 60000
| Liquid Handsoap |  | 20 | Bottle | 500 | 10000
| Disinfectant Spray |  | 30 | Bottle | 800 | 24000
| Sodium Carbonate, AR Grade, 500 g per bottle |  | 20 | Bottle | 2500 | 50000 | Small Value Procurement | 30-calendar days
| Sodium Bicarbonate, AR Grade, 500 g per bottle |  | 20 | Bottle | 2000 | 40000
| Sodium Hydroxide,CAS # 1310-73-2, AR grade, 1 kg/bottle | 15 btls | 60 | btls | 4000 | 240000
| Sodium Sulfite, anhydrous, AR grade, CAS # 7757-83-7, 500 g/bottle | 15 btls | 60 | btls | 2500 | 150000
| Pectinase Enzyme, 1 L per Bottle |  | 50 | btls | 5500 | 275000 | Agency to Agency | 30-calendar days
| Xylanase Enzyme, 1 L per Bottle |  | 50 | btls | 5500 | 275000
| Beakers, borosilicate glass, 2L | 20 pcs | 20 | pcs | 1300 | 26000 | Negotaited - Small Value Procurement | 30-calendar days
| Beakers, borosilicate glass, 1L | 15 pcs | 15 | pcs | 800 | 12000
| Beakers, borosilicate glass, 500 mL | 15 pcs | 15 | pcs | 250 | 3750
| Graduated cylinder, borosilicate glass, 1L |  | 10 | pcs | 2400 | 24000
| Graduated cylinder, borosilicate glass, 500 mL |  | 10 | pcs | 2000 | 20000
| Graduated cylinder, borosilicate glass, 100 mL |  | 10 | pcs | 1000 | 10000
| Gooch Glass Filter | 24 pcs | 24 | pcs | 2500 | 60000
| Reagent bottle, clear, borosilicate glass, 1L |  | 15 | pcs | 1000 | 15000
| Reagent bottle, clear, borosilicate glass, 500 mL |  | 15 | pcs | 2000 | 30000
| Reagent bottle, amber, borosilicate glass, 1L |  | 15 | pcs | 1000 | 15000
| Reagent bottle, amber, borosilicate glass, 500 mL |  | 15 | pcs | 2000 | 30000
| Vacuum pump |  | 5 | pcs | 10000 | 50000 | Small Value Procurement | 30-calendar days
| Vacuum Desiccator, borosilicate glass |  | 2 | pcs | 25000 | 50000
| Set of Calibration Weights with Certificate and Case |  | 1 | set | 50000 | 50000 | Small Value Procurement | 30-calendar days
| LPG Tank/Fuel |  | 20 | tank | 5000 | 100000 | Small Value Procurement | 30-calendar days
| Lint-free wipes, Kimwipes |  | 30 | boxes | 500 | 15000 | Small Value Procurement | 30-calendar days
| Nitrile Gloves (Medium) | 10 boxes | 10 | boxes | 300 | 3000
| Nitrile Gloves (Large) | 10 boxes | 10 | boxes | 300 | 3000
Other Supplies and Materials Expenses
| Wi-Fi Duplex Wide-format All-in-One Ink Tank Printer |  | 2 | units | 40000 | 80000 | Small Value Procurement | 30-calendar days
| Office Partition |  | 4 | pcs | 20000 | 80000 | Small Value Procurement | 30-calendar days
| Ergonomic Mesh Chair |  | 6 | pcs | 7000 | 42000 |  | 30-calendar days
| Hair dryer/blower |  | 1 | pc | 3000 | 3000 |  | 30-calendar days
| Pull-up Tissue |  | 10 | boxes | 1100 | 11000 |  | 30-calendar days
| Customized Certificate Holder, legal size |  | 20 | pcs | 700 | 14000 |  | 30-calendar days
| Mannequin, Glass Fiber, with bag |  | 10 | pcs | 15000 | 150000 |  | 30-calendar days
| Transcriber |  | 3 | pcs | 2000 | 6000 | Shopping / Direct Retail | 30-calendar days
| Decorticated Banana Fibers |  | 300 | kg | 300 | 90000 | Small Value Procurement | 30-calendar days
| Raw Bamboo Fibers |  | 300 | kg | 300 | 90000 | Small Value Procurement | 30-calendar days
| Sign Pen, Blue, 0.5mm | 30 pcs | 30 | pcs | 150 | 4500 | Shopping | 30-calendar days
| Mobile Prepaid Load Cards (Smart – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960 | Shopping / Direct Retail | 30-calendar days
| Mobile Prepaid Load Cards (Globe – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960
| P.E. Plastic Bag (20x30 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 2000 | 20000 | Small Value Procurement | 30-calendar days
| P.E. Plastic Bag (25x50 inches, 0.002 inches (thickness) 50pcs/pack | 10 packs | 10 | packs | 2500 | 25000
| P.E. Plastic Bag (40x60 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 3000 | 30000
Training Expenses
| Registration Fee on APAM PAASE |  | 4 | pax | 5000 | 20000 | Shopping / Direct Retail
| Seminar on GHS Labelling, Storage, and Risk Assessment |  | 3 | pax | 2688 | 8064 | Shopping / Direct Retail
| Office Supply and Equipment | Office Supply and Equipment
| Name Plate Holder |  | 30 | pcs | 400 | 12000 | Shopping | 30-calendar days
| Laboratory Equipment | Laboratory Equipment
| Air Compressor |  | 1 | lot | 150000 | 150000
| Uninterruptible Power Supply |  | 2 | unit | 49999 | 99998 | Small Value Procurement
| Heavy-Duty Electrical Cable Wire, 14/2C, 1.5 sq. mm, 75-100m |  | 1 | roll | 8000 | 8000 | Small Value Procurement | 30-calendar days
| Heavy-Duty Electrical Cable Wire, 8/3C, 75-100m |  | 1 | roll | 8000 | 8000
| 60A Circuit Breaker, industrial type, automatic, three (3) phase |  | 4 | pc | 8000 | 32000
| 30A Circuit Breaker, industrial type, automatic, one (1) phase |  | 4 | pc | 5000 | 20000
| Polyurethane Air Pneumatic Hose, 75-100m |  | 1 | roll | 8000 | 8000
| PVC Pipe 1 1/2 in or 2 diameter inches |  | 6 | pc | 250 | 1500
| Heavy-Duty Electrical Cable Wire No. 8 |  | 3 | box | 8000 | 24000
| PVC Pipe Connector |  | 5 | pc | 100 | 500
| Electrical Tape |  | 2 | box | 1000 | 2000
| Clamp |  | 3 | pc | 100 | 300
| Lock nut for breaker |  | 3 | pc | 150 | 450
| Customized stainless bucket with cover and water tap | 6 pcs | 6 | pcs | 7000 | 42000 | Shopping | 30-calendar days
| Multi-Station Magnetic Hot Plate Stirrer |  | 2 | pcs | 150000 | 300000 | Small Value Procurement | 30-calendar days
| Brown cones |  | 2000 | pcs | 80 | 160000 | Small Value Procurement | 30-calendar days
| Laboratory Refrigerator |  | 1 | unit | 200000 | 200000 | Small Value Procurement | 30-calendar days
| Repair and Mentainance Expenses | Laboratory Equipment
| Repair and Mentainance Services |  | 1 | lot | 5000 | 5000 | Negotaited Procurement
TOTAL BUDGET: |  | 6360982
+ 10% Provision for Inflation |  | 636098.2
+ 10% Contingency |  | 636098.2
TOTAL ESTIMATED BUDGET: |  | 7633178.4
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: | [6 empty] | Recommending Approval: | [7 empty] | Approved by:
KIMBERLY P. VIRON |  |  | MARILOU G. AGUSTIN | [6 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, Property, Procurement and General Services Section | [6 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  |  | Date: ______________________ | [6 empty] | Date: ______________________ | [7 empty] | Date: ______________________

## Copy of APRIL - JUNE (hidden)
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
END-USER/UNIT: RDD-CDABUS
Charged to: “Functional Philippine Camouflage Fabric for Field Service Uniform(FSU)/ Battle Dress Unifom(BDU) Application”
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | QUANTITY/ | UNIT OF MEASURE | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE | SIZE | [5 empty] | Apr | May | Jun | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
Other Professional Services
| FESEM Imaging | 19 | 19 | sample | 8000 | 152000
| Thermogravimetric Analysis | 19 | 19 | sample | 3500 | 66500
| Differential Scanning Calorimetry | 19 | 19 | sample | 3000 | 57000
Laboratory Supplies Expenses
| Pectinase Enzyme, 1 L per Bottle |  | 5 | Bottle | 5500 | 27500
| Xylanase Enzyme, 1 L per Bottle |  | 4 | Bottle | 5500 | 22000
| Beakers, borosilicate glass, 2L | 20 pcs | 20 | pcs | 1300 | 26000 | Negotaited - Small Value Procurement | 30-calendar days |  | 20
| Beakers, borosilicate glass, 1L | 15 pcs | 15 | pcs | 800 | 12000 |  |  |  | 15
| Beakers, borosilicate glass, 500 mL | 15 pcs | 15 | pcs | 250 | 3750 |  |  |  | 15
| Graduated cylinder, borosilicate glass, 1L |  | 10 | pcs | 2400 | 24000 |  |  |  | 10
| Graduated cylinder, borosilicate glass, 500 mL |  | 10 | pcs | 2000 | 20000 |  |  |  | 10
| Graduated cylinder, borosilicate glass, 100 mL |  | 10 | pcs | 1000 | 10000 |  |  |  | 10
| Gooch Glass Filter | 24 pcs | 24 | pcs | 2500 | 60000 |  |  |  | 24
Other Supplies and Materials Expenses
| Heavy-Duty Electrical Cable Wire, 14/2C, 1.5 sq. mm, 75-100m |  | 1 | roll | 8000 | 8000
| Heavy-Duty Electrical Cable Wire, 8/3C, 75-100m |  | 1 | roll | 8000 | 8000
| 60A Circuit Breaker, industrial type, automatic, three (3) phase |  | 4 | pc | 8000 | 32000
| 30A Circuit Breaker, industrial type, automatic, one (1) phase |  | 4 | pc | 5000 | 20000
| Uninterruptible Power Supply |  | 2 | unit | 49999 | 99998
| Air Compressor |  | 1 | lot | 150000 | 150000
| Polyurethane Air Pneumatic Hose, 75-100m |  | 1 | roll | 8000 | 8000
| Sign Pen, Blue, 0.5mm | 30 pcs | 30 | pcs | 150 | 4500 | Shopping | 30-calendar days | 30
| Mobile Prepaid Load Cards (Smart – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960 | Shopping / Direct Retail | 30-calendar days | 40
| Mobile Prepaid Load Cards (Globe – 100 pesos load) | 40 pcs | 40 | pcs | 199 | 7960 |  |  | 40
| P.E. Plastic Bag (20x30 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 2000 | 20000 | Negotiated Procurement-Small Value Procurement | 30-calendar days | 2
| P.E. Plastic Bag (25x50 inches, 0.002 inches (thickness) 50pcs/pack | 10 packs | 10 | packs | 2500 | 25000 |  |  | 2
| P.E. Plastic Bag (40x60 inches, 0.002 inches (thickness) 50pcs/pack) | 10 packs | 10 | packs | 3000 | 30000 |  |  | 2
| Office Supply and Equipment | Office Supply and Equipment
| Office Services | Office Supply and Equipment |  |  | 0
| Laboratory Equipment | Laboratory Equipment |  |  | 0
| Electrical Cables; Royal Cord, 3 Core | 2 units | 2 | units | 7200 | 14400 | Small Value Procurement |  |  | 2
| Electrical Breaker | 6 units | 6 | units | 500 | 3000 | Small Value Procurement |  |  | 6
| Uninterruptible Power Supply | 2 units | 2 | units | 10000 | 20000 | Small Value Procurement |  |  | 1
| Industrial air compressor |  | 1 | lot | 49000 | 49000 | Small Value Procurement |  |  | 1
| Industrial filter paper, 60x60 cm | 5 packs | 5 | packs | 9999 | 49995 | Small Value Procurement |  |  | 10
| Parafilm | 10 rolls | 10 | rolls | 4000 | 40000 | Small Value Procurement |  |  | 10
| Customized stainless bucket with cover and water tap | 6 pcs | 6 | pcs | 7000 | 42000 | Small Value Procurement |  |  | 6
Cash Advance
TOTAL BUDGET: |  | 1120563
+ 10% Provision for Inflation |  | 112056.3
+ 10% Contingency |  | 112056.3
TOTAL ESTIMATED BUDGET: |  | 1344675.6
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: | [6 empty] | Recommending Approval: | [7 empty] | Approved by:
________________________ |  |  | MARILOU G. AGUSTIN | [6 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, Property, Procurement and General Services Section | [6 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  |  | Date: ______________________ | [6 empty] | Date: ______________________ | [7 empty] | Date: ______________________

## Copy of 2024 PPMP BDU (hidden)
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
END-USER/UNIT: RDD-CDABUS
Charged to: “Functional Philippine Camouflage Fabric for Field Service Uniform(FSU)/ Battle Dress Unifom(BDU) Application”
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE |  |  |  |  | Jan | Feb | Mar | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
OPS
| Customized Corporate Polo Shirt with Logo Embroidery | 40 pcs. | 800 | 32000 | Negotiated Procurement |  | 40
| Printing Services (Camouflage Print 2) | 1 pc. | 33000 | 33000 | Negotiated Procurement |  | 1
| Abrasion Resistance | 3 samples | 800 | 2400 | Agency to Agency |  | 3
| Strength and Elongation (single strand, ASTM D 2256 / ASTM D 2256 M) | 3 samples | 700 | 2100 | Agency to Agency |  | 3
| Evenness (ASTM D 1425 / ASTM D 1425M) | 3 samples | 1100 | 3300 | Agency to Agency |  | 3
| Hairiness (ASTM D 5647) | 3 samples | 1100 | 3300 | Agency to Agency |  | 3
| Yarn shrinkage (oven, ASTM D 2259 single yarns) | 3 samples | 700 | 2100 | Agency to Agency |  | 3
| Yarn number (Skein, ASTM D 1907) | 3 samples | 400 | 1200 | Agency to Agency |  | 3
| Yarn twist (single, ASTM D 1423) | 3 samples | 700 | 2100 | Agency to Agency |  | 3
Other Supplies and Materials Expenses
| Certificate Holder, Legal Size, Material: PTF Fabric | 20 pcs | 500 | 10000 | Small Value Procurement |  | 20
| Lei/Garland | 30 pcs | 300 | 9000 | Small Value Procurement |  | 30
| -Bag Tag | 20 pcs | 300 | 6000 | Small Value Procurement |  | 20
| -Infinity scarf | 5 pcs | 500 | 2500 | Small Value Procurement |  | 5
| -Headband belt | 5 pcs | 400 | 2000 | Small Value Procurement |  | 5
| Sign Pen, Blue, 0.5mm | 30 pcs | 150 | 4500 | Small Value Procurement |  | 30
| Packaging Box | 20 pcs | 300 | 6000 | Small Value Procurement |  | 20
| Mobile Prepaid Load Cards (Smart – 100 pesos load) | 40 pcs | 199 | 7960 | Small Value Procurement |  | 40
| Mobile Prepaid Load Cards (Globe – 100 pesos load) | 40 pcs | 199 | 7960 | Small Value Procurement |  | 40
| P.E. Plastic Bag (20x30 inches, 0.002 inches (thickness) 50pcs/pack) | 2 packs | 2000 | 4000 | Small Value Procurement |  | 2
| P.E. Plastic Bag (25x50 inches, 0.002 inches (thickness) 50pcs/pack | 2 packs | 2500 | 5000 | Small Value Procurement |  | 2
| P.E. Plastic Bag (40x60 inches, 0.002 inches (thickness) 50pcs/pack) | 2 packs | 3000 | 6000 | Small Value Procurement |  | 2
| Nitrile Gloves (Medium) | 10 boxes | 300 | 3000 | Small Value Procurement |  | 10
| Nitrile Gloves (Large) | 10 boxes | 300 | 3000 | Small Value Procurement |  | 10
| Labgown (Medium) | 2 pcs | 500 | 1000 | Small Value Procurement |  | 2
| Labgown (Large) | 2 pcs | 500 | 1000 | Small Value Procurement |  | 2
| Mask | 10 boxes | 200 | 2000 | Small Value Procurement |  | 10
| Facial Tissue | 10 packs | 200 | 2000 | Small Value Procurement |  | 10
| Rolled Tissue | 10 packs | 200 | 2000 | Small Value Procurement |  | 10
| Parafilm | 10 rolls | 4000 | 40000 | Small Value Procurement |  |  | 10
| Ziplock (Small) | 10 packs | 200 | 2000 | Small Value Procurement |  | 10
| Ziplock (Medium) | 10 packs | 250 | 2500 | Small Value Procurement |  | 10
| Ziplock (Large) | 10 packs | 350 | 3500 | Small Value Procurement |  | 10
| Ziplock (Extra Large) | 10 packs | 400 | 4000 | Small Value Procurement |  | 10
Office Equipment
Laboratory Equipment
<-- INSERT ROW IF NEEDED
TOTAL BUDGET: |  | 218420
+ 10% Provision for Inflation |  | 21842
+ 10% Contingency |  | 21842
TOTAL ESTIMATED BUDGET: |  | 262104
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  | Reviewed by: | [5 empty] | Recommending Approval: | [7 empty] | Approved by:
________________________ |  | MARILOU G. AGUSTIN | [5 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  | Head, Property, Procurement and General Services Section | [5 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  | Date: ______________________ | [5 empty] | Date: ______________________ | [7 empty] | Date: ______________________

## PPMP Sample (hidden)
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
(Sample Only)
END-USER/UNIT: RDD-NFUS
Charged to: Digitalization of Philippine Textiles to Protect and Sustain the Handloom Weaving Sector
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE |  |  |  |  | Jan | Feb | Mar | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
Office Supplies
| 32gb OTG flashdrive | 80 pieces | 625 | 50000 | Small Value Procurement |  | 80
| 16GB microSD card | 5 pieces | 600 | 3000 | Small Value Procurement |  | 5
| Powerbank | 10 pieces | 1000 | 10000 | Small Value Procurement |  | 10
| External hard drive, 1TB | 10 pieces | 5000 | 50000 | Small Value Procurement |  | 10
| Wireless mouse | 5 pieces | 500 | 2500 | Small Value Procurement |  | 5
| Binder Clip 4 per pack black | 20 packs | 25 | 500 | Shopping |  | 20
| Binder clip 2 per pack black | 15 packs | 20 | 300 | Shopping |  | 15
| Paper clip vinyl coated assorted 100s | 5 packs | 30 | 150 | Shopping |  | 5
| Envelope document 5/pack | 10 packs | 30 | 300 | Shopping |  | 10
| Envelope expanding with elastic, legal | 30 packs | 10 | 300 | Shopping |  | 30
| Sticky flags | 20 packs | 100 | 2000 | Shopping |  | 20
| Highlighter (yellow) | 5 pieces | 15 | 75 | Shopping |  | 5
| Glue stick | 10 packs | 30 | 300 | Shopping |  | 10
| Long brown envelope | 50 packs | 20 | 1000 | Shopping |  | 50
| Clearbook, long | 15 pieces | 133.3333 | 2000 | Shopping |  | 15
| Spray paint | 1 piece | 1000 | 1000 | Small Value Procurement |  |  | 1
| All in one laser printer | 3 units | 10000 | 30000 | Small Value Procurement |  |  | 3
| Certificate paper | 100 pieces | 10 | 1000 | Shopping |  |  | 100
| ID and ID laces | 100 pieces | 20 | 2000 | Shopping |  |  | 100
| Manila paper | 50 pieces | 5 | 250 | Shopping |  |  | 50
| USB to VGA/HDMI adapter for Macbook | 3 units | 133.3333 | 400 | Small Value Procurement |  |  | 3
| USB to VGA/HDMI adapter for other laptops | 3 units | 133.3333 | 400 | Small Value Procurement |  |  | 3
| A4 paper/500 pcs/ream | 30 reams | 183.3333 | 5500 | Shopping |  |  | 30
| Paper shredder | 1 piece | 5000 | 5000 | Small Value Procurement |  |  | 1
| Black ink for printer | 8 carts | 400 | 3200 | Shopping |  |  | 8
| Colored ink for printer | 8 carts | 400 | 3200 | Shopping |  |  | 8
| Metal fasteners | 3 packs | 66.6667 | 200 | Shopping |  |  | 3
| Folder for A4 size documents, 10 pcs per pack | 20 packs | 50 | 1000 | Shopping |  |  |  | 20
| Blue sign pens | 20 pieces | 30 | 600 | Shopping |  |  |  | 20
| Regular pens | 100 pieces | 10 | 1000 | Shopping |  |  |  | 100
| Permanent markers | 50 pieces | 20 | 1000 | Shopping |  |  |  | 50
| Transparent tape | 20 pieces | 20 | 400 | Shopping |  |  |  | 20
| Stapler | 3 pieces | 100 | 300 | Shopping |  |  |  | 3
| Staple wires | 10 boxes | 50 | 500 | Shopping |  |  |  | 10
| Correction tape | 10 pieces | 30 | 300 | Shopping |  |  |  | 10
| Scissors | 10 pieces | 30 | 300 | Shopping |  |  |  | 10
Laboratory Supplies
| Machining of components H1 | 4 units | 1640 | 6560 | Small Value Procurement |  | 4
| Machining of components H2 | 4 units | 860 | 3440 | Small Value Procurement |  | 4
| Machining of component M | 8 units | 1000 | 8000 | Small Value Procurement |  | 8
| Disposable ABR electrodes | 300 units | 50 | 15000 | Small Value Procurement |  | 300
| Disposable snap electrodes | 100 units | 57 | 5700 | Small Value Procurement |  | 100
| Skin prep gel | 4 units | 1375 | 5500 | Small Value Procurement |  |  | 4
| Neurodiagnostic Conductive Electrode Paste | 4 units | 1800 | 7200 | Small Value Procurement |  |  | 4
| Gold/silver electrode | 6 units | 1333.3333 | 8000 | Small Value Procurement |  |  | 6
| 70% Isopropyl alcohol | 10 units | 28 | 280 | Small Value Procurement |  |  | 10
| Micropore tape 1in | 6 boxes | 350 | 2100 | Small Value Procurement |  |  |  | 6
| Sterile gauze, individually wrapped | 10 boxes | 300 | 3000 | Small Value Procurement |  |  |  | 10
| Alcohol swab | 6 boxes | 400 | 2400 | Small Value Procurement |  |  |  | 6
Office Equipment
Laboratory Equipment
<-- INSERT ROW IF NEEDED
TOTAL BUDGET: |  | 247155
+ 10% Provision for Inflation |  | 24715.5
+ 10% Contingency |  | 24715.5
TOTAL ESTIMATED BUDGET: |  | 296586
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  | Reviewed by: | [5 empty] | Recommending Approval: | [7 empty] | Approved by:
________________________ |  | MARILOU G. AGUSTIN | [5 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  | Head, Property, Procurement and General Services Section | [5 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  | Date: ______________________ | [5 empty] | Date: ______________________ | [7 empty] | Date: ______________________