## PPMP 2nd Quarter
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
Charged to: GAA-CICA Bamboo Textile Product Development
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Apr | May | Jun | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
50203010 02 |  | Office Supplies Expenses
|  | 5 pcs stapler, 23/15 (9/16") | 1 lot | 300 | 117000 | Negotiated Procurement-Small Value Procurement | ≤ 30 calendar days | 5
|  | 10 boxes 50mm vinyl coated paper clip (100clips/box) |  | 50 |  |  |  | 10
|  | 10 boxes 1-1/4" (32mm) binder clips (12pcs/box) |  | 70 |  |  |  | 10
| OS-073 | 10 packs Label Index Stickers, 5 colors |  | 60 |  |  |  | 10
| OS-026 | 30 reams A4 Bondpaper, 70gsm |  | 380 |  |  |  | 30
| OS-057 | 20 reams Legal Bondpaper, 70gsm |  | 380 |  |  |  | 20
| OS-115 | 50 packs Sticker Paper, Matte (A4, 10's/pack) |  | 150 |  |  |  | 50
| OS-006 | 20 pieces Double-sided adhesive tape, 1" |  | 35 |  |  |  | 20
| OS-069 | 50 packs Specialty Boardpaper, 30's, 90gsm |  | 150 |  |  |  | 50
| OS-068 | 50 packs Vellum Board (A4, 10's/pack) |  | 150 |  |  |  | 50
| OS-027 | 10 boxes Permanent Marker, Black, Waterproof, 12's/box |  | 500 |  |  |  | 10
| OS-238 | 5 pieces Ruler, stainless steel, 12" |  | 100 |  |  |  | 5
|  | 5 pieces Ruler, stainless steel, 24" |  | 200 |  |  |  | 5
|  | 5 units Heavy duty metal storage shelf |  | 8000 |  |  |  | 5
|  | 50 pieces A6 waybill thermal sticker label roll, 500 pcs/roll |  | 500 |  |  |  | 50
50203990 00 |  | Other Supplies Expenses
|  | 5 pcs Manual Liquid Transfer Pump Suction Tube Length: ≥ 390 mm Discharge tube length: ≥ 540 mm | 1 lot | 300 | 145500 | Negotiated Procurement-Small Value Procurement | ≤ 30 calendar days |  | 5
|  | 5 packs Resealable Plastic Bag 120mm x 170mm (100pcs/pack), Clear |  | 200 |  |  |  |  | 10
|  | 5 packs Resealable Plastic Bag 200mm x 280mm (100pcs/pack), Clear |  | 300 |  |  |  |  | 10
|  | 3 packs Resealable Plastic Bag 340mm x 450mm (100pcs/pack), Clear |  | 600 |  |  |  |  | 10
|  | 5 pieces Stainless Crucible Tongs, 300mm |  | 1000 |  |  |  |  | 5
|  | 5 pieces Stainless Crucible Tongs, 500mm |  | 1200 |  |  |  |  | 5
|  | 10 pieces Stock Pot With Lid, Stainless Steel, 150 liters |  | 2000 |  |  |  |  | 10
|  | 10 pieces Stainless Pitcher, 1-2L |  | 500 |  |  |  |  | 10
| OS-108 | 50 packs Pull-ups Tissue, 2 ply, ≤ 190pulls/pack |  | 250 |  |  |  |  | 50
| MDL-057 | 20 packs P.E Plastic 20" x 30", Clear |  | 1500 |  |  |  |  | 20
| MDL-010 | 20 packs P.E Plastic 8" x 12", Clear |  | 1500 |  |  |  |  | 20
|  | 2 units Electric drill CE approval input power: 400 W rated voltage: 220-240 V frequency: 50/60 Hz no load speed: 0-3500 r/min chuck capacity Ø : 10mm plug & cable : VDE approved 2m |  | 6000 |  |  |  |  | 2
|  | 2 pieces Two-step steel ladder |  | 5000 |  |  |  |  | 2
|  | 5 pieces Heavy duty blade cutter knife, snap-off, 18x100 mm |  | 500 |  |  |  |  | 5
|  | Pineapple-based powerloom woven fabric - 1100 yds, assorted colors - at least 5% pineapple fiber content - fabric width: at least 55 inches -11 rolls at 100 yds per roll - Inclusive of delivery to PTRI -VAT inclusive | 1 lot | 165000 | 165000 | Negotiated Procurement-Small Value Procurement | ≤ 30 calendar days | 1
|  | fabric roll rack - A-frame type - 12 hanging rods - 1930 x 600 x 2000 mm (LxWxH) - with swivel wheels with brakes - customized with metal board on top - ceramic coating | 1 lot | 30000 | 150000 | Negotiated Procurement-Small Value Procurement | ≤ 60 calendar days | 3
|  | fabric tube roll - cardboard - length: ≤ 62" - inner diameter: ≤ 1.75" |  | 1000 |  |  |  | 60
|  | 6 pieces Fabric shears, stainless steel, 8" | 1 lot | 1000 | 83400 | Negotiated Procurement-Small Value Procurement | ≤ 30 calendar days |  | 6
|  | 6 pieces Fabric shears, stainless steel, 9" |  | 1000 |  |  |  |  | 6
|  | 6 pieces Fabric shears, stainless steel, 10" |  | 1200 |  |  |  |  | 6
|  | 6 pieces Pinking shears, stainless steel, 8'-10" |  | 1200 |  |  |  |  | 6
|  | 6 pieces Foldable Meter Stick, Metal (aluminum) |  | 600 |  |  |  |  | 6
|  | 12 pieces Tailor's Tape Measure, Telescopic/ retractable with case; 60" length |  | 600 |  |  |  |  | 12
|  | 12 pieces Sewing machine needles (high speed, single), DB X 1 90/9 |  | 600 |  |  |  |  | 12
|  | 12 pieces Sewing machine needles (high speed, single) , DB X 1 90/11 |  | 600 |  |  |  |  | 12
|  | 12 pieces Sewing machine needles (high speed, single) , DB X 1 90/14 |  | 600 |  |  |  |  | 12
|  | 6 sets Pattern Drafting Ruler Set - acrylic - Inclusions: see-through grid L-square; straight gridded ruler; french curve, hip/ arm cure, flexible ruler |  | 2000 |  |  |  |  | 6
|  | 6 pieces Magnetic pin holder, magnetic plate; wrist-worn (adjustable) |  | 500 |  |  |  |  | 6
|  | 6 boxes Tailor's pencil , box of 12, white |  | 500 |  |  |  |  | 6
|  | 6 boxes Tailor's pencil , box of 12, assorted |  | 500 |  |  |  |  | 6
|  | 6 sets Dressmaker sewing pins, 480-pc set, round pearl headed straight steel |  | 400 |  |  |  |  | 6
|  | 6 sets Dressmaker sewing pins, 200-pc set, plain, solid headed straight steel |  | 200 |  |  |  |  | 6
|  | Wilcom e4 decorating embroidery software | 1 unit | 40000 | 40000 | Shopping | ≤ 60 calendar days |  |  | 1
|  | Camshaft Balancer (for fabrication) with fixed shafting | 1 lot | 15000 | 30000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days | 1
|  | Camshaft Balancer (for fabrication) with detachable shafting |  | 15000 |  | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days | 1
50203080 00 |  | Medical, Dental, Laboratory Supplies Expenses
|  | Ginned Cotton Fibers | 250 kgs | 300 | 75000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days |  |  | 250
|  | Lyocell Fiber - 98-100 mm longstaple fibers, 300kg/bale - 1.4-1.9 dtex - bright or dull lustre - inclusive of delivery to DOST-PTRI - tax inclusive | 1 bale | 265000 | 265000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days |  |  | 1
|  | 50 kgs Talisay Leaves, as natural dye source | 1 lot | 40 | 48250 | Shopping | ≤ 30 calendar days | 50
|  | 50 kgs Cogon grass, as natural dye source |  | 40 |  |  |  | 50
|  | 25 kgs Annatto seeds, no oil, as natural dye source |  | 250 |  |  |  | 25
|  | 10 pcs whole young coconut (buko), as natural dye source |  | 50 |  |  |  | 10
|  | 50 kgs coffee pulp, as natural dye source |  | 50 |  |  |  | 50
|  | 5 kg Indigo powder dye source |  | 7000 |  |  |  | 5
|  | 10 pieces laundry net | 1 lot | 100 | 7500 | Shopping | ≤ 30 calendar days | 10
|  | 3 sets PVC Pipe, 3 meters length by 3 inches thickness |  | 500 |  |  |  | 3
|  | 5 kgs Ferrous Sulfate, technical grade |  | 500 |  |  |  | 5
|  | 5 kgs Sodium Hydroxide (Flakes), Technical Grade |  | 500 |  |  |  | 5
|  | Hydrogen Peroxide, Technical grade, 48% - 50% purity, 35 kg/cby | 5 cby | 8000 | 40000 | Shopping | ≤ 90 calendar days | 5
|  | Cellulase Enzyme - clear (light to dark brown) - pH (1% sol:4-5) - density 1-1.1 g/mL | 30 kgs | 1500 | 45000 | Shopping | ≤ 90 calendar days | 30
|  | 15 gallons non-ionic detergent | 1 lot | 1000 | 34450 | Shopping | ≤ 30 calendar days |  | 15
|  | 5 units laboratory thermometer, temp range: -10°C to 110°C |  | 1000 |  | Shopping | ≤ 30 calendar days |  | 5
|  | 15 pieces goggles protection, silicone, transparent |  | 450 |  | Shopping | ≤ 30 calendar days |  | 15
| MDL-023 | 20 pairs Heavy Duty Latex Gloves, Chemical Resistant |  | 250 |  |  |  |  | 20
|  | 10 packs Nylon Bags, Dimensions: 35 cm x 41.5 cm, 10 pcs per pack |  | 270 |  |  |  |  | 10
50211990 00 |  | Other Professional Services
|  | Colormatching service for fabrics and yarns | 30 kgs | 230 | 6900 | Negotiated Procurement-Small Value Procurement | ≤ 30 calendar days |  |  | 30
|  | Scouring/bleaching services for fabrics and yarns | 50 kgs | 95 | 4750 | Negotiated Procurement-Small Value Procurement | ≤ 30 calendar days |  | 50
|  | Small scale batch dyeing service for yarns and fabrics | 70 kgs | 500 | 35000 | Negotiated Procurement-Small Value Procurement | ≤ 30 calendar days |  | 70
|  | 1 lot Fabric dyeing and finishing services - 150 kgs, assorted - Inclusive of finishing (enzyme, water repellent and/or flame retardant) - Inclusive of reactive dyeing - Inclusive of softening and calendaring - VAT inclusive | 1 lot | 49500 | 49500 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days |  | 1
|  | Dry cleaning services | 1 lot | 5000 | 5000 | Petty Cash Fund | per schedule |  | 1
|  | Professional weaving services - 1000 m, assorted - powerloom weaving - Natural textile fiber (NTF) blended yarns - Warping yarns: PE/Filament - Weft/Filling yarns: NTF blend 15-20 / 2 - 60" width, 70-100epi / 20-48ppi | 1 lot | 100000 | 100000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days | 1
|  | Professional weaving services - 1000 m, assorted - powerloom weaving - Natural textile fiber (NTF) blended yarns - Warping yarns: T/C (Technical Cotton) - Weft/Filling yarns: NTF blend 15-20 / 2 - 60" width, 70-100epi / 20-48ppi | 1 lot | 100000 | 100000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days | 1
|  | Professional weaving services - 1000 m, assorted - powerloom weaving - Natural textile fiber (NTF) blended yarns (Special Fabrics) - Warping yarns: T/C (Technical Cotton) - Weft/Filling yarns: NTF blend 15-20 / 2 - 60" width, 70-100epi / 20-48ppi | 1 lot | 100000 | 100000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days |  | 1
|  | Professional weaving services - 1000 m, assorted - powerloom weaving - Natural textile fiber (NTF) blended yarns (Special Fabrics) - Warping yarns: PE/Filament - Weft/Filling yarns: NTF blend 15-20 / 2 - 60" width, 70-100epi / 20-48ppi | 1 lot | 100000 | 100000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days |  | 1
|  | Professional sewing services Inclusions: - Customized tailored coat, 4 pcs, using Philippine tropical fabrics with Inubon a Sabong weave accents | 1 lot | 60000 | 60000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days | 1
|  | Professional sewing services Inclusions: - 14-piece collection, using Philippine tropical fabrics | 1 lot | 150000 | 150000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days |  | 1
|  | Handloom weaving services Inclusions: - diamond weave Inabel pattern - warp: cotton/technical cotton - weft: bamboo blended yarns - 23 to 24 inches width - return of retain samples and wastage - VAT inclusive - inclusive of delivery charges to DOST-PTRI, General Santos Ave., Bicutan, Taguig City | 25 yards | 1000 | 25000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days |  |  | 25
|  | Handloom weaving services Inclusions: - Inubon a Sabong weave pattern - warp: cotton/technical cotton - weft: bamboo blended yarns - 20 to 23 inches width - return of retain samples and wastage - VAT inclusive - inclusive of delivery charges to DOST-PTRI, General Santos Ave., Bicutan, Taguig City | 25 yards | 1000 | 25000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days | 25
|  | Handloom weaving services Inclusions: - Patadyong weave pattern - warp: cotton/technical cotton - weft: bamboo blended yarns - 20 to 23 inches width - return of retain samples and wastage - VAT inclusive - inclusive of delivery charges to DOST-PTRI, General Santos Ave., Bicutan, Taguig City | 25 yards | 1000 | 25000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days | 25
|  | Handloom weaving services Inclusions: - Yakan weave pattern - warp: cotton/technical cotton - weft: bamboo blended yarns - 17 to 18 inches width - return of retain samples and wastage - VAT inclusive - inclusive of delivery charges to DOST-PTRI, General Santos Ave., Bicutan, Taguig City | 25 yards | 1500 | 37500 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days | 25
|  | Handloom weaving services Inclusions: - warp: cotton/technical cotton - weft: bamboo blended yarns - 23 to 24 inches width - return of retain samples and wastage - VAT inclusive - inclusive of delivery charges to DOST-PTRI, General Santos Ave., Bicutan, Taguig City | 25 yards | 1000 | 25000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days |  |  | 25
|  | Handloom weaving services Inclusions: - warp: 21d silk - weft: cotton/cotton-piña blend - 30 inches width - return of retain samples and wastage - VAT inclusive - inclusive of delivery charges to DOST-PTRI, General Santos Ave., Bicutan, Taguig City | 25 yards | 1999.99 | 49999.75 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days | 25
|  | Handloom weaving services Inclusions: - warp: 21d silk - weft: bamboo blended yarns - 30 inches width - return of retain samples and wastage - VAT inclusive - inclusive of delivery charges to DOST-PTRI, General Santos Ave., Bicutan, Taguig City | 25 yards | 1999.99 | 49999.75 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days | 25
|  | Handloom weaving services Inclusions: - warp: 21d silk - weft: piña - 30 inches width - with suksok design using lyocell yarns - return of retain samples and wastage - VAT inclusive - inclusive of delivery charges to DOST-PTRI, General Santos Ave., Bicutan, Taguig City | 10 meters | 4950 | 49500 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days | 10
|  | Handloom weaving services Inclusions: - warp: silk - weft: piña - 30 inches width - with suksok design - return of retain samples and wastage - VAT inclusive - inclusive of delivery charges to DOST-PTRI, General Santos Ave., Bicutan, Taguig City | 10 meters | 4950 | 49500 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days | 10
|  | Printing services (Direct-to-Fabric Prints) | 20 yards | 2000 | 40000 | Negotiated Procurement-Small Value Procurement | ≤ 90 calendar days |  |  | 20
50604050 14 |  | Technical & Scientific Equipment - Equipment Outlay
|  | Single-head embroidery machine Technical Specifications: - no. of needles: 7 - dimensions: 25.3" L x 29.3" W x 28.9" H, 93 lbs. - max. sewing area: 11.4" x 11" - cap sewing area: 11.4" x 2.7" - max. speed: 1000 spm (650 spm caps) - memory: 40 million stitches/3,000 designs - 100 included designs, 12 onboard fonts - design transfer/networking: USB ports, LAN port, included network & connection software - onboard editing: scale, rotate, mirror, copy/repeat, programmable offset, pull compensation, stitch cleanup, adjustable lock stitches - hoop library: all compatible hoops stored in memory + 15 additional slots for new hoop types - timesaving features: automatic job interrupt/resume, load/setup next designs while machine is embroidering - maintenance aids: auto error-correction, auto maintenance reminders, maintenance mode automates DIY maintenance - table footprint: 11" w x 17" d - power: 110V / 220 W Inclusions: - Installation, Testing, and Commisioning of equipment at the DOST-PTRI, Bicutan, Taguig City - After Sales Service Certificate: ≥ 1 year - Warranty Certifcate: ≥ 1 years - After Sales Technical Assistance and spare parts: ≥ 1 year - VAT inclusive - Onsite training and issuance of training certificates - Delivery period : ≤ 60 calendar days | 1 lot | 500000 | 500000 | Small Value Procurement | ≤ 60 calendar days |  |  | 1
TOTAL APPROVED BUDGET: |  |  | 2293749.5
+ 10% Provision for Inflation |  |  | 229374.95
+ 10% Contingency |  |  | 229374.95
TOTAL ESTIMATED BUDGET: |  |  | 2752499.4
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
ZAILLA F. PAYAG |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: ______________________ |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________