## Mangyan Project
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
END-USER/UNIT: TSD-PCTS
Charged to: FRONTIER (Fostering the Revitalization of Nascent Textile Innovation Ecosystem in the Region): Stakeholders Conference - Mangyan Project
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE |  |  |  |  | April | May | June | REMARKS
Representation Expenses
| Meals during the Weaving Demonstration and Needs Assessment Program (AM and PM snacks, lunch, dinner, 2 days) 50 pax | 1 lot | 200000 | 200000 | small value procurement | on schedule |  | 1
Transportation and Delivery Expenses
| Van Rental | 1 lot | 150000 | 150000 | small value procurement | on schedule |  | 1
Venue Rental
| Accommodation Expenses (May 29, 2024 to June 2, 2024) | 1 lot | 180000 | 180000 | small value procurement | on schedule |  | 1
CASH ADVANCES
| Cotton fibers and natural dye sources (e.g., indigo, tagum) | 1 lot | 20000 | 20000 | cash advance | on schedule |  | 1
| Meals during the Travel of the Weavers (lunch) 25 pax | 1 lot | 20000 | 20000 | cash advance | on schedule |  | 1
| Meals and Venue during the Welcome Dinner to the Mangyan Weavers for 35 pax on May 29, 2024 | 1 lot | 30000 | 30000 | cash advance | on schedule |  | 1
| Meals during the visit to the National Museum (AM and PM snacks, lunch, dinner) 35 pax | 1 lot | 50000 | 50000 | cash advance | on schedule |  | 1
| Transportation Expenses of Weavers | 1 lot | 10000 | 10000 | cash advance | on schedule |  | 1
| Mobile expenses | 1 lot | 2400 | 2400 | cash advance | on schedule |  | 1
TOTAL BUDGET: |  | 662400
+ 10% Provision for Inflation |  | 66240
+ 10% Contingency |  | 66240
TOTAL ESTIMATED BUDGET: |  | 794880
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  | Reviewed by: | [5 empty] | Recommending Approval:
________________________ |  | MARILOU G. AGUSTIN | [5 empty] | MERLITA R. ODI
Project Leader |  | Head, Property, Procurement and General Services Section | [5 empty] | Head, Budget and Treasury Section
Date: ______________________ |  | Date: ______________________ | [5 empty] | Date: ______________________

## RSTW 4B - MIMAROPA PPMP
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
END-USER/UNIT: TSD-PCTS
Charged to: FRONTIER (Fostering the Revitalization of Nascent Textile Innovation Ecosystem in the Region) - Regional Handloom Weaving Innovation Center (RHWIC)
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE |  |  |  |  | April | May | June | PR No. | RFQ No. | PhilGEPS Reference No. | PhilGEPS Closing Date | AOC No. | BAC Reso No. and Date | PO No. | Name of Payee | BURS/ORS Amount | COA Received Date | Utilization Rate | NTP No. | IAR No. | OR / SI No. Date | ICS/PAR No. | RIS/RSMI No. | DV Date | Disbursement Rate | REMARKS | REMARKS
50203010 02 | Office Supplies
| Office Supplies - Handloom weaving materials for the Techno Forum | 1 lot | 5000 | 5000 | shopping | 7 calendar days | 1 |  |  | 2405-0540 dtd. 05-03-2024 | 0764-24A dtd. 05-03-2024
Printing and Binding Expenses
| Brochures and sticker on sintra for the exhibit | 4 units | 15000 | 15000 | shopping | 7 calendar days | 1 |  |  | 2404-0539 dtd. 05-03-2024 | 0766-24A dtd. 05-03-2024
CASH ADVANCES
| Mobile expenses | 1 lot | 3000 | 3000 | cash advance | 7 calendar days |  | 1
| Handloom weaving materials - yarns | 1 lot | 4725 | 4725 | cash advance | 7 calendar days | 1
| Tokens for the RSTW exhibit 280 pcs. macrame keychain | 1 lot | 10000 | 10000 | cash advance | on schedule | 1 |  |  | 2404-0506 dtd. 04-26-2024 | 0752-24 dtd. 05-03-2024 |  |  | 24-313A dtd. 05-03-2024 |  |  | BOHEMIAN CRAFTY ONLINE SHOP | 9880 |  |  |  | 2024-0455 DTD. 05-16-2024 | 22001 149751 DTD. 05-05-2024 | [5 empty] | Delivered - 5/22/24
| Various groceries | 1 lot | 5000 | 5000 | cash advance | on schedule | 1 |  |  | 2404-0506 dtd. 04-26-2024 | 0751-24 dtd. 05-03-2024 | [5 empty] | PUREGOLD PRICE CLUB/ OZ GROCERY STORE | 4218.5 |  |  |  | 2024-0450 DTD. 05-16-2024 | 62874 dtd. 5/6/24 1985, 1986 dtd. 5/8/24 | [5 empty] | Delivered - 5/21/24
| Baskets made from nito vines | 1 lot | 15000 | 15000 | cash advance | 15 working days |  | 1 |  | 2405-0584 dtd. 05-08-2024 | 0833-24 dtd. 05-08-2024 | [5 empty] | EDLYN A. AGUILAR | 8800 |  |  |  | 2024-0451 DTD. 05-16-2024 | AR dtd. 5/10/24 | 2405-092 |  |  |  |  | Delivered / Released 5/23/24
| Meals during the Techno Forum (PM snacks) 100 pax | 1 lot | 15000 | 15000 | cash advance | on schedule | 1 |  |  | 2404-0508 dtd. 04-26-2024 | 0753-24 dtd. 05-03-2024 |  |  | 24-326 dtd. 05-07-2024 |  |  | VENCIO's GARDEN HOTEL & RESTAURANT | 15000 |  |  |  | 2024-0452 DTD. 05-16-2024 | 15853 DTD. 05-08-2024 | [5 empty] | Delivered - 5/21/24
| Meals during Innovation Dialogue at Mansalay, Oriental Mindoro | 1 lot | 20000 | 20000 | cash advance | per schedule |  | 1 |  | 2405-0585 dtd. 05-08-2024 | 0834-24 dtd. 05-08-2024 | [17 empty] | Cancelled
| Communication Expenses Globe 300 load (surf, call & text card) 2 pcs Smart 300 load (surf, call & text card) 8 pcs | 1 lot | 3000 | 3000 | cash advance | 7 calendar days | 1 |  |  | 2404-0507 dtd. 04-26-2024 | 0766-24 dtd. 05-03-2024 |  |  | 24-312A dtd. 05-03-2024 |  |  | THE SM STORE - BICUTAN | 2920 | [10 empty] | Delivered - 5/22/24
| Facebook boosting | 1 lot | 5000 | 5000 | cash advance | on schedule | 1 |  |  | 2404-0504 dtd. 4/26/24 | 0750-24 dtd. 5/3/24 | [5 empty] | META PLATFORMS IRELAND LIMITED | 5000 |  |  |  | 2024-0436 5/9/24 | 7254362881341117-14277959 dtd. 5/8/24 | [5 empty] | Delivered
| Handloom woven fabrics (ramit) | 1 lot | 15000 | 15000 | cash advance | on schedule |  | 1 |  | 2405-0586 dtd. 05-08-2024 | 0835-24 dtd. 05-08-2024
TOTAL BUDGET: |  | 15000
+ 10% Provision for Inflation |  | 1500
+ 10% Contingency |  | 1500
TOTAL ESTIMATED BUDGET: |  | 18000
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  | Reviewed by: | [5 empty] | Recommending Approval: | [12 empty] | Approved by:
________________________ |  | MARILOU G. AGUSTIN | [5 empty] | MERLITA R. ODI | [12 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  | Head, Property, Procurement and General Services Section | [5 empty] | Head, Budget and Treasury Section | [12 empty] | Director IV
Date: ______________________ |  | Date: ______________________ | [5 empty] | Date: ______________________ | [12 empty] | Date: ______________________