## Sheet1
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
END-USER/UNIT: OD-TIPS
Charged to: GAA-CICA project entitled "FRONTIER: Fostering the Revitalization of Nascent Textile Innovation Ecosystems in the Regions - Stakeholders Conference (Textile Gallery)"
Projects, Programs and Activities (PAPs)
| Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Apr | May | Jun | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
-1 | -2 | -3 | -4 | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20 | -21 | -22 | -23 | -24 | -25 | -26 | -27 | -28 | -29 | -30 | -31 | -32 | -33 | -34 | -35
50203010 02 |  | Office Supplies Expenses
|  | A4 size | 1 ream | 250 | 250 | Shopping | 15 working days | 1 | 0 | 0
|  | Specialty Paper | 5 packs | 100 | 500 | Shopping | 15 working days | 5 | 0 | 0
|  | Ballpoint, ballpen, blue, 12 pcs/box | 3 box | 300 | 900 | Shopping | 15 working days | 3 | 0 | 0
|  | 20 packs "SIGN HERE" Page Markers, 5 colors, 150 sheets/pack | 5 packs | 70 | 350 | Shopping | 15 working days | 5 | 0 | 0
50203990 00 |  | Other Supplies Expenses
|  | Table Cover (Spandex) Size (29 inch x 47 inch x 24 inch) Color: Light gray (15 pcs) Black (15 pcs) | 30 pieces | 250 | 7500 | Shopping | 15 working days | 30 | 0 | 0
|  | Chair cover (spandex) Color: Light gray (50 pcs) Black (50 pcs) | 100 pieces | 450 | 13500 | Shopping | 15 working days | 100 | 0 | 0
|  | Silk Screen | 8 pieces | 115 | 920 | Cash Advance | Per schedule | 8 | 0 | 0
|  | Squeegee | 8 pieces | 45 | 360 | Cash Advance | Per schedule | 8 | 0 | 0
|  | Tokens/Prizes, 270 pcs | 1 lot | 15120 | 15120 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 0 | 0
|  | Various Groceries | 1 lot | 2000 | 2000 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Raffia | 1 lot | 5000 | 5000 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Natural dye sources and implements and shirt | 1 lot | 5000 | 5000 | Cash Advance | Per schedule | 1 | 0 | 0
|  | HDMI Adapter Connection: Mini DP male to HDMI Female Thunderbolt 2.0 Video Res: 4Kx2K Compatibility: Apple Macbook, Macbook Pro, MacBook Air, iMAc, Mac mini, Mac Pro Wire & Port specs: Pure copper Mini DP Port Corrosio-resistant, Copper coated, ABS shell | 1 pc | 900 | 900 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Conference System Main Unit Power source: AC220V-240V 50Hz Input : MIC, Auxiliary Output :8P mic unit portX3, monitor, recording Frequency response: 50-16000Hz Size : 420x175x65MM Weight: 3.7kg Attachment: 8P DIN extension cable 10Mx1 Color : black | 1 unit | 8000 | 8000 | Shopping | 15 working days | 1 | 0 | 0
|  | Delegate's Unit Conference Mic Mic ON/OFF Buttons Built - in 2W Speaker Volume Control Unidirectional condenser mic Red Light Indicate when mic is On | 12 pcs | 3000 | 36000 | Shopping | 15 working days | 12 | 0 | 0
Printing and Binding Expenses
|  | Brochures | 3 lots | 7200 | 21600 | Shopping | 15 working days | 1 | 1 | 1
|  | Sintra Boards | 3 lots | 2800 | 8400 | Shopping | 15 working days | 1 | 1 | 1
|  | Printing of PTC Proceedings | 1 lot | 400000 | 400000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 0 | 0
|  | Printing Services (For Innovation Dialogue and Techno Forum Materials) For 2024 RSTIW Region V | 1 lot | 10000 | 10000 | Cash Advance | Per schedule | 0 | 1 | 0
Communication Expenses
|  | Mobile Load Cards | 1 lot | 3000 | 3000 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Communication Expenses -18 pcs Prepaid Load Cards (Php300.00) -Surf, Call and Text For 2024 RSTIW Region V | 18 pieces | 300 | 5400 | Cash Advance | Per schedule | 0 | 18 | 0
50211990 00 |  | Other Professional Services
|  | Laundry Services | 3 lots | 30000 | 90000 | Negotiated Procurement - Small Value Procurement | 15 working days | 1 | 1 | 1
|  | Dry Cleaning Laundry Services for the outfits For 2024 RSTIW Region V | 2 lots | 2500 | 5000 | Cash Advance | Per schedule | 0 | 2 | 0
|  | General Provision for Services | 5 lots | 10000 | 50000 | Negotiated Procurement - Small Value Procurement | 15 working days | 5 | 0 | 0
|  | Rental of Venue for 3rd Philippine Handloom Weaving Conference (With Accommodation and Meals) Date of Event: April 26, 2024 Location: Kalibo, Aklan Inclusions: *for 100 pax *Meal Package -AM Snack, Lunch and PM Snack per day *Provisions for Function Hall/ Event Hall 900 sqm or better *Stage Decoration and centerpiece display (Fresh Flowers) for 1 day *Space for Weavers Bazaar *Inclusive of Electrical Charges *Basic Sound System with 2 Microphones, Projector and Widescreen, Basic Sound System and Lights, 2 wireless microphones, 6 wired microphones and VGA cable for laptop *Free Parking for guests *Accommodation for Speakers & Committee 9 rooms for 18 pax on April 25, 2024 VAT Inclusive | 1 lot | 200000 | 200000 | Negotiated Procurement - Small Value Procurement | Per schedule | 1 | 0 | 0
50299040 00 |  | Delivery and Transportation Expenses
|  | Delivery expense, from DOST-PTRI to communities, partners, and stakeholders | 30 lots | 1000 | 30000 | Cash Advance | Per schedule | 10 | 10 | 10
|  | Transportation expense, from DOST-PTRI to communities, partners, and stakeholders | 30 lots | 1000 | 30000 | Cash Advance | Per schedule | 10 | 10 | 10
Local Travel Expenses
|  | Local Travel to Bohol | 1 lot | 214000 | 214000 | Negotiated Procurement - Small Value Procurement | Per schedule | 1 | 0 | 0
Airfare for 2 VIP Guests Round Trip Ticket with 20 kgs Baggage Allowance May 22, 2024 - NAIA to Virac Airport May 24, 2024 - Virac Airport to NAIA For 2024 RSTIW Region V
50299030 00 |  | Representation Expenses
|  | Meals and snacks for meetings and events | 15 lots | 15000 | 225000 | Negotiated Procurement - Small Value Procurement | Per schedule | 5 | 5 | 5
|  | Meals for Tubigon Loom weavers | 25 pax | 150 | 3750 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Representation Expenses -Meals (Lunch) during Innovation Dialogue For 2024 RSTIW Region V | 30 pax | 150 | 4500 | Cash Advance | Per schedule | 0 | 30 | 0
|  | Meals for 2 VIP Guests (May 22-24, 2024) AM/PM Snacks Breakfast, Lunch, Dinner For 2024 RSTIW Region V | 1 lot | 15000 | 15000 | Cash Advance | Per schedule | 0 | 1 | 0
|  | Accomodation Expenses for 2 VIP Guests Event: DOST-PTRI Fasion Show Date: May 22-24, 2024 For 2024 RSTIW Region V |  |  |  | Cash Advance | Per schedule | 0 |  | 0
Advertising Expenses
|  | Advertising Expenses | 1 lot | 5000 | 5000 | Negotiated Procurement - Small Value Procurement | Per schedule | 1 | 0 | 0
50604050 14 |  | Capital Outlay
|  | Lights System in the Gallery | 1 lot | 500000 | 500000 | Negotiated Procurement - Small Value Procurement | 60 working days | 1 | 0 | 0
TOTAL APPROVED BUDGET: |  |  | ₱1,368,300.00
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
EVANGELINE FLOR P. MANALANG |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Officer-in-Charge, Research and Development Division |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Revision Date: 18 April 2024 |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________

## Revised 2nd Quarter
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
END-USER/UNIT: OD-TIPS
Charged to: GAA-CICA project entitled "FRONTIER: Fostering the Revitalization of Nascent Textile Innovation Ecosystems in the Regions - Stakeholders Conference (Textile Gallery)"
Projects, Programs and Activities (PAPs)
| Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Apr | May | Jun | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
-1 | -2 | -3 | -4 | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20 | -21 | -22 | -23 | -24 | -25 | -26 | -27 | -28 | -29 | -30 | -31 | -32 | -33 | -34 | -35
50203010 02 |  | Office Supplies Expenses
|  | A4 size | 1 ream | 250 | 250 | Shopping | 15 working days | 1 | 0 | 0
|  | Specialty Paper | 5 packs | 100 | 500 | Shopping | 15 working days | 5 | 0 | 0
|  | Ballpoint, ballpen, blue, 12 pcs/box | 3 box | 300 | 900 | Shopping | 15 working days | 3 | 0 | 0
|  | 20 packs "SIGN HERE" Page Markers, 5 colors, 150 sheets/pack | 5 packs | 70 | 350 | Shopping | 15 working days | 5 | 0 | 0
50203990 00 |  | Other Supplies Expenses
|  | Table Cover (Spandex) Size (29 inch x 47 inch x 24 inch) Color: Light gray (15 pcs) Black (15 pcs) | 30 pieces | 1400 | 42000 | Shopping | 15 working days | 30 | 0 | 0
|  | Chair cover (spandex) Color: Light gray (50 pcs) Black (50 pcs) | 100 pieces | 250 | 25000 | Shopping | 15 working days | 100 | 0 | 0
|  | Silk Screen | 8 pieces | 115 | 920 | Cash Advance | Per schedule | 8 | 0 | 0
|  | Squeegee | 8 pieces | 45 | 360 | Cash Advance | Per schedule | 8 | 0 | 0
|  | Tokens/Prizes, 270 pcs | 1 lot | 15120 | 15120 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 0 | 0
|  | Various Groceries | 1 lot | 2000 | 2000 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Raffia | 1 lot | 5000 | 5000 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Natural dye sources and implements and shirt | 1 lot | 5000 | 5000 | Cash Advance | Per schedule | 1 | 0 | 0
|  | HDMI Adapter Connection: Mini DP male to HDMI Female Thunderbolt 2.0 Video Res: 4Kx2K Compatibility: Apple Macbook, Macbook Pro, MacBook Air, iMAc, Mac mini, Mac Pro Wire & Port specs: Pure copper Mini DP Port Corrosio-resistant, Copper coated, ABS shell | 1 pc | 900 | 900 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Conference System Main Unit Power source: AC220V-240V 50Hz Input : MIC, Auxiliary Output :8P mic unit portX3, monitor, recording Frequency response: 50-16000Hz Size : 420x175x65MM Weight: 3.7kg Attachment: 8P DIN extension cable 10Mx1 Color : black | 1 unit | 8000 | 8000 | Shopping | 15 working days | 1 | 0 | 0
|  | Delegate's Unit Conference Mic Mic ON/OFF Buttons Built - in 2W Speaker Volume Control Unidirectional condenser mic Red Light Indicate when mic is On | 12 pcs | 3000 | 36000 | Shopping | 15 working days | 12 | 0 | 0
Printing and Binding Expenses
|  | Brochures | 3 lots | 7200 | 21600 | Shopping | 15 working days | 1 | 1 | 1
|  | Sintra Boards | 3 lots | 2800 | 8400 | Shopping | 15 working days | 1 | 1 | 1
|  | Printing of PTC Proceedings | 1 lot | 400000 | 400000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 0 | 0
|  | Printing Services (For Innovation Dialogue and Techno Forum Materials) For 2024 RSTIW Region V | 1 lot | 10000 | 10000 | Cash Advance | Per schedule | 0 | 1 | 0
Communication Expenses
|  | Mobile Load Cards | 1 lot | 3000 | 3000 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Communication Expenses -18 pcs Prepaid Load Cards (Php300.00) -Surf, Call and Text For 2024 RSTIW Region V | 18 pieces | 300 | 5400 | Cash Advance | Per schedule | 0 | 18 | 0
50211990 00 |  | Other Professional Services
|  | Laundry Services | 3 lots | 30000 | 90000 | Negotiated Procurement - Small Value Procurement | 15 working days | 1 | 1 | 1
|  | Dry Cleaning Laundry Services for the outfits For 2024 RSTIW Region V | 2 lots | 2500 | 5000 | Cash Advance | Per schedule | 0 | 2 | 0
|  | General Provision for Services | 5 lots | 10000 | 50000 | Negotiated Procurement - Small Value Procurement | 15 working days | 5 | 0 | 0
|  | Rental of Venue for 3rd Philippine Handloom Weaving Conference (With Accommodation and Meals) Date of Event: April 26, 2024 Location: Kalibo, Aklan Inclusions: *for 100 pax *Meal Package -AM Snack, Lunch and PM Snack per day *Provisions for Function Hall/ Event Hall 900 sqm or better *Stage Decoration and centerpiece display (Fresh Flowers) for 1 day *Space for Weavers Bazaar *Inclusive of Electrical Charges *Basic Sound System with 2 Microphones, Projector and Widescreen, Basic Sound System and Lights, 2 wireless microphones, 6 wired microphones and VGA cable for laptop *Free Parking for guests *Accommodation for Speakers & Committee 9 rooms for 18 pax on April 25, 2024 VAT Inclusive | 1 lot | 200000 | 200000 | Negotiated Procurement - Small Value Procurement | Per schedule | 1 | 0 | 0
|  | Reinstallation, Delivery, and Refurbishment of DOSTPTRI KatHABI Design Exhibits and Other Collaterals Provision of: I. Mini-stage Techno Display Platform 3-units 2m x 2m x 0.20m (H) elevated wood with/cove light 1-unit 6mx6m needle punch carpet 24-meters LED strip lights II. Product Display Platform 1-unit 10mx2mx0.1m elevated platform 5-units 2mx1.8mx0.3m (H) mannequin platform base 1-lot faux grass carpet 9-sqm needle punch carpet (gray) 1-unit overhead structure and column support 3-units clothesline display 2-units display shelves 3-units 2mx2mx0.20m(H) elevated wood platform w/ cove light 12-units pin light 4-units RGB lights 1-unit 15amps v 60Hz Circuit Breaker III. Photowall 1-unit 3mx0.5mx2.4m (H) photo-wall with electrical layout 4-units pin light IV. Weaving Machine Platform 1-unit 3mx2mx0.25m (H) elevated wood platform V. Display Vertical TV 6-unit vertical TV with electrical layout | 1 lot | 674000 | 674000 |  |  |  |  | 1
50299040 00 |  | Delivery and Transportation Expenses
|  | Delivery expense, from DOST-PTRI to communities, partners, and stakeholders | 30 lots | 1000 | 30000 | Cash Advance | Per schedule | 10 | 10 | 10
|  | Transportation expense, from DOST-PTRI to communities, partners, and stakeholders | 30 lots | 1000 | 30000 | Cash Advance | Per schedule | 10 | 10 | 10
Local Travel Expenses
|  | Local Travel to Bohol | 1 lot | 214000 | 214000 | Negotiated Procurement - Small Value Procurement | Per schedule | 1 | 0 | 0
Airfare for 2 VIP Guests Round Trip Ticket with 20 kgs Baggage Allowance May 22, 2024 - NAIA to Virac Airport May 24, 2024 - Virac Airport to NAIA For 2024 RSTIW Region V
50299030 00 |  | Representation Expenses
|  | Meals and snacks for meetings and events | 15 lots | 15000 | 225000 | Negotiated Procurement - Small Value Procurement | Per schedule | 5 | 5 | 5
|  | Meals for Tubigon Loom weavers | 25 pax | 150 | 3750 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Representation Expenses -Meals (Lunch) during Innovation Dialogue For 2024 RSTIW Region V | 30 pax | 150 | 4500 | Cash Advance | Per schedule | 0 | 30 | 0
|  | Meals for 2 VIP Guests (May 22-24, 2024) AM/PM Snacks Breakfast, Lunch, Dinner For 2024 RSTIW Region V | 1 lot | 15000 | 15000 | Cash Advance | Per schedule | 0 | 1 | 0
|  | Accomodation Expenses for 2 VIP Guests Event: DOST-PTRI Fasion Show Date: May 22-24, 2024 For 2024 RSTIW Region V |  |  |  | Cash Advance | Per schedule | 0 |  | 0
Advertising Expenses
|  | Advertising Expenses | 1 lot | 5000 | 5000 | Negotiated Procurement - Small Value Procurement | Per schedule | 1 | 0 | 0
50604050 14 |  | Capital Outlay
|  | Lights System in the Gallery | 1 lot | 500000 | 500000 | Negotiated Procurement - Small Value Procurement | 60 working days | 1 | 0 | 0
TOTAL APPROVED BUDGET: |  |  | ₱1,368,300.00
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
EVANGELINE FLOR P. MANALANG |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Officer-in-Charge, Research and Development Division |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Revision Date: 18 April 2024 |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________