## RYPIC Q2
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2025
For 2nd Quarter of CY 2025
END-USER/UNIT: FRONTIER: Fostering the Revitalization of Nascent Textile Innovation Ecosystems in the Region - Regional Yarn Production and Innovation Center (RYPIC)
CHARGED TO: FRONTIER: Fostering the Revitalization of Nascent Textile Innovation Ecosystems in the Region - Regional Yarn Production and Innovation Center (RYPIC)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Apr | May | Jun | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
50203010 02 |  | Office Supplies Expenses
| OS-224 | 20 rolls Tape, electrical 100m | 1 lot | 150 | 97670 | Shopping | 15 calendar days
| OS-093 | 20 rolls Tape, masking 1 inch width 100m |  | 200
|  | 50 rolls Tape, masking 2 inch width 100m |  | 300
| OS-303 | 50 rolls Tape, packaging 2 inches width 100m |  | 250
| OS-233 | 20 rolls Tape, transparent 1 inch width 100m |  | 150
|  | 50 rolls Tape, transparent 2 inch width 100m |  | 300
|  | 20 rolls, Tape double sided, 1 inch width, 100m |  | 100
|  | 20 pcs, Pencil eraser, 2B, large |  | 15
| OS-273 | 5 boxes Rubber band No 18, box |  | 150
| OS-154 | 20 pieces Note pad stick on 3x3', 100 sheets |  | 50
|  | 20 boxes, Folder, A4 |  | 500
|  | 20 boxes, Folder, Folio |  | 500
| OS-001 | 50 reams Paper multipurpose A4 500 sheets |  | 250
| OS-002 | 20 reams Paper multipurpose, Legal, 500 sheets |  | 300
|  | 10 units Ribbon for Bundy Clock S-960P |  | 700
|  | 5 reams Attendance Time Card, 200pcs/pack |  | 200
|  | 5 pieces EPSON 003 Black Ink | 1 lot | 200 | 247300 | Shopping | 30 calendar days
|  | 3 pieces EPSON 003 Yellow Ink |  | 200
|  | 3 pieces EPSON 003 Magenta Ink |  | 200
|  | 3 pieces EPSON 003 Cyan Ink |  | 200
|  | 15 pieces HP 206A Genuine Toner Cartridge Ink W2110A- Black |  | 5300
|  | 10 pieces HP 206A Genuine Toner Cartridge Ink W2113A- Magenta |  | 5500
|  | 10 pieces HP 206A Genuine Toner Cartridge Ink W2111A- Cyan |  | 5500
|  | 10 pieces HP 206A Genuine Toner Cartridge Ink W2112A- Yellow |  | 5500
50203990 00 |  | Other Supplies Expenses
| OSMI-042 | Alcohol, Isoprophyl, Gallon | 40 | 600 | 24000 | Shopping | 15 calendar days
| OSMI-036 | 10 pieces Insecticide 600ml | 1 lot | 300 | 18000 | Shopping | 15 calendar days
| OSMI-043 | 10 pieces Disinfectant Spray |  | 500
| OSMI-329 | 10 pieces Liquid Handsoap, 500ml |  | 100
| OSMI-019 | 50 packs Paper towel, interfold 150 pulls per pack |  | 80
| OSMI-102 | 50 boxes Interfolded Tissue paper |  | 100
| OSMI-089 | 50 pieces Battery, dry cell size AA | 1 lot | 75 | 7000 | Shopping | 15 calendar days
| OSMI-090 | 50 pieces Battery, dry cell size AAA |  | 65
|  | 25 pcs Sandpaper, 1000 grit | 1 lot | 25 | 18030 | Shopping | 30 calendar days
|  | 25 pcs Sandpaper, 2000 grit |  | 25
|  | 1 set Combination wrench, 6-24mm |  | 2500
|  | 2 sets Allen wrench, 2-12mm |  | 300
|  | 2 pcs Long nose pliers, 7" |  | 250
|  | 2 pcs Combination pliers, 7" |  | 250
|  | 2 pcs Diagonal cutting pliers (side cutter), 7" |  | 250
|  | 1 set Circlip pliers, 4-pc set, 7" |  | 1200
|  | 2 pcs Philip screw driver (+) |  | 120
|  | 2 pcs Flat screw driver (-) |  | 120
|  | 1 unit Hand impact drill, 910 watts, 13mm |  | 3000
|  | 3 pcs Masonry drill bit, 4-12 mm (5/32,3/16,1/4,5/16,3/8,1/2) |  | 700
|  | 3 pcs Metal drill bit, 4-12 mm (5/32,3/16,1/4,5/16,3/8,1/2) |  | 1800
|  | 20 pcs Big plastic basket (plastic crates) | 1 lot | 350 | 7000 | Shopping | 15 calendar days
|  | 4 pcs 24-inch Wall mounted suttter exhaust fan | 1 lot | 7500 | 30000 | Shopping | 15 calendar days
|  | 1 pc Vespa 1HP belt driven Air Cmpressor, 88 L, 100 to 115 Psi | 1 lot | 20000 | 20000 | Shopping | 30 calendar days
|  | 1 lot Wooden peg board 1m x 4m with 50 pcs rods and installation | 1 lot | 30000 | 30000 | Shopping | 15 calendar days |  | 1 lot
|  | 1 lot Wall-mounted wooden clothes rack, swivel-type with installation | 1 lot | 30000 | 30000 | Shopping | 15 calendar days |  | 1 lot
50203080 00 |  | Medical, Dental, and Laboratory Supplies Expenses
|  | 50 boxes Facemask KF94, 100 pcs per box | 1 lot | 200 | 72750 | Shopping | 15 calendar days
|  | 5 packs Heavy duty clear plastic bag size 40" x 60", 50pcs per pack |  | 4000 |  |  |  |  | 1 lot
|  | 5 packs Heavy duty clear plastic bag size 25" x 50", 50pcs per pack |  | 3500
|  | 5 packs Heavy duty clear plastic bag size 20" x 40", 50pcs per pack |  | 3000
|  | 25 rolls Garbage bag, XL, 10 pcs per roll |  | 150
|  | 25 rolls Garbage bag, 2XL, 10 pcs per roll |  | 200
|  | 100 pcs Resealable zip lock bag, 4"x6.5" |  | 15
|  | 1 pc. Digital platform weighing scale | 1 lot | 4500 | 4500 | Shopping | 15 calendar days |  | 1 lot
|  | 10000 kgs Cotton Lint | 10000 kgs | 130 | 130000 | Negotiated Procurement - Small Value Procurement | 30 calendar days |  | 4000 kgs | 6000 kgs
50203090 00 |  | Fuel, Oil and Lubricants Expenses
|  | -Fuel, Oils and Lubricants | 1,680 liters | 120 | 201600 | Direct Contracting
50299040 00 |  | Transportation and Delivery Expenses
|  | 20 lots Courier Services | 20 lots | 300 | 6000 | Petty Cash Fund |  |  | 10 lots | 10 lots
|  | 8 lots Transport of Materials | 8 lots | 5000 | 40000 | Petty Cash Fund |  |  | 8 lots | 8 lots
|  | 2 lots Trucking Services | 2 lots | 55000 | 110000 | Negotiated Procurement - Small Value Procurement / Shopping |  |  | 2 lots | 1 lot
50299990 99 |  | Other Maintenance and Operating Expenses
|  | 2 lots Preventive Maintenance and Repair of six (6) Airconditioning Units | 2 lots | 20000 | 40000 | Negotiated Procurement - Small Value Procurement |  |  | 1 lot | 1 lot
50201010 00 |  | Travelling Expenses – Local
|  | Travel expense | 1 lot | 50000 | 50000 | Negotiated Procurement - Small Value Procurement
50299030 00 |  | Representation Expenses
|  | Representation | 25 lots | 100 | 2500 | Shopping
50211990 00 |  | Other Professional Services
|  | Calibration (digital timer, thermometer, balance) | 1 lot | 70000 | 70000 | Direct contracting
50204020 00 |  | Electricity Expenses
|  | 3 lots Electricity | 3 lots | 25000 | 75000 | Direct Contracting |  | 1 lot | 1 lot | 1 lot
Equipment Outlay
|  | 1 set Decorticating Machine - capacity 400-600 kg (fabrication) | 1 lot | 2397000 | 2397000 | Public Bidding |  |  |  | 1 lot
|  | 1 set 50HP Steam Boiler (fabrication) | 1 lot | 3080000 | 3080000 | Public Bidding |  | 1 lot
|  | 1 set Degumming Machine; Capacity: 1000 L / 65 kg (Fiber) (Fabrication) | 1 lot | 6050000 | 6050000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Mechanical Softening Machine (fabrication) | 1 lot | 1760000 | 1760000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Chemical Softening Machine (fabrication) | 1 lot | 1100000 | 1100000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Fiber Dryer (Fabrication) | 1 lot | 1320000 | 1320000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Fiber Cutting Machine (fabrication) | 1 lot | 1000000 | 1000000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Fiber 1 lot Opener (fabrication) | 1 lot | 1650000 | 1650000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Integrated Blow Card with 40 pcs Sliver Cans and Laptop | 1 lot | 4042000 | 4042000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Double Feed Drawframe Machine with 100 pcs Sliver Cans | 1 lot | 2772000 | 2772000 | Public Bidding |  |  |  | 1 lot
|  | 1 set 24 Spindles Roving Machine with 2000 pcs Roving Tubes and Laptop | 1 lot | 2887000 | 2887000 | Public Bidding |  |  |  | 1 lot
|  | 4 sets 96 Spindles Ring Frame Machine with 5000 RF Bobbins | 1 lot | 869000 | 3476000 | Public Bidding |  |  |  | 1 lot
|  | 1 set 12 Drums Winding Machine with 7000 pcs Paper Cones | 1 lot | 4042000 | 4042000 | Public Bidding |  |  |  | 1 lot
|  | 2 sets 64 Spindles Twisting Machine with 5000 Twister Bobbins | 1 lot | 2887500 | 5775000 | Public Bidding |  |  |  | 1 lot
|  | 1 set 12 Drums Sizing Machine with 10,000 pcs Paper Cones | 1 lot | 4620000 | 4620000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Yarn Singeing Machine | 1 lot | 3300000 | 3300000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Reeling Machine (Cone to Muff Winder) | 1 lot | 1650000 | 1650000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Yarn Mercerizing Machine lot | 1 lot | 3300000 | 3300000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Re-Reeling Machine (Muff to Cone Winder) | 1 lot | 3300000 | 3300000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Sliver Wrap Block | 1 lot | 220000 | 220000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Yarn Wrap Reel | 1 lot | 220000 | 220000 | Public Bidding |  |  |  | 1 lot
|  | 1 set Electronic Weighing Scale | 1 lot | 137000 | 137000 | Public Bidding |  |  | 1 lot
|  | 5 sets Air Conditioning System | 1 lot | 170000 | 850000 | Public Bidding |  |  | 1 lot
<-- INSERT ROW IF NEEDED
TOTAL APPROVED BUDGET: |  |  | 58948000
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
ENGR. ALEXANDER M. ARGAME, JR. |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Progaram Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________