## Draft PPMP Q2 - GAA Frontier Na
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
END-USER/UNIT: RDD-CDABUS
Charged to: GAA-CICA project entitled "FRONTIER: Fostering the Revitalization of Nascent Textile Innovation Ecosystems in the Regions - Establishment of Natural Dye Hub"
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Apr | May | Jun | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
50604050 03 |  | Information & Communication Technology Equipment
|  | Conference Room Projector | 1 piece | 50000 | 50000 | Shopping | 15 working days | 1 | 0 | 0
|  | Wireless Presentation Remote and Laser | 2 pieces | 3000 | 6000 | Shopping | 15 working days | 2 | 0 | 0
|  | HDMI Cable | 3 pieces | 1500 | 6000 | Shopping | 15 working days | 4 | 0 | 0
|  | Universal Extension Cable | 3 pieces | 3000 | 3000 | Shopping | 15 working days | 5 | 0 | 0
50203010 02 |  | Office Supplies Expenses
|  | Permanent marker (blue) | 1 box | 1000 | 1000 | Shopping | 15 working days | 1 | 0 | 0
|  | Permanent marker (black) | 1 box | 1000 | 1000 | Shopping | 15 working days | 1 | 0 | 0
|  | Pencil | 5 boxes | 150 | 750 | Shopping | 15 working days | 2 | 2 | 1
|  | Sharpener | 2 pieces | 300 | 600 | Shopping | 15 working days | 1 | 1 | 0
|  | Ballpen (Blue) | 100 pieces | 20 | 2000 | Shopping | 15 working days | 45 | 30 | 30
|  | Gel pen (Blue) | 50 pieces | 100 | 5000 | Shopping | 15 working days | 15 | 15 | 10
|  | Masking tape medium size | 25 pieces | 100 | 2500 | Shopping | 15 working days | 10 | 10 | 5
|  | Masking tape large size | 25 pieces | 120 | 3000 | Shopping | 15 working days | 10 | 10 | 5
|  | Double adhesive tape | 25 pieces | 100 | 2500 | Shopping | 15 working days | 10 | 10 | 5
|  | Cubicle workstation | 2 lots | 22500 | 45000 | Shopping | 15 working days | 2 | 0 | 0
|  | Conference table | 1 piece | 15000 | 15000 | Shopping | 15 working days | 1 | 0 | 0
|  | Sofa set | 1 set | 30000 | 30000 | Shopping | 15 working days | 1 | 0 | 0
|  | Reversible Magnetic Mobile White Board | 1 pieces | 5000 | 5000 | Shopping | 15 working days | 3 | 0 | 0
|  | White Board Marker | 100 pieces | 100 | 10000 | Shopping | 15 working days | 100 | 0 | 0
|  | White Board Eraser | 20 pieces | 80 | 1600 | Shopping | 15 working days | 20 | 0 | 0
|  | Printer Ink | 50 sets | 3000 | 150000 | Shopping | 15 working days | 20 | 20 | 10
|  | Multipurpose-Scissors | 10 pieces | 250 | 2500 | Shopping | 15 working days | 3 | 3 | 2
|  | Toner | 25 pieces | 8000 | 200000 | Shopping | 15 working days | 15 | 5 | 5
|  | Printer Maintenance Box | 5 pieces | 2000 | 10000 | Shopping | 15 working days | 5 | 0 | 0
|  | Sewing Thread Rack, 48 spool, wall-mounted | 5 pieces | 3000 | 15000 | Shopping | 15 working days | 5 | 0 | 0
|  | Expanding Envelopes | 50 pieces | 200 | 10000 | Shopping | 15 working days | 50 | 0 | 0
|  | Paper Clips, various sizes | 50 boxes | 200 | 10000 | Shopping | 15 working days | 59 | 0 | 0
|  | Binder Clips, various sizes | 50 boxes | 200 | 10000 | Shopping | 15 working days | 59 | 0 | 0
|  | Portable Storage Box | 15 boxes | 3000 | 45000 | Shopping | 15 working days | 15 | 0 | 0
|  | Hardbound Signing Folder | 20 pieces | 1000 | 20000 | Shopping | 15 working days | 20 | 0 | 0
|  | A4 Size Bond Paper | 25 boxes | 1700 | 42500 | Shopping | 15-30 working days | 25 | 0 | 0
|  | Folio Size Bond Paper | 25 boxes | 1700 | 42500 | Shopping | 15-30 working days | 25 | 0 | 0
|  | Acrylic Name Plate Stand | 20 pieces | 500 | 10000 | Shopping | 15 working days | 25 | 0 | 0
50203080 00 |  | Medical, Dental Laboratory Supplies Expenses
|  | Vacuum pump | 2 lots | 40000 | 80000 | Shopping | 30 working days | 2 | 0 | 0
|  | Nitrile Gloves, ambidextrous, non-sterile, powder-free, various sizes | 25 boxes | 1500 | 37500 | Shopping | 60-90 working days | 50 | 0 | 0
|  | White Nylon Mechanic Work Gloves, Size 7, Small, Nitrile Foam Coating | 10 packs | 4000 | 40000 | Shopping | 15 working days | 10 | 0 | 0
|  | White Nylon Mechanic Work Gloves, Size 8, Medium, Nitrile Foam Coating | 10 packs | 5500 | 55000 | Shopping | 15 working days | 10 | 0 | 0
|  | White Nylon Mechanic Work Gloves, Size 10, XL, Nitrile Foam Coating | 10 packs | 6500 | 65000 | Shopping | 15 working days | 10 | 0 | 0
|  | Stainless Steel Laboratory Trolley | 2 pieces | 5000 | 10000 | Shopping | 30 working days | 2 | 0 | 0
|  | Beaker with handle 3000 mL, borosilicate glass | 5 pieces | 2000 | 10000 | Shopping | 30 working days | 5 | 0 | 0
|  | Bleaching Solution | 40 gallons | 500 | 20000 | Shopping | 15 working days | 40 | 0 | 0
|  | Liquid Detergent | 20 bottles | 900 | 18000 | Shopping | 15 working days | 20 | 0 | 0
|  | Liquid Handsoap | 20 bottles | 500 | 10000 | Shopping | 15 working days | 20 | 0 | 0
|  | Disinfectant Spray | 25 bottles | 800 | 20000 | Shopping | 15 working days | 50 | 0 | 0
|  | UV-Vis Rectangular Quartz Cuvette, with frosted and clear sides, 10mm | 4 pieces | 10000 | 40000 | Negotiated Procurement - Small Value Procurement | 30 working days | 4 | 0 | 0
|  | Quartz Cuvette, with frosted and clear sides, 20mm | 4 pieces | 10000 | 40000 | Negotiated Procurement - Small Value Procurement | 30 working days | 4 | 0 | 0
|  | Whatman Filter Paper, 125mm | 25 boxes | 5000 | 125000 | Shopping | 15 working days | 25 | 0 | 0
|  | Cleaning Sponge (Foam and Scratch) | 48 pieces | 100 | 4800 | Shopping | 15 working days | 48 | 0 | 0
|  | Alcohol (Isopropyl) | 20 gallons | 530 | 10600 | Shopping | 15 working days | 50 | 0 | 0
|  | Alcohol dispenser | 5 pieces | 1000 | 5000 | Shopping | 15 working days
|  | Fabric conditioner (Downy antibac) | 15 packs | 500 | 7500 | Shopping | 15 working days | 15 | 0 | 0
|  | Laundry bar (Perla) | 25 pieces | 20 | 500 | Shopping | 15 working days | 25 | 0 | 0
|  | Multipurpose Sponge and Foam (Scotch Brite) | 25 pieces | 75 | 1875 | Shopping | 15 working days | 25 | 0 | 0
|  | Natural dye powder (Yellow ginger) | 2 kilogram | 25000 | 25000 | Shopping | 30 working days | 1 | 0 | 0
|  | Natural dye powder (Mahogany) | 2 kilogram | 25000 | 25000 | Shopping | 30 working days | 1 | 0 | 0
|  | Natural dye powder (Talisay) | 2 kilogram | 25000 | 25000 | Shopping | 30 working days | 1 | 0 | 0
|  | Stainless Steel Strainers | 50 pieces | 250 | 12500 | Shopping | 15 working days | 5 | 0 | 0
|  | Glass container with aluminum lid 250ml | 25 pieces | 125 | 3125 | Shopping | 30 working days | 25 | 0 | 0
|  | Glass container with aluminum lid 50ml | 100 pieces | 75 | 7500 | Shopping | 30 working days | 100 | 0 | 0
|  | PET bottles 250ml | 50 pieces | 500 | 25000 | Shopping | 30 working days | 20 | 20 | 10
|  | Non-Ionic detergent (Cleanmate) | 25 gallons | 800 | 20000 | Shopping | 30 working days | 25 | 0 | 0
|  | LPG Refill | 10 pieces | 1500 | 15000 | Shopping | Per schedule | 10 | 0 | 0
|  | Hose and regulator | 3 pieces | 1000 | 3000 | Shopping | 15 working days | 3 | 0 | 0
|  | Plastic bag (black) Large | 25 pieces | 150 | 3750 | Shopping | 15 working days | 25 | 0 | 0
|  | Plastic bag (clear) Large | 25 pieces | 150 | 3750 | Shopping | 15 working days | 25 | 0 | 0
|  | Multipurpose Rag | 100 pieces | 5 | 500 | Shopping | 15 working days | 100 | 0 | 0
|  | Disposable Face Mask | 20 boxes | 100 | 2000 | Shopping | 15 working days | 50 | 0 | 0
|  | Interfolded paper towels, 2 ply, 150 pulls, 30 packs per box | 30 boxes | 2500 | 75000 | Shopping | 15 working days | 30 | 0 | 0
|  | Tissue paper, 3 ply, 24 rolls per pack | 30 packs | 1000 | 30000 | Shopping | 15 working days | 30 | 0 | 0
|  | Methanol, 2.5L, AR, CAS No. 67-56-1 | 20 bottles | 1500 | 30000 | Negotiated Procurement - Small Value Procurement | 30 working days | 20 | 0 | 0
|  | Acetone, AR, 2.5L per bottle, CAS No. 67-64-1 | 10 bottles | 5000 | 50000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Nutrient Broth, analytic grade, 500 grams per bottle | 10 bottles | 7000 | 70000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Guar Gum, analytic grade, 1 kg per bottle | 3 bottles | 15000 | 45000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 1 | 1
|  | Cream of tartar, 500g per bottle | 2 bottles | 500 | 1000 | Negotiated Procurement - Small Value Procurement | 30 working days
|  | Ammonium sulfate, 500g per bottle | 2 bottles | 1000 | 2000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 1 | 0
|  | Sodium acetate, 500g per bottle | 2 bottles | 1500 | 3000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 1 | 0
|  | Sodium Benzoate, 500g per bottle | 2 bottles | 1000 | 2000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 1 | 0
|  | Citric Acid, 500g per bottle | 2 bottles | 800 | 1600 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 1 | 0
|  | Tartaric Acid/Oxalic Acid, 1000g per bottle | 2 bottles | 1500 | 3000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 1 | 0
|  | Sodium carbonate, 500g per bottle | 2 bottles | 800 | 1600 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 1 | 0
|  | Potassium Alumium sulfate, Analytical grade, 1000g per bottle | 1 bottle | 3000 | 3000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 0 | 0
|  | Potassium Alumium sulfate, technical grade, 1000g per bottle | 2 bottles | 500 | 1000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 1 | 0
|  | Sodium hydroxide | 25 kilograms | 600 | 15000 | Negotiated Procurement - Small Value Procurement | 30 working days | 25 | 0 | 0
|  | Copper Sulfate | 75 kilograms | 450 | 33750 | Negotiated Procurement - Small Value Procurement | 30 working days | 75 | 0 | 0
|  | Soda ash | 25 kilograms | 450 | 11250 | Negotiated Procurement - Small Value Procurement | 30 working days | 25 | 0 | 0
|  | Glacial Acetic Acid, technical grade, 30 kg per carbouy | 10 bottles | 1200 | 12000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Sodium hydrosulfite | 10 kilograms | 900 | 9000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Calcium hydroxide(lime) | 10 kilograms | 600 | 6000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Ethanol, 4L/cby | 5 carboy | 2500 | 12500 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Hydrogen Peroxide | 10 carboy | 2000 | 20000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
50203990 00 |  | Other Supplies Expenses
|  | Silkscreen Printing Table and Accessories | 1 set | 50000 | 50000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 0 | 0
|  | Fluorscent Lamp | 5 pieces | 2000 | 10000 | Negotiated Procurement - Small Value Procurement | 30 working days
|  | Cable wires | 1 lot | 500 | 25000 | Negotiated Procurement - Small Value Procurement | 30 working days
|  | Weighing balance, digital, 0.5-7.5kg | 25 pieces | 1000 | 25000 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Weighing balance, mechanical, 60kg | 25 pieces | 3000 | 75000 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Tongs | 60 pieces | 2000 | 120000 | Negotiated Procurement - Small Value Procurement | 30 working days | 15 | 0 | 0
|  | LPG Tank and Refill | 10 pieces | 6000 | 60000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Stirrers | 25 pieces | 800 | 20000 | Negotiated Procurement - Small Value Procurement | 30 working days | 25 | 0 | 0
|  | Strainer small | 30 pieces | 750 | 7500 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Strainer medium | 30 pieces | 1050 | 10500 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Strainer large | 30 pieces | 1350 | 13500 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Beakers | 30 pieces | 5400 | 54000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Graduated Cylinders | 60 pieces | 5400 | 27000 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Polyethylene plastic (standard) | 25 packs | 1800 | 9000 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Measuring cup, max 2 L capacity | 60 pieces | 900 | 54000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Stainless steel cup, 1L (for colormatching) | 60 pieces | 4000 | 240000 | Negotiated Procurement - Small Value Procurement | 30 working days | 25 | 0 | 0
|  | Stainless steel vessel, 5L capacity | 60 pieces | 5000 | 300000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Stainless vessel, 10L capacity | 60 pieces | 7000 | 420000 | Negotiated Procurement - Small Value Procurement | 30 working days | 25 | 0 | 0
|  | Seedlings | 1 lot | 5000 | 25000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 0 | 0
|  | Plastic container, 120L | 10 pieces | 900 | 9000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Water sprinklers | 10 pieces | 700 | 7000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Water can | 5 pieces | 700 | 3500 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Mosquito net | 5 pieces | 400 | 10000 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Canvas (Lona) | 5 pieces | 4500 | 27000 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Shovel Round | 5 pieces | 900 | 4500 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Shovel Spade | 5 pieces | 900 | 4500 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Pico | 10 pieces | 900 | 9000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Pruning shear | 10 pieces | 900 | 9000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Bolo | 5 pieces | 2500 | 12500 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Hoe | 5 pieces | 1500 | 7500 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Carborundum | 5 pieces | 500 | 2500 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 0 | 0
|  | Seedling bag | 10 pieces | 1500 | 15000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | Stainless vessel, 20 - 30 L cap. | 20 pieces | 8000 | 160000 | Negotiated Procurement - Small Value Procurement | 30 working days | 20 | 0 | 0
|  | Coffee powder, 200g per bottle | 5 pieces | 600 | 3000 | Negotiated Procurement - Small Value Procurement | 30 working days | 2 | 2 | 1
|  | Ceramic mug and saucer | 15 pieces | 500 | 7500 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 5 | 5
|  | Drinking glass | 15 pieces | 100 | 1500 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 5 | 5
|  | Ceramic plates | 15 pieces | 100 | 1500 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 5 | 5
|  | Placemats | 15 pieces | 150 | 1500 | Negotiated Procurement - Small Value Procurement | 30 working days | 5 | 5 | 5
|  | Stainless vessel, 60 - 70 L cap | 15 pieces | 20000 | 300000 | Negotiated Procurement - Small Value Procurement | 30 working days | 15 | 0 | 0
|  | Silkscreen frames | 25pieces | 1000 | 25000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 10 | 5
|  | Photographic table/light box | 1 piece | 50000 | 5000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 0 | 0
|  | Flat iron | 2 pieces | 1500 | 3000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 1 | 0
|  | Hair blower | 1 piece | 2000 | 2000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 0 | 0
|  | Hand-held steamer | 1 piece | 3000 | 3000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 0 | 0
|  | Paint brush | 50 pieces | 100 | 5000 | Negotiated Procurement - Small Value Procurement | 30 working days | 15 | 15 | 10
|  | Craft Art blades | 10 sets | 500 | 5000 | Negotiated Procurement - Small Value Procurement | 30 working days | 4 | 3 | 3
|  | Pails | 15 pieces | 1000 | 15000 | Negotiated Procurement - Small Value Procurement | 30 working days | 15 | 0 | 0
|  | Basin | 15 pieces | 1000 | 15000 | Negotiated Procurement - Small Value Procurement | 30 working days | 15 | 0 | 0
|  | Vietcong Burners | 20 pieces | 5000 | 100000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10 | 0 | 0
|  | 20 pieces Naturally-dyed handloom woven fabrics | 1 lot | 30000 | 600000 | Negotiated Procurement - Small Value Procurement | Per schedule
|  | Dye sources - Talisay leaves | 50 kilograms | 40 | 2000 | Cash Advance | Per schedule | 50 | 0 | 0
|  | Dye sources - Annatto seeds | 50 kilograms | 250 | 12500 | Cash Advance | Per schedule | 25 | 0 | 0
|  | Dye sources - Buko | 25 kilograms | 50 | 1250 | Cash Advance | Per schedule | 25 | 0 | 0
|  | Dye sources - Cogon grass | 25 kilograms | 40 | 1000 | Cash Advance | Per schedule | 25 | 0 | 0
|  | Dye sources - Yellow ginger | 25 kilograms | 150 | 3750 | Cash Advance | Per schedule | 25 | 0 | 0
50211990 00 |  | Other Professional Services
|  | Heavy metal testing for fibers and fabrics | 10 lots | 50000 | 500000 | Negotiated Procurement - Small Value Procurement | Per schedule
|  | Colorfastness Test for Dyed Fabrics | 10 lots | 5000 | 50000 | Negotiated Procurement - Small Value Procurement | Per schedule
|  | Commissioned exhibit materials | 10 lots | 10000 | 100000 | Negotiated Procurement - Small Value Procurement | Per schedule | 10 | 0 | 0
|  | General Provision for Services | 5 lots | 10000 | 50000 | Negotiated Procurement - Small Value Procurement | Per schedule | 5 | 0 | 0
|  | Other professional services, weaving of 20 meters (length) × 20 inches (width), naturally-dyed yarns | 5 lots | 49999 | 249995 | Negotiated Procurement - Small Value Procurement | Per schedule | 5 | 0 | 0
|  | Other professional services, sewing and development of naturally-dyed wearables for men and women | 5 lots | 30000 | 150000 | Negotiated Procurement - Small Value Procurement | Per schedule | 5 | 0 | 0
|  | Other professional services, sewing and development of naturally-dyed pina-bamboo fabrics into barong for men and women | 2 lots | 15000 | 30000 | Negotiated Procurement - Small Value Procurement | Per schedule | 2 | 0 | 0
Printing and Binding Expenses
|  | Printing Services (Tarpaulin, etc.) | 10 lots | 7000 | 70000 | Negotiated Procurement - Small Value Procurement | Per schedule
Training expenses
|  | Training, seminars, and conferences expenses | 5 lots | 15000 | 75000 | Cash Advance | Per schedule | 0 | 2 | 3
50299040 00 |  | Delivery and Transportation Expenses
|  | Delivery expense, from DOST-PTRI to weaving communities, partners, and stakeholders, and vice-versa | 30 lots | 1000 | 30000 | Cash Advance | Per schedule | 10 | 10 | 10
|  | Transportation expense, from DOST-PTRI to weaving communities, partners, and stakeholders, and vice-versa | 30 lots | 1000 | 30000 | Cash Advance | Per schedule | 10 | 10 | 10
50213050 14 |  | Repair and Maintenance
|  | Additional Works for NatDyes Hubs | 3 lots | 600000 | 1800000 | Negotiated Procurement | 120 working days | 1 | 1 | 1
|  | TBI repairs | 1 lot | 500000 | 500000 | Negotiated Procurement | 120 working days
|  | Construction Works for NatDyes Hubs | 2 lots | 1500000 | 3000000 | Negotiated Procurement | 120 working days | 1 | 1 | 1
|  | Signages for NatDyes Hubs | 5 lots | 200000 | 1000000 | Negotiated Procurement | 120 working days | 2 | 2 | 1
Local Travel Expenses
|  | Airplane Tickets | 15 lots | 50000 | 750000 | Negotiated Procurement - Small Value Procurement | Per schedule | 5 | 10 | 5
|  | Bus Tickets | 20 lots | 3000 | 60000 | Negotiated Procurement - Small Value Procurement | Per schedule | 5 | 10 | 5
|  | TNVS Fares | 15 lots | 2000 | 30000 | Cash Advance | Per schedule | 5 | 5 | 5
Foreign Travel Expenses
|  | Airplane Tickets for Local and Foreign Resource Speakers of 2024 Philippine Dyes and Colorants Symposium | 2 lots | 50000 | 100000 | Negotiated Procurement - Small Value Procurement | Per schedule | 0 | 0 | 2
|  | Hotel Accommodation for Local and Foreign Resource Speakers of 2024 Philippine Dyes and Colorants Symposium | 2 lots | 30000 | 60000 | Negotiated Procurement - Small Value Procurement | Per schedule | 0 | 0 | 2
50299030 00 |  | Representation Expenses
|  | Meals and snacks for meetings, trainings, and events | 15 lots | 15000 | 225000 | Negotiated Procurement - Small Value Procurement | Per schedule | 5 | 5 | 5
Subscription Expenses
|  | Scientific Software | 1 lot | 500000 | 500000 | Negotiated Procurement - Small Value Procurement | Per schedule | 0 | 0 | 1
50604050 14 |  | Capital Outlay - Technical & Scientific Equipment
|  | UV-Vis Spectrophotometer | 1 lot | 2000000 | 2000000 | Negotiated Procurement | 120 working days | 0 | 0 | 1
|  | Shaking Incubator | 1 lot | 250000 | 250000 | Negotiated Procurement | 120 working days | 0 | 0 | 1
|  | Dye Source Chopper/Shredder | 1 lot
|  | Bench Scale Extraction/Dyeing Assembly and Accessories | 1 lot | 200000 | 200000 | Negotiated Procurement - Small Value Procurement | 90 working days | 1 | 0 | 0
|  | Packaging and Labelling Machine | 1 lot | 200000 | 200000 | Negotiated Procurement - Small Value Procurement | 90 working days | 1 | 0 | 0
|  | Digital Centrifuge | 1 lot | 200000 | 200000 | Negotiated Procurement - Small Value Procurement | 120 working days | 1 | 0 | 0
TOTAL APPROVED BUDGET: |  |  | 13767045
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
JENNELI E. CAYA |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Officer-in-Charge, Research and Development Division |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Revision Date: 17 April 2024 |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________

## Previous Q1 PPMP (Reference)
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
END-USER/UNIT: RDD-CDABUS
Charged to: FRONTIER: Fostering the Revitalization of Nascent Textile Innovation Ecosystems in the Regions - Establishment of Natural Dye Hub
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Jan | Feb | Mar | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
50604050 03 |  | Information & Communication Technology Equipment
|  | WiFi Printer and Scanner | 3 lots | 20000 | 60000 | Shopping | 30-45 working days | 3 | 0 | 0
|  | Laptop Computer with Microsoft Office License | 4 lots | 49995 | 199980 | Shopping | 30-45 working days | 4 | 0 | 0
|  | Scientific Software | 1 lot | 300000 | 300000 | Negotiated Procurement-Small Value Procurement | 30-45 working days | 1 | 0 | 0
|  | HDMI Cable | 4 pieces | 3000 | 12000 | Shopping | 30-45 working days | 4 | 0 | 0
|  | Mirrorless Compact Digital Camera | 1 lot | 49995 | 49995 | Shopping | 30-45 working days | 1 | 0 | 0 | [23 empty] | 2/29/2024-Received PR from End-user(for Endorsement) -Sir Jake revised just the RFQ form
|  | Screen Projector and Portable Panel | 1 lot | 49995 | 49995 | Shopping | 30-45 working days | 0 | 0 | 1
|  | Speaker and Microphone | 1 lot | 49995 | 49995 | Shopping | 30-45 working days | 0 | 0 | 1
50203010 02 |  | Office Supplies Expenses
| OS-026 | 25 boxes A4 Size Bond Paper | 1 lot | 1700 | 95350 | Shopping | 15-30 working days | 0 | 25 | 0
| OS-056 | 25 boxes Folio Size Bond Paper |  | 1700 |  |  |  | 0 | 25 | 0
| OS-073 | 25 pieces Label Sticker Flag |  | 100 |  |  |  | 0 | 25 | 0
| OS-161 | 25 pieces Sticky Notepad |  | 150 |  |  |  | 0 | 25 | 0
|  | 25 pieces White Board Marker |  | 100 |  |  |  | 0 | 25 | 0
|  | 25 pieces White Board Eraser |  | 80 |  |  |  | 0 | 20 | 0
|  | Printer Ink | 50 sets | 3000 | 150000 | Shopping | 15-30 working days | 0 | 50 | 0
|  | Toner | 25 pieces | 8000 | 200000 | Shopping | 15-30 working days | 0 | 25 | 0
|  | Printer Maintenance Box | 5 pieces | 2000 | 10000 | Shopping | 15-30 working days | 0 | 5 | 0
|  | Data Filing Cabinet | 2 pieces | 30000 | 60000 | Shopping | 15-30 working days | 0 | 2 | 0
|  | Sewing Thread Rack, 48 spool, wall-mounted | 5 pieces | 3000 | 15000 | Shopping | 15-30 working days | 0 | 5 | 0
|  | Interfolded paper towels, 2 ply, 150 pulls, 30 packs per box | 30 boxes | 2500 | 75000 | Shopping | 15-30 working days | 0 | 0 | 30
|  | Tissue paper, 3 ply, 24 rolls per pack | 30 packs | 1000 | 30000 | Shopping | 15-30 working days | 0 | 0 | 30
|  | Expanding Envelopes | 50 pieces | 200 | 10000 | Shopping | 15-30 working days | 0 | 0 | 50
|  | Paper Clips, various sizes | 50 boxes | 200 | 10000 | Shopping | 15-30 working days | 0 | 0 | 50
|  | Binder Clips, various sizes | 50 boxes | 200 | 10000 | Shopping | 15-30 working days | 0 | 0 | 50
|  | Portable Storage Box | 15 boxes | 3000 | 45000 | Shopping | 15-30 working days | 0 | 0 | 15
|  | MOA Folder | 20 pieces | 1000 | 20000 | Shopping | 15-30 working days | 0 | 0 | 20
|  | Acrylic Name Plate Stand | 20 pieces | 500 | 10000 | Shopping | 15-30 working days | 0 | 0 | 20
50203080 00 |  | Medical, Dental Laboratory Supplies Expenses
| MDL-076 | Sodium Hydroxide, liquid, 48-50% concentration, 30kg per carbouy | 10 carbouys | 2000 | 20000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 10 | 0 | 0 | 2402-0152 dd. 02-19-2024 | 0288-24 dtd. 02-22-2024 | [21 empty] | 02/26/2024- Done Recording PR and RFQ No. (For PhilGEPS)
| MDL-005 | Sodium Metabisulfite, technical grade | 10 kilograms | 350 | 3500 |  |  | 5 | 0 | 0
| MDL-006 | Sodium Silicate, technical grade | 50 liters | 500 | 25000 |  |  | 150 | 0 | 0
| MDL-076 | Sodium Hydroxide, flakes, technical grade | 15 kilograms | 600 | 9000 |  |  | 55 | 0 | 0
|  | Potash Alum, technical grade | 15 kilograms | 200 | 3000 |  |  | 55 | 0 | 0
|  | Sodium Hydrosulfite, technical grade | 10 kilograms | 900 | 9000 |  |  | 55 | 0 | 0
| MDL-139 | Hydrochloric Acid, 37%, analytic grade, 2.5L per bottle | 4 bottles | 3000 | 12000 |  |  | 4 | 0 | 0
| MDL-014 | Sulfuric Acid, 98%, analytic grade, 2.5L per bottle | 4 bottles | 3000 | 12000 |  |  | 4 | 0 | 0
|  | Acetone, analytic grade, 2.5L per bottle | 10 bottles | 5000 | 50000 |  |  | 4 | 0 | 0
|  | Sodium Sulfite, anhydrous, analytic grade, 500g per bottle | 8 bottles | 2000 | 16000 |  |  | 8 | 0 | 0
|  | Guar Gum, analytic grade, 1 kg per bottle | 3 bottles | 15000 | 45000 |  |  | 3 | 0 | 0
|  | Sodium Alginate, analytic grade, 1kg per bottle | 3 bottles | 15000 | 45000 |  |  | 3 | 0 | 0
|  | Copper Sulfate | 1 lot | 450 | 11250 |  |  | 55 | 0 | 0
|  | Soda Ash | 25 kilograms | 450 | 11250 |  |  | 25 | 0 | 0
|  | Nutrient Broth, analytic grade, 500 grams per bottle | 10 bottles | 7000 | 70000
| MDL-228 | Glacial Acetic Acid, technical grade, 30 kg per carbouy | 10 carbouys | 5500 | 55000 |  |  | 10 | 0 | 0
| MDL-158 | Ethanol, technical grade, 4L per carbouy | 10 carbouys | 2500 | 25000 |  |  | 10 | 0 | 0
| MDL-255 | Hydrogen Peroxide, technical grade, 30kg per carbouy | 30 carbouys | 4500 | 135000 |  |  | 30 | 0 | 0
| MDL-017 | Methanol, 2.5L, AR | 20 bottles | 1500 | 30000 |  |  | 10 | 0 | 0
|  | Calcium Hydroxide (Lime) | 15 kilograms | 700 | 10500 |  |  | 15 | 0 | 0
|  | Bleaching Solution | 40 gallons | 500 | 20000 |  |  | 40 | 0 | 0
|  | Non-Ionic Detergent | 60 gallons | 800 | 48000 |  |  | 60 | 0 | 0
| OSMI-031 | Liquid Detergent | 20 bottles | 900 | 18000 |  |  | 10 | 0 | 0
|  | Liquid Handsoap | 20 bottles | 500 | 10000 |  |  | 20 | 0 | 0
|  | Disinfectant Spray | 50 bottles | 800 | 40000 |  |  | 50 | 0 | 0
|  | Weighing Balance, digital, 0.5-7.5kg | 10 units | 12000 | 120000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 10 | 0 | 0
|  | UV-Vis Rectangular Quartz Cuvette, with frosted and clear sides, 10mm | 4 pieces | 10000 | 40000 | Shopping | 60-90 working days | 4 | 0 | 0
|  | Quartz Cuvette, with frosted and clear sides, 20mm | 4 pieces | 10000 | 40000 | Shopping | 60-90 working days | 4 | 0 | 0
|  | Whatman Filter Paper, 125mm | 25 boxes | 5000 | 125000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 25 | 0 | 0
|  | Weighing Balance, mechanical, 60kg | 10 units | 8000 | 80000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 10 | 0 | 0
|  | 5 sets Tong, various sizes | 1 lot | 2500 | 29000 | Shopping | 60-90 working days | 5 | 0 | 0
|  | 5 sets Stirrer, various sizes |  | 900 |  |  |  | 5 | 0 | 0
|  | 5 sets Strainer, various sizes |  | 2400 |  |  |  | 5 | 0 | 0
|  | 5 sets Glass Beakers, various sizes |  | 10000 | 100000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 5 | 0 | 0
|  | 5 sets Glass Cylinder, various sizes |  | 10000 |  |  |  | 5 | 0 | 0
|  | Stainless Steel Vessel, various sizes | 5 sets | 45000 | 225000 | Negotiated Procurement / Shopping | 60-90 working days | 5 | 0 | 0
|  | Vietcong Burner, various sizes | 5 sets | 6000 | 30000 | Shopping | 60-90 working days | 5 | 0 | 0
|  | 5 packs Polyethylene Plastic, standard size | 1 lot | 1000 | 36000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 5 | 0 | 0
| OSMI-056 | 10 pieces Plastic Pail with Handle and Cover, 32L capacity |  | 600 |  |  |  | 10 | 0 | 0
|  | 10 pieces Plastic Basin, 64L capacity |  | 1000 |  |  |  | 10 | 0 | 0
|  | 10 sets Measuring Cup, max 2L capacity |  | 1000 |  |  |  | 10 | 0 | 0
|  | 10 packs Polyethylene Bags |  | 500 |  |  |  | 10 | 0 | 0
| MDL-264 | Thermometer, 0-110 degrees Celsius | 10 pieces | 500 | 5000 | Shopping | 60-90 working days | 10 | 0 | 0
| MDL-193 | Nitrile Gloves, ambidextrous, non-sterile, powder-free, various sizes | 25 boxes | 1500 | 37500 | Shopping | 60-90 working days | 25 | 0 | 0
|  | LPG Tank/Fuel | 20 tanks | 5000 | 100000 | Direct Retail | 60-90 working days | 0 | 20 | 0
|  | Isoprophyl Alcohol, 70% solution | 48 pieces | 200 | 9600 | Shopping | 15-30 working days | 0 | 0 | 48
|  | Cleaning Sponge (Foam and Scratch) | 48 pieces | 100 | 4800 | Shopping | 15-30 working days | 0 | 0 | 48
50203990 00 |  | Other Supplies Expenses
|  | Portable Abaca Stripping Machine | 30 sets | 7000 | 210000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 0 | 30 | 0
|  | Silkscreen Table and Accessories | 1 set | 50000 | 50000 | Shopping | 15-30 working days | 0 | 1 | 0
|  | Airconditioning Unit | 4 lots | 50000 | 200000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 4 | 0 | 0
|  | White Nylon Mechanic Work Gloves, various sizes | 5 packs | 6000 | 30000 | Shopping | 15-30 working days | 0 | 5 | 0
|  | 10 pieces Pruning Shear | 1 lot | 1000 | 48000 | Shopping | 15-30 working days | 0 | 10 | 0
|  | 25 pieces Bolo |  | 700 |  |  |  | 0 | 25 | 0
|  | 15 pieces Hoe |  | 700 |  |  |  | 0 | 15 | 0
|  | 10 pieces Pico |  | 1000 |  |  |  | 0 | 10 | 0
|  | Carborondum | 5 pieces | 700 | 3500 | Shopping | 15-30 working days | 0 | 5 | 0
|  | Water Can, Water Sprinkler | 5 sets | 1500 | 7500 | Shopping | 15-30 working days | 0 | 5 | 0
|  | Mosquito Net | 25 yards | 500 | 2500 | Shopping | 15-30 working days | 0 | 25 | 0
|  | Canvas (Lona/Weather Protection Cover) | 50 meters | 200 | 10000 | Shopping | 15-30 working days | 0 | 50 | 0
|  | Seedling, Seedling Bag | 5 lots | 6500 | 32500 | Shopping | 15-30 working days | 0 | 5 | 0
|  | Plastic Container, 120L capacity | 15 pieces | 1000 | 15000 | Shopping | 15-30 working days | 0 | 15 | 0
|  | Handloom-Woven Piña-Silk Fabrics | 100 yards | 980 | 98000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 100 | 0 | 0 | 2402-0107 dtd. 02-13-2024 | 0221-0107 dtd. 02-13-2024 | [21 empty] | 2/20/2024-Recorded PR and RFQ No. Note: 99,000 ung sa PR nila, same sa revised PPMP
|  | Handloom-Woven Pure Silk Fabrics | 100 yards | 980 | 98000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 100 | 0 | 0
|  | Handloom-Woven Abaca Fabrics | 100 yards | 980 | 98000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 100 | 0 | 0
|  | Handloom-Woven Pineapple Fabrics | 100 yards | 980 | 98000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 100 | 0 | 0
|  | Indigo Dye Powder | 7 kilograms | 8000 | 56000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 7 | 0 | 0 | 2402-0106 dtd. 02/13/2024 | 0222-24 dtd. 02/13/2024 | [21 empty] | 2/20/2024-Recorded PR and RFQ Note: 7000 lng unit cost nasa PR nila before
|  | Plant-Based Natural Dye Sources, reference, various | 1 lot | 5000 | 5000 | Shopping | 15-30 working days | 1 | 0 | 0
|  | Natural Dye Sources, preparation/research, various | 10 lots | 15000 | 150000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 2 | 4 | 4
|  | Spinning Tubes | 500 pieces | 95 | 47500 | Negotiated Procurement-Small Value Procurement | [27 empty] | 02/29/2024-Received PR from End-User(For Endorsement)
|  | Portable Fabric Stands, various sizes | 20 pieces | 1000 | 20000 | Shopping | 15-30 working days | 0 | 0 | 20
|  | Luggage | 2 pieces | 15000 | 30000 | Shopping | 15-30 working days | 0 | 0 | 2
|  | First Aid Box with Medical Supplies | 7 pieces | 4500 | 31500 | Shopping | 15-30 working days | 0 | 0 | 7
|  | Sling Bag with Compartment | 7 pieces | 2000 | 14000 | Shopping | 15-30 working days | 0 | 0 | 7
|  | Resin for Dye Sources | 1 lot | 50000 | 50000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 0 | 0 | 1
|  | Portable Hand-held Iron Steamer | 1 piece | 20000 | 20000 | Shopping | 15-30 working days | 0 | 0 | 1
|  | Silicon Carbide (Knife Sharpening Tool) | 5 pieces | 500 | 2500 | Shopping | 15-30 working days | 0 | 0 | 1
50211990 00 |  | Other Professional Services
|  | Colorfastness Test for Dyed Fabrics | 5 lots | 10000 | 50000 | Negotiated Procurement-Small Value Procurement | Per Schedule | 0 | 5 | 0
|  | Hand-Woven Sustainable Shoes | 125 pieces | 2500 | 312500 | Negotiated Procurement-Small Value Procurement | Per Schedule | 125 | 0 | 0 | 2402-0197 dtd. 02-26-2024 | 0355-24 dtd. 02-27-2024 | [21 empty] | 02/26/2024-Received PR from End-User 02/28/2024-Recorded PR No. 03/06/2024-Recorded RFQ No.
|  | Printing Services | 10 lots | 1500 | 15000 | Shopping / Cash Advance | Per Schedule | 2 | 4 | 4
|  | Technical Specifications -Weaving of naturally-dyed yarns into drop-down fabrics -Length: at least 20 meters -Width: at least 20 inches Supplementary Documents -Quotations must be submitted with the following: 1. Updated and valid Mayor's Permit 2. Updated and valid BIR 2303 3. PhilGEPS Registration Certificate Delivery -Delivery Period: 45-60 working days -Inclusive of Value-Added Tax (VAT) and other applicable taxes -Inclusive of delivery charges to DOST-PTRI, General Santos Avenue, Bicutan, Taguig City | 1 lot | 49999 | 49999 |  | 45-60 working days | 0 | 1 | 0 | 2402-0108 dtd. 2-13-2024 | 0220-24 dtd. 2-13-2024 | [21 empty] | 2/20/2024-Recorded PR and RFQ No.
|  | Technical Specifications -NatDyed Prototype Wearable -Sewing and Development of Naturally-Dyed Wearable for Men and Women Supplementary Documents -Quotations must be submitted with the following: 1. Updated and valid Mayor's Permit 2. Updated and valid BIR 2303 3. Signed and notarized Omnibus Swon Statement (OSS) 4. PhilGEPS Registration Certificate Delivery -Delivery Period: 45-60 working days -Inclusive of Value-Added Tax (VAT) and other applicable taxes -Inclusive of delivery charges to DOST-PTRI, General Santos Avenue, Bicutan, Taguig City | 3 sets | 49999 | 149997 |  | 45-60 working days | 0 | 3 | 0 | 2402-0122 dtd. 02-14-2024 | 0225-24 dtd. 02-15-2024 | [21 empty] | 2/20/2024-Recorded PR and RFQ No.
|  | Pure Silk Fabric | 32 meters | 1100 | 35200 |  | 45-60 working days | 0 | 0 | 32
|  | Printing Services - Sintra Boards for the Training and Exhibits on Natural Dyeing | 1 lot | 50000 | 50000 |  | 15-30 working days | 0 | 0 | 1
Subscription Expenses
|  | Industry Market Research on Natural Dyes | 1 lot | 300000 | 300000 | Direct Retail Purchasing | per schedule | 0 | 0 | 1
50299040 00 |  | Delivery and Transportation Expenses
|  | Delivery and Transportation Expenses | 15 lot | 1000 | 15000 | Cash Advance | per schedule | 0 | 0 | 15 | 24/01-0029
|  | Transportation and Delivery Expense -To conduct coordination and collaboration meeting for the 1st Philippine Dyes and Colorants Symposium -Date: 01 March 2024, Friday -From: DOST-PTRI, General Santos Avenue, Bicutan, Taguig City -To: De La Salle - College of St. Benilde, 2554 Taft Avenue, Malate, Manila -Vice-versa List of Passengers: 1. Kimberly P. Veron 2. Randy A. Sales 3. Cris Angelo Pagtalunan | 1 lot | 2000 | 2000 | Cash Advance | per schedule | 0 | 0 | 1 | [23 empty] | 03/04/2024-Received PR from End-user
|  | Transportation and Delivery Expense - Dispatch of indigo-dyed bamboo-lyocell for processing - From Philippine Textile Research Institute, DOST Compound, General Santos Avenue, Bicutan, Taguig City to Bagtason Loom Weavers Association, Bagtason, Bugasong, Philipipines | 1 lot | 3000 | 3000 | Cash Advance | per schedule | 0 | 0 | 1 | [23 empty] | 2/20/2024-Received PR from End-User
50213050 14 |  | Repair and Maintenance
|  | Repair and Maintenance | 3 lots | 600000 | 1800000 | Negotiated Procurement-Small Value Procurement | Per Schedule | 0 | 0 | 3
50604050 14 |  | Capital Outlay - Technical & Scientific Equipment
|  | Bench Scale Extraction/Dyeing Assembly and Accessories | 1 lot | 200000 | 200000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 1 | 0 | 0
|  | Packaging and Labelling Machine | 1 lot | 200000 | 200000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 0 | 1 | 0
|  | Dye Source Chopper/Shredder | 1 lot | 200000 | 200000 | Negotiated Procurement-Small Value Procurement | 30-calendar days | 1 | 0 | 0 | 2402-0151 dtd. 02-19-2024 | 0287-24 dtd. 02-22-2024 | [21 empty] | 02/26/2024- Done Recording PR and RFQ No. (For PhilGEPS)
|  | UV-Vis Spectrophotometer | 1 lot | 2000000 | 2000000 | Public Bidding | 30-calendar days | 1 | 0 | 0 | 2402-0199 dtd. 02-26-2024 | [22 empty] | 02/26/2024-Received PR from End-User 02/28/2024-Recorded PR No.
|  | Digital Centrifuge | 1 lot | 200000 | 200000 | Negotiated Procurement-Small Value Procurement | 30-calendar days | 1 | 0 | 0 | [23 empty] | 02/29/2024-Received PR from End-User
|  | Shaking Incubator | 1 lot | 250000 | 250000 | Negotiated Procurement-Small Value Procurement | 30-calendar days | 1 | 0 | 0 | 2402-0198 dtd. 02-26-2024 | [22 empty] | 02/26/2024-Received PR from End-User 02/28/2024-Recorded PR No.
Cash Advance
|  | Mobile Load Card | 11 pieces | 150 | 1650 | Cash Advance | per schedule | 0 | 0 | 11 | [23 empty] | 02/26/2024-Received PR from End-User
|  | Refill or Liquefied Petroleum Gas (LPG) -Eleven (11) kilograms per tank -For Laboratory use at the TBI NatDyes Center | 4 tanks | 1200 | 4800 | Cash Advance | per schedule | 0 | 0 | 4 | 2402-0196 C/A | [5 empty] | MACRO LIQUID PETROLEUM GAS CO., INC. | 4180 | [7 empty] | 2024-02-28 | 2024-0194 dtd. 2/29/24 | n/a | n/a | n/a | n/a | n/a | n/a | with IAR dtd. 2/29/24
|  | AM Snacks Date: 22 January 2024 Event: Meetiing with MEDTECS Time: 10;00 AM to 12:00 PM Place: TELA Conference, DOST-PTRI | 22 pax | 150 | 3300 | Cash Advance | per schedule | 22 | 0 | 0 | 24/01 0035 dtd. 01-15-2024 | [22 empty] | 02/26/2024-Received PR from End-User -Recorded PR No. (For Out Sir Boysen)
|  | Printing Services -Sintra Boards for the Training and Exhibits on Natural Dyeing with the Abra State Institute of Science and Technology (ASIST) Main Campus, Abra Inclusions: -One (1) piece 31.5 inch x 82.5 inch for Indigo Dyeing -One (1) piece 31.5 inch x 82.5 inch for Natural Dyeing -One (1) piece 31.5 inch x 82.5 inch for Silkscreen Printing -One (1) piece 31.5 inch x 82.5 inch for Natural Paints | 1 lot | 8000 | 8000 | Cash Advance | per schedule | 0 | 1 | 0 | 2402-0121 dtd. 02-14-2024 | 0228-24 dtd. 02-15-2024 | [21 empty] | 2/20/2024-Recorded PR and RFQ No.
|  | Transportation and Delivery Expense - DIspatch of talisay-dyed and undyed cotton yarns for processing - From 364 Edang, Malibay, Pasay City, Metro Manila to Bulbulala, Lapaz, Abra | 1 lot | 2000 | 2000 | Cash Advance | per schedule | 0 | 0 | 1 | [23 empty] | 2/20/2024-Received PR from End-User
|  | Printing Services -Tarpaulin for the Technical Lecture and Training on Natural Dyeing and MOA Signing Ceremony between the DOST-PTRI and Abra State Institute of Science and Technology (ASIST) Main Campus Inclusions: -One (1) piece 36 in x 72 in tarpaulin for Mondanting -One (1) piece 36 in x 72 in tarpaulin for Extraction -One (1) piece 36 in x 72 in tarpaulin for Pre-treatment -One (1) piece 36 in x 72 in tarpaulin for Dyeing | 1 lot | 5000 | 5000 | Cash Advance | per schedule | 0 | 0 | 1 | [23 empty] | 2/20/2024-Received PR from End-User
|  | Customized Piña-Based Fabric for Barong Technical Specifications -Warp: Piña-Seda -Weft: Bamboo-PTF blend fabric -Design: Customized embroidery for barong tops | 2 lot | 7200 | 14400 | Cash Advance | 15 calendar days | 0 | 0 | 2 | [23 empty] | 2/20/2024-Received PR from End-User
50299030 00 |  | Representation Expenses
|  | AM Snacks @ ₱100/pax | 10 pax | 100 | 1000 | Cash Advance | per schedule | 0 | 0 | 10 | [23 empty] | 2/20/2024-Received PR from End-User
|  | Lunch @ 250.00/pax | 10 pax | 250 | 2500 |  | per schedule |  |  | 10
|  | AM Snacks Date: 22 January 2024 Event: Meetiing with MEDTECS Time: 10;00 AM to 12:00 PM Place: TELA Conference, DOST-PTRI | 22 pax | 150 | 3300 | Cash Advance | per schedule | 22 | 0 | 0 | 24/01 0035 dtd. 01-15-2024 | [22 empty] | 02/26/2024-Received PR from End-User -Recorded PR No. (For Out Sir Boysen)
|  | AM Snacks @ ₱100.00/pax Date: 28 February 2024, 10:00 a.m. to 12:00 p.m. | 20 pax | 100 | 2000 | Cash Advance | per schedule | 0 | 20 | 0 | 2402-0234 dtd. 02-28-2024 | [22 empty] | 03/04/2024-Received PR from End-user -Recorded PR No.
|  | Lunch @ 250.00/pax Date: 28 February 2024, 10:00 a.m. to 12:00 p.m. | 15 pax | 250 | 3750 |  | per schedule |  | 15
TOTAL APPROVED BUDGET: |  |  | 10489611
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
JENNELI E. CAYA |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Officer-in-Charge, Research and Development Division |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Revision Date: 13 March 2024 |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________