## 2nd Quarter as of 04-24-24
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
End-User/Unit: TSD-MPU
Charged to: Regional Yarn Production and Innovation Center (RYPIC) - Mindanao
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | APR | MAY | JUN | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
50203010 02 |  | Office Supplies Expenses
|  | 27 pieces RYPIC Mindanao Polo Shirt | 1 lot | 700 | 18900 | Shopping | 30 working days | 27
|  | 4 pieces Universal Extension Wheel / Cord | 2 lots | 2200 | 16000 | Shopping | 30 working days | 4
|  | 6 pieces Individual Switch Extension Cord, 4 gang |  | 1200 |  |  |  | 6
|  | 10 units Stand Fan | 10 units | 6500 | 65000 | Negotiated Procurement - Small Value Procurement | 30 working days | 10
|  | 1 pieces Air Blow Gun | 1 lot | 3000 | 7000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1
|  | 1 roll Air Hose |  | 4000 |  |  |  | 1
|  | 10 packs Heavy duty clear plastic bag: size 40" x 60"; 50pcs per pack | 2 lots | 5000 | 25000 | Shopping | 30 working days |  | 10
|  | 10 packs Heavy duty clear plastic bag: size 25" x 50"; 50pcs per pack |  | 4000 |  |  |  |  | 10
|  | 10 packs Heavy duty clear plastic bag: size 20" x 40"; 50pcs per pack |  | 3500 |  |  |  |  | 10
|  | 6 pieces CALCULATOR, compact, 12 digits | 2 lots | 1000 | 280600 | Shopping | 30 working days |  | 6
|  | 100 pieces NOTEPAD stick on 3" x 3" yellow |  | 250 |  |  |  |  | 100
|  | 10 pieces RULER, plastic, 450mm |  | 80 |  |  |  |  | 10
|  | 100 pieces SIGN PEN, BLUE, liquid/gel ink, 0.5mm needle tip |  | 300 |  |  |  |  | 100
|  | 6 pieces STAPLER, w/ Remover : NO.35 |  | 300 |  |  |  |  | 6
|  | 20 boxes STAPLE WIRE NO.35 : max 5000's/box |  | 150 |  |  |  |  | 20
|  | 4 pieces White Board (3x4 ft) |  | 3000 |  |  |  |  | 4
|  | 50 pieces MARKER, whiteboard, blue |  | 200 |  |  |  |  | 50
|  | 4 pieces Tape dispenser, table top |  | 500 |  |  |  |  | 4
|  | 30 rolls TAPE, masking, 24mm |  | 70 |  |  |  |  | 30
|  | 30 rolls TAPE, masking, 48mm |  | 80 |  |  |  |  | 30
|  | 10 boxes BATTERY, dry cell, size: AA |  | 2000 |  |  |  |  | 10
|  | 10 boxes BATTERY, dry cell, size: AAA |  | 3000 |  |  |  |  | 10
|  | 10 pairs SCISSORS, symmetrical, blade length: 65mm min |  | 80 |  |  |  |  | 10
|  | 100 boxes CLIP, BACKFOLD, all metal, clamping: 19mm (-1mm) |  | 70 |  |  |  |  | 100
|  | 50 boxes CLIP, BACKFOLD, all metal, clamping: 25mm (-1mm) |  | 80 |  |  |  |  | 50
|  | 50 boxes CLIP, BACKFOLD, all metal, clamping: 50mm (-1mm) |  | 90 |  |  |  |  | 50
|  | 4 pieces 3 Layer Desk File Organizer Document Paper Tray (27cm×35cm×28cm) |  | 500 |  |  |  |  | 4
|  | 20 pieces DATA FILE BOX, magazine box made of chipboard, with closed ends |  | 200 |  |  |  |  | 20
|  | 20 boxes PAPER CLIP, vinyl/plastic coat, length: 32mm min |  | 30 |  |  |  |  | 20
|  | 20 boxes PAPER CLIP, vinyl/plastic coat, length: 50mm min |  | 50 |  |  |  |  | 20
|  | 100 pcs Brown Document Envelope, A4/Short |  | 50 |  |  |  |  | 100
|  | 100 pcs Brown Document Envelope, Legal/Long (10" x 15") |  | 80 |  |  |  |  | 100
|  | 50 books RECORD BOOK, 500 pages, size: 214mm x 278mm min |  | 300 |  |  |  |  | 50
|  | 100 reams PAPER, multicopy, A4, 80 gsm |  | 350 |  |  |  |  | 100
|  | 100 reams PAPER, multicopy, legal, 80 gsm |  | 450 |  |  |  |  | 100
|  | 4 boxes RUBBER BAND, 70mm min lay flat length (#18) |  | 400 |  |  |  |  | 4
|  | 10 boxes PENCIL, lead w/ eraser, wood cased, hardness |  | 200 |  |  |  |  | 10
50203210 03 |  | Semi- Expendable - ICT Equipment
|  | 2 units All-in-One Tank Printer | 1 lot | 49000 | 178000 | Negotiated Procurement - Small Value Procurement | 30 working days | 2
|  | 2 units Color Duplex Document Scanner |  | 40000 |  |  |  | 2
|  | 4 units Wireless Wi-Fi Router | 4 units | 6000 | 24000 | Negotiated Procurement - Small Value Procurement | 30 working days | 4
50203090 00 |  | Fuel, Oil and Lubricants Expenses
|  | 30 drums Diesel fuel 210L/ drum | 1 lot | 17000 | 510000 | Direct Retail | 30 working days |  |  | 30
50299040 00 |  | Transportation and Delivery Expense
|  | 10 lots Transport of Materials | 5 lots | 4500 | 45000 | Petty Cash Fund |  | 8 | 2
|  | 2 lots Trucking Services | 2 lots | 50000 | 100000 | Negotiated Procurement - Small Value Procurement / Shopping |  | 1 | 1
|  | 15 lots Courier Fee of Documents | 15 lots | 300 | 4500 | Petty Cash Fund |  | 6 | 4 | 5
50203990 00 |  | Other Supplies Expenses
|  | 27 pieces RYPIC Mindanao Polo Shirt | 27 pieces | 700 | 18900 | Shopping | 30 working days | 27
|  | 35 pieces Working clothes with embroidered DOST-PTRI logo, white shirt | 35 pieces | 350 | 12250 | Negotiated Procurement - Small Value Procurement | 30 working days |  | 35
|  | 1000 pieces Corrugated box with print | 1000 pieces | 200 | 200000 | Negotiated Procurement - Small Value Procurement | 30 working days |  | 1000
|  | 2 units Water Dispenser | 2 units | 15000 | 30000 | Shopping | 30 working days | 2
|  | 4 pieces Wet and Dry Vacuum Cleaner | 4 pieces | 6500 | 26000 | Shopping | 30 working days | 4
|  | 4 units Hydraulic Hand Pallet Truck | 4 units | 26000 | 104000 | Shopping | 30 working days | 4
|  | 4 units Push Cart | 4 units | 4000 | 16000 | Shopping | 30 working days | 4
|  | 4 pieces 240 L Mobile Trash Bin with Cover | 2 lots | 7000 | 28000 | Shopping | 30 working days | 4
50205020 01 |  | Telephone Expenses – Mobile
|  | 2 lots Telephone and Internet Installation | 2 lots | 10000 | 20000 | Direct Contracting | 30 working days |  | 2
50203220 01 |  | Semi-Expendable - Furniture and Fixtures
|  | 20 pieces Light bulbs | 20 pieces | 500 | 10000 | Shopping | 30 working days | 20
|  | 3 pieces Folding tables | 1 lot | 10000 | 70000 | Shopping | 30 working days | 3
|  | 20 pieces Chairs |  | 2000 |  |  | 30 working days | 20
|  | 2 units Aluminum multi-purpose ladder | 2 units | 10000 | 20000 | Shopping | 30 working days | 2
|  | 1 lot Signage (NTFIH) | 1 lot | 542000 | 1092000 | Public Bidding | 30 working days | 1
|  | 1 lot Signage (RYPIC) |  | 550000 |  |  |  | 1
50203080 00 |  | Medical, Dental Laboratory Supplies Expenses
|  | 1 unit Air Compressor | 1 unit | 25000 | 25000 | Shopping | 30 working days | 1
|  | 1 unit Digital Weighing Scale, max weight: 30kgs | 1 unit | 6500 | 6500 | Shopping | 30 working days | 1
|  | 1 unit Digital Clamp Meter Tester | 1 unit | 3500 | 3500 | Shopping | 30 working days | 1
|  | 30 pairs Laboratory Shoes, random sizes | 30 pairs | 500 | 15000 | Shopping | 30 working days |  | 30
|  | 500 pieces Rags | 500 pieces | 50 | 25000 | Shopping | 30 working days |  | 500
|  | 200 packs Anionic Detergent, 1kg/pack | 200 packs | 50000 | 50000 | Negotiated Procurement - Small Value Procurement | 30 working days |  | 200
|  | 3000 kilograms Banana Pseudostem (Cavendish) | 1 lot | 300 | 975000 | Negotiated Procurement - Small Value Procurement | 30 working days |  | 3000
|  | 300 kilograms Abaca Leaf Sheaths |  | 250 |  |  |  |  | 300
|  | 300 kilograms Bamboo Culm (Kawayang Tinik) | 300 kls | 200 | 60000 | Negotiated Procurement - Small Value Procurement | 30 working days | 300
|  | 1000 kilograms Cotton Lint | 1000 kls | 110 | 110000 | Negotiated Procurement - Small Value Procurement | 30 working days |  | 100
50299030 00 |  | Representation Expenses
|  | 10 lots Meals | 10 lots | 5000 | 50000 | Shopping / Petty Cash Fund | 30 working days | 5 | 5
50215010 01 |  | Taxes, Duties, and Licenses
|  | 1 lot RYPC Cotabato Operations Manual | 1 lot | 2500 | 2500 | Shopping / Petty Cash Fund | 30 working days | 1
|  | 2 lots Notary Public | 2 lots | 350 | 700 | Petty Cash Fund | 30 working days | 1 | 1
50604050 14 |  | Technical & Scientific Equipment-Equipment Outlay
|  | 1 set Yarn Mercerizing Machine | 1 lot | 3000000 | 3000000 | Public Bidding | 90 working days | 1
50211990 00 |  | Other Professional Services
|  | DYEING SERVICE | 1 lot | 200000 | 200000 | Negotiated Procurement - Small Value Procurement | 45 working days | 1
1) Dyeing and Finishing Services of 860 meters (237.5 kg) of woven fabric for Men's Tops of Civil Service Commission
2) Dyeing and Finishing Services of 1114 meters (280.4 kg) of woven fabric for Women's Tops of Civil Service Commission
3) Dyeing and Finishing Services of 928 meters (326.1 kg) of woven fabric for Womens Bottoms of Civil Service Commission
50604050 14 |  | Indirect Cost
|  | 1 unit Microwave Oven | 1 unit | 15000 | 15000 | Negotiated Procurement - Small Value Procurement | 45 working days | 1
|  | 1 unit Heavy Duty Laser Printer | 1 unit | 35000 | 35000 | Negotiated Procurement - Small Value Procurement | 45 working days | 1
TOTAL APPROVED BUDGET: |  |  | 7494350
+ 10% Provision for Inflation |  |  | 749435
+ 10% Contingency |  |  | 749435
TOTAL ESTIMATED BUDGET: |  |  | 8993220
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
DANIEL LEON J. LAVIN |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: April 4, 2024 |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________
6th Revision