## Q1-Silktures
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
END-USER/UNIT: RDD-NFUS
Charged to: Biofunctional and Sustainable Silk-Based Sutures (BioSilktures)
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Apr | May | Jun | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
50213050 02 |  | Repair and Maintenance – Office Equipment
|  | Repair of FTIR | 1 lot | 25000 | 25000 | Negotiated Procurement-Small Value Procurement |  |  |  | 1
|  | Repair of Split Type Wall Mounted Inverter Airconditioner | 4 lot | 8000 | 32000 | Negotiated Procurement-Small Value Procurement |  | 2 |  | 2
|  | Preventive Maintenance of Split Type Wall Mounted Inverter Airconditioner | 2 unit | 8000 | 16000 | Negotiated ProcurementSmall Value Procurement |  | 1 |  | 1
50203010 02 |  | Office Supplies Expenses
|  | 100 pieces Kraft expanding envelope with elastic band, legal size | 1 lot | 80 | 79000 | Shopping |  |  | 100
|  | 10 pieces Metal file organizer rack, 3-layer |  | 850 |  |  |  |  | 10
|  | 10 pieces Stand file organizer box, blue |  | 450 |  |  |  |  | 10
| OS-122 | 100 pieces Sign Pen, blue, liquid/gel ink, 0.5mm tip |  | 80 |  |  |  |  | 100
| OS-182 | 25 reams Paper, Multi-purpose, A4 size, 70gsm |  | 300 |  |  |  |  | 25
| OS-183 | 25 reams Paper, Multi-purpose, Legal size, 70gsm |  | 350 |  |  |  |  | 25
| OS-074 | 25 reams Paper, Pink, A4 size, 70gsm |  | 500 |  |  |  |  | 5
|  | 10 books Record Book, 300 pages, size: 214mm x 278mm (min) |  | 350 |  |  |  |  | 10
|  | 100 pieces 4 trolley 6-drawers Multi-purpose Storage Organizer Trolley |  | 6000 |  |  |  |  | 4
|  | 10 pieces Standard Scissors |  | 50 |  |  |  |  | 10
| OS-217 | 5 pieces Tailor Scissors |  | 150 |  |  |  |  | 5
|  | 5 pieces Sewing Scissors |  | 180 |  |  |  |  | 5
|  | 20 pieces Glue stick |  | 80 |  |  |  |  | 20
|  | 4 pieces Presentation Clicker | 1 lot | 9000 | 111000 | Shopping |  |  |  | 4
|  | 6 boxes Wireless HDMI Transmitter and Reciever |  | 2500 | [5 empty] | 6
|  | 20 pieces Ink Toner 001 Black |  | 750 | [5 empty] | 20
|  | 20 pieces Ink Toner 001 Magenta |  | 750 | [5 empty] | 20
|  | 20 pieces Ink Toner 001 Cyan |  | 750 | [5 empty] | 20
|  | 20 pieces Ink Toner 001 Yellow |  | 750 | [5 empty] | 20
50203080 00 |  | Medical, Dental Laboratory Supplies Expenses
| MDL-080 | 2 bottles Absolute Ethanol, CAS No. 64-17-5, AR Grade, ≥98.5%, 2.5L | 1 lot | 3750 | 145600 | Negotiated Procurement-Small Value Procurement |  |  | 2
|  | 1 bottle Aluminum Oxide Pellets, 3mm, CAS No. 1344-28-1, 95%, 250g |  | 11900 |  |  |  |  | 1
|  | 1 bottle Barium Chloride Dihydrate,10361-37-2, ≥99%, 1kg |  | 8500 |  |  |  |  | 1
|  | 1 bottle Barium Sulfate, CAS No. 7727-43-7, ≥99%, 1kg |  | 20000 |  |  |  |  | 1
|  | 1 bottle Chitosan, CAS No.9012-76-4, ≥75% deacetylation, 250g |  | 40000 |  |  |  |  | 1
|  | 5 bottles Curcumin, CAS No. 458-37-7, ≥ 95%, 10g |  | 4740 |  |  |  |  | 5
|  | 1 bottle Cyrene, CAS No. 53716-82-8, AR Grade, ≥ 98.5%, 100mL |  | 14000 |  |  |  |  | 1
|  | 1 bottle Dimethylformamide, CAS No. 68-12-2, AR Grade, ≥99.8%, 2.5L |  | 10000 |  |  |  |  | 1
|  | 1 bottle Dimethylsulfoxide, CAS No. 67-68-5, AR Grade, ≥99.9%, 2.5L |  | 10000 |  |  |  |  | 1
|  | 1 bottle Ethyl Acetate, CAS No.141-78-6, AR Grade, ≥99.8%, 2.5L | 1 lot | 10000 | 139425 | Negotiated Procurement-Small Value Procurement |  |  | 1
|  | 1 bottle Europium (III) Oxide, CAS No.1308-96-9, ≥ 99.5%, 25g |  | 43200 |  |  |  |  | 1
|  | 1 bottle Fluorescein Sodium Salt,518-47-8, ≥95%, 50g |  | 10000 |  |  |  |  | 1
|  | 1 bottle Hexane, CAS No. 110-54-3, AR Grade, ≥98.5%, 4L |  | 5325 |  |  |  |  | 1
|  | 1 bottle I-Carrageenan, CAS No. 9062-07-1, Commercial Grade, 100g |  | 6000 |  |  |  |  | 1
|  | 2 bottles Lithium Carbonate, CAS No. 554-13-2, ≥99.99%,50g |  | 23000 |  |  |  |  | 2
|  | 1 bottle PDDA, CAS No. 26062-79-3, Mw 200,000-350,000, 1kg |  | 4500 |  |  |  |  | 1
|  | 2 bottles Poly (4-stryneresulfonic acid), 100g |  | 7200 |  |  |  |  | 2
|  | 4 bottles Quinine Sulfate, CAS No.207671-44-1, ≥99%, 25g | 1 lot | 9000 | 164180 | Negotiated Procurement-Small Value Procurement |  |  | 4
|  | 4 bottles Silicon Dioxide, CAS No. 60676-86-0, ≥ 99.9%,25g |  | 7800 |  |  |  |  | 4
|  | 1 bottle Terbium (III, IV) Oxide, CAS No. 12037-01-3, 99.9% trace metals basis, 10g |  | 45480 |  |  |  |  | 1
|  | 2 bottles Urea, CAS No.57-13-6, ACS Grade, ≥95%, 500g |  | 4000 |  |  |  |  | 2
|  | 1 bottle Zinc Chloride, CAS No. 7646-85-7, ≥97%, 1kg |  | 16500 |  |  |  |  | 1
|  | 1 bottle λ-Carrageenan, CAS No. 9064-57-7, ≥90%, 25g, 50g |  | 27000 |  |  |  |  | 1
| MDL-178 | 2 bottles Glacial Acetic Acid, CAS No. 64-19-7, AR Grade, ≥99.8%, 2.5L | 1 lot | 3750 | 96200 | Negotiated Procurement-Small Value Procurement |  |  | 2
|  | 10 carbouys Sodium Hydroxide, 48% Purity, Technical Grade, 30kg |  | 2500 |  |  |  |  | 10
|  | 1 bottle Sodium Lauryl Sulfate, CAS No. 151-21-3, ≥95%, 500g |  | 7200 |  |  |  |  | 1
|  | 1 bottle Sodium Phosphate Dibasic, CAS No. 7558-79-4, 1kg |  | 21000 |  |  |  |  | 1
|  | 1 bottle Sodium Selenite, CAS No. 10102-18-8, 100 g |  | 20000 |  |  |  |  | 1
|  | 1 bottle Sodium Sulfate, CAS No. 7757-82-6, ≥99%, 1 kg |  | 9500 |  |  |  |  | 1
| MDL-228 | 20 bottles Glacial Acetic Acid, Technical Grade, 1 Liter |  | 300 |  |  |  |  | 20
|  | Agate Mortar and Pestle | 1 unit | 49000 | 49000 | Shopping |  |  | 1
50203990 00 |  | Other Supplies Expenses
|  | Banana Fibers | 17.25 kg | 400 | 6900 | Negotiated Procurement/Shopping |  |  | 17.25
|  | Ginned Cotton Fibers | 300 kg | 300 | 90000 | Negotiated Procurement-Small Value Procurement |  |  |  | 300
|  | 13 pieces Safety hard hat, adjustable chin strap and forehead cotton lining, white | 1 lot | 1500 | 40300 | Shopping |  |  | 13
|  | 13 pieces Mesh safety reflective vest |  | 800 |  |  |  |  | 13
|  | 13 pieces Whistle, plastic |  | 300 |  |  |  |  | 13
|  | 13 pieces Flashlight, 100 lumens, rechargeable LIT battery |  | 500 |  |  |  |  | 13
|  | 10 pieces Universal Adaptor Plug | 1 lot | 1000 | 40000 | Shopping |  |  |  | 10
|  | 5 pieces Universal Outlet Extension Cord Power Cable 10 Gang |  | 3000 | [5 empty] | 5
|  | 5 pieces Universal Extension Wheel Cord Power , 10 or 15 meters |  | 3000 | [5 empty] | 5
|  | 1 set Flash Speed Light | 1 lot | 8000 | 11000 | Shopping |  |  |  | 1
|  | 1 set Camera Battery |  | 3000 | [5 empty] | 1
|  | 2 units Lavatory Faucet | 1 lot | 7000 | 18000 | Shopping |  |  | 2
|  | 2 units Wash Basin Connection Pipe |  | 2000 |  | Shopping |  |  | 2
50203010 01 |  | Supplies and Materials Expenses ( Indirect Cost) (FAD-BTS)
|  | 10 boxes Stapler, standard type | 1 lot | 150 | 18310 | Shopping |  |  | 10
|  | 10 boxes Staple wire No.35 |  | 150 |  |  |  |  | 10
|  | 5 boxes Sign pen - blue |  | 300 |  |  |  |  | 5
|  | 30 boxes Fastener, metal |  | 100 |  |  |  |  | 30
|  | 2 boxes Rubber Band |  | 150 |  |  |  |  | 2
|  | 3 Jars GLUE, All Purpose |  | 70 |  |  |  |  | 3
|  | 3 packs Pink Paper A4 |  | 300 |  |  |  |  | 3
|  | 1 pieces Self Inking Stamp (PAID) |  | 1000 |  |  |  |  | 1
|  | 1 pieces Self Inking Stamp (8 Digit Numbers) |  | 1000 |  |  |  |  | 1
|  | 1 pieces Self Inking Stamp (Date Stamp 12 years) |  | 1000 |  |  |  |  | 1
|  | 20 pieces Eraser, Plastic/Rubber |  | 20 |  |  |  |  | 20
|  | 20 boxes Interfolded Paper Towels, 2 ply, 100 pulls,per box |  | 100 |  |  |  |  | 20
|  | 5 packsTissue Paper, 3 ply, 24 rolls per pack |  | 800 |  |  |  |  | 5
50211990 00 |  | Other Professional Services
|  | Weaving Services | 1 lot | 2500 | 2500 | Negotiated Procurement-Small Value Procurement/Cash Advance |  | 1
|  | Cultural Performance (PHWC) | 1 lot | 40000 | 40000 | Negotiated Procurement-Small Value Procurement/Cash Advance
50299020 00 |  | Printing and Publication Expenses
|  | Journal Article | 1 unit | 41443.4 | 41443.4 | Negotiated Procurement/Shopping |  | 1
50205020 01 |  | Telephone Expenses – Mobile
|  | Mobile Load Card | 26 pc | 150 | 3900 | Shopping |  |  | 13 | 13
50299040 00 |  | Transportation and Delivery Expense
|  | Bus Rental for Weavers and Digitalization Staff (PHWC) | 1 lot | 70000 | 70000 | Shopping |  |  | 1
|  | Trucking Services (PHWC) | 1 lot | 30000 | 30000 | Shopping |  |  | 1
50299040 00 |  | Subscription Expenses
|  | Creative Cloud Apps Annual Subscription | 1 license | 4850 | 4850 | Petty Cash Fund / Direct Retail |  |  |  | 1
50604050 14 |  | Technical & Scientific Equipment - Equipment Outlay
|  | Medical Braiding Machine | 1 lot | 3500000 | 3500000 | Public Bidding |  |  | 1
|  | PC Computer with accessories | 3 lots | 125000 | 375000 | Negotiated Procurement/Shopping |  |  | 3
|  | Microscope with imaging software | 1 lot | 1000000 | 1000000 | Public Bidding |  |  |  | 1
TOTAL APPROVED BUDGET: |  |  | 4774608.4
+ 10% Provision for Inflation |  |  | 477460.84
+ 10% Contingency |  |  | 477460.84
TOTAL ESTIMATED BUDGET: |  |  | 5729530.08
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
JULIUS L. LEAÑO JR., Ph.D. |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: ______________________ |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________

## Q2 - Silktures
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
END-USER/UNIT: RDD-NFUS
Charged to: Biofunctional and Sustainable Silk-Based Sutures (BioSilktures)
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | May | Apr | Jun | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
(1): 50203010 02; (3): Office Supplies Expenses | 141570 | 147686
|  | 50 pieces Kraft expanding envelope with elastic band, legal size | 1 lot | 80 | 4000 | Small Value Procurement | 15-30 working days |  | 50 | 50
|  | 5 pieces Metal file organizer rack, 3-layer |  | 850 | 4250 | Small Value Procurement |  |  | 5 | 5
|  | 5 pieces Stand file organizer box, blue |  | 450 | 2250 | Small Value Procurement |  |  | 5 | 5
|  | 50 pieces Sign Pen, blue, liquid/gel ink, 0.5mm tip |  | 80 | 4000 | Small Value Procurement |  |  | 50 | 50
|  | 15 reams Paper, Multi-purpose, A4 size, 70gsm |  | 300 | 4500 | Small Value Procurement |  |  | 15 | 15
|  | 15 reams Paper, Multi-purpose, Legal size, 70gsm |  | 350 | 5250 | Small Value Procurement |  |  | 15 | 15
|  | 15 reams Paper, Pink, A4 size, 70gsm |  | 500 | 7500 | Small Value Procurement |  |  | 15 | 15
|  | 8 books Record Book, 300 pages, size: 214mm x 278mm (min) |  | 350 | 2800 | Small Value Procurement |  |  | 8 | 8
|  | 4 trolley 6-drawers Multi-purpose Storage Organizer Trolley |  | 2000 | 6000 | Small Value Procurement |  |  | 3 | 3
|  | 8 pieces Standard Scissors |  | 50 | 400 | Small Value Procurement |  |  | 8 | 8
|  | 8 pieces Glue stick |  | 80 | 640 | Small Value Procurement |  |  | 8 | 8
|  | Paper Clips, Material: Steel, color: Silver 50mm 100pcs/box | 25 boxes | 120 | 3000 | Shopping |  | 25 |  | 25
|  | 8 pcs Notebook, steno, ≥60 leaves | 8 pieces | 60 | 480 | Shopping |  | 8 |  | 8
|  | Page flags/Marker, assorted colors Size: 1.2 x 4.5 cm, 100 flags/pack | 10 packs | 200 | 2000 | Shopping |  |  | 10 | 10
|  | 3 Office Partition | 1 lot | 28000 | 84000 | Shopping |  | 3 |  | 3
|  | 3 Office Mesh Chair |  | 3500 | 10500 | Shopping |  | 3 |  | 3
(1): 50203080 00; (3): Medical, Dental Laboratory Supplies Expenses | 1276420 | 3000000
|  | Hot Plate with Magnetic Stirring Specifications: 280 mm x 280 mm or equivalent or better 200 - 1500 C temperature range, 1 increment or equivalent or better 100 - 1500 rpm speed or equivalent or better Ceramic Plate | 2 units | 40000 | 80000 | Negotiated Procurement-Small Value Procurement | 30-45 working days | 2 |  | 2
|  | Tabletop Desiccator, 210mm diameter or equivalent or better | 3 lots | 5000 | 15000 | Shopping | 30-45 working days |  | 3 | 3
|  | 5 packs PH Indicator Strip, 0-14 100's per pack | 1 lot | 2500 | 12500 | Negotiated Procurement-Small Value Procurement | 30-45 working days |  | 5 | 5
|  | 25mL Silver, dispersion nanoparticles, 40nm particle size (TEM), 0.02 mg/ml in aqueous buffer, contains sodium citrate as stabilizer, Sigma-Aldrich CAT# 730807 |  | 22000 | 22000 |  | 30-45 working days |  | 1 | 1
|  | 500g Silver Nitrate AR, TPC India 33088 |  | 21000 | 42000 |  | 30-45 working days |  | 2 | 2
|  | 1g Silk Fibroin average mol wt. 100 kDa (water soluble) Sigma Aldrich CAT#925802 |  | 15000 | 15000 |  | 30-45 working days |  | 1 | 1
|  | 2 boxes Filter nPaper #4, 125mm, Whatman, box of 100's |  | 2100 | 4200 |  | 30-45 working days |  | 2 | 2
|  | 500g Lithium Bromide (LiBr) | 1 bottle | 15000 | 15000 | Negotiated Procurement-Small Value Procurement | 30-45 working days |  | 1 | 1
|  | 5 bottles Sulfuric Acid (H2SO4), ≥98%≥98% Analytical Reagent (AR) Volume: 2.5 L/bottle | 5 bottles | 2500 | 12500 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 5 |  | 5
|  | 8 pairs Heat Resistant and Slide Resistant Gloves | 8 pairs | 1000 | 8000 | Shopping |  |  | 8 | 8
|  | 8 pieces Rectangular High-Density Polyethylene (HDPE) with handle Laboratory Basket | 8 pieces | 90 | 720 | Shopping | 30-45 working days |  | 8 | 8
|  | 10 boxes Nitrile Gloves (Medium) | 1 lot | 300 | 12000 | Shopping |  |  | 10 | 10
|  | 10 boxes Nitrile Gloves (Large) |  | 300 |  |  |  |  | 10 | 10
|  | 6 pieces Labgown (Medium) |  | 500 |  |  |  |  | 6 | 6
|  | 6 pieces Labgown (Large) |  | 500 |  |  |  |  | 6 | 6
|  | 20 pieces Beakers, borosilicate glass, 2L | 1 lot | 1300 | 155750 | Negotiated Procurement-Small Value Procurement |  |  | 20 | 20
|  | 15 pieces Beakers, borosilicate glass, 1L |  | 800 |  |  |  |  | 15 | 15
|  | 15 pieces Beakers, borosilicate glass, 500 mL |  | 250 |  |  |  |  | 15 | 15
|  | 10 pieces Graduated cylinder, borosilicate glass, 1L |  | 2400 |  |  |  |  | 10 | 10
|  | 10 pieces Graduated cylinder, borosilicate glass, 500 mL |  | 2000 |  |  |  |  | 10 | 10
|  | 10 pieces Graduated cylinder, borosilicate glass, 100 mL |  | 1000 |  |  |  |  | 10 | 10
|  | 24 pieces Gooch Glass Filter |  | 2500 |  |  |  |  | 24 | 24
|  | Nunc EasYFlask, Filtered 55-mL cell culture flask, surface area = 175 cm2, 30 cases | 1 lot | 7000 | 352000 |  |  | 6 |  | 6
|  | Nunc™ Cell-Culture Treated Multidishes, 24-well multidishes, 150 pcs |  | 24000 |  |  |  | 2 |  | 2
|  | Dulbecco's Modified Eagle's Medium (DMEM), 10 x 500 mL |  | 21000 |  |  |  | 2 |  | 2
|  | Gibco™ 10% fetal bovine serum |  | 50000 |  |  |  | 1 |  | 1
|  | Gibco™, Phosphate Buffer Solution (PBS) without Ca2+ or Mg2+, 10 x 500 mL |  | 20000 |  |  |  | 2 |  | 2
|  | Trypsin-EDTA (0.25%), phenol red, 20 x 100mL |  | 24000 |  |  |  | 2 |  | 2
|  | Trypsin Neutralizing Solution, 100mL |  | 2300 |  |  |  | 20 |  | 20
|  | Sterile conical tubes |  | 30 |  |  |  | 200 |  | 200
|  | Nunc™ MicroWell™ 96-Well Microplates, 160 cases |  | 15000 |  |  |  | 2 |  | 2
|  | Resazurin, 1g | 1 lot | 9000 | 84500 |  |  | 4 |  | 4
|  | 0.22µm Membrane Syringe Filters, 1 box |  | 7500 |  |  |  | 4 |  | 4
|  | Terumo, 20mL Luer Lock Syringe, 50pcs |  | 2000 |  |  |  | 3 |  | 3
|  | Pyrex, Beaker, 1000mL |  | 1000 |  |  |  |  | 5 | 5
|  | Pyrex, Beaker, 500 mL |  | 750 |  |  |  |  | 5 | 5
|  | Petri dish, Sterile, Disposable, With Cover,25 pcs |  | 750 |  |  |  |  | 5 | 5
|  | BioPette™ A P3960-2A (0.1-2 µL) | 1 lot | 13000 | 219000 |  |  |  | 1 | 1
|  | BioPette™ A P3960-10A (0.5-10 µL) |  | 13000 |  |  |  |  | 1 | 1
|  | BioPette™ A P3960-20A (2-20 µL) |  | 13000 |  |  |  |  | 1 | 1
|  | BioPette™ A P3960-100A (10-100 µL) |  | 13000 |  |  |  |  | 1 | 1
|  | BioPette™ A P3960-200A (20-200 µL) |  | 13000 |  |  |  |  | 1 | 1
|  | BioPette™ A P3960-1000A (100-1000 µL) |  | 13000 |  |  |  |  | 1 | 1
|  | 2 µL filtered pipette tips |  | 2000 |  |  |  |  | 10 | 10
|  | 10 uL filtered pipette tips |  | 2000 |  |  |  |  | 10 | 10
|  | 20 µL filtered pipette tips |  | 2000 |  |  |  |  | 10 | 10
|  | 200 µL filtered pipette tips |  | 2000 |  |  |  |  | 10 | 10
|  | 1000 µL filtered pipette tips |  | 2000 |  |  |  |  | 10 | 10
|  | Multichannel pipettor 200 uL |  | 35000 |  |  |  |  | 1 | 1
|  | Multichannel pipette reservoir, 50 mL, disposable reagent reservoir, nonsterile |  | 6000 |  |  |  |  | 1 | 1
|  | 1L PYREX Reagent Bottle Media Bottle Glass | 5 pieces | 1200 | 6000 |  |  |  | 5 | 5
|  | 500mL PYREX Reagent Bottle Media Bottle Glass | 5 pieces | 1000 | 5000 |  |  |  | 5 | 5
|  | 250mL PYREX Reagent Bottle Media Bottle Glass | 5 pieces | 1000 | 5000 |  |  |  | 5 | 5
|  | Lysol No Rinse, 4x1 gal | 1 lot | 7000 | 100250 |  |  |  |  | 2
|  | 70% Isopropanol, 1 carboy |  | 3000 | [5 empty] | 10
|  | Household bleach, 1 gal |  | 1000 | [5 empty] | 5
|  | Paper towels, 30 packs |  | 1500 | [5 empty] | 10
|  | Hairnet, 100 pcs |  | 170 | [5 empty] | 5
|  | Mask, 50 pcs |  | 180 | [5 empty] | 25
|  | Gloves, 100 pcs |  | 250 | [5 empty] | 25
|  | Laboratory Gown with cuff, Free size |  | 950 | [5 empty] | 6
|  | Laboratory Shoes, Free size |  | 600 | [5 empty] | 6
|  | Shoe covers, 100 pcs |  | 150 | [5 empty] | 5
|  | Yellow plastic bags, 10 pcs, Medium |  | 100 | [5 empty] | 15
|  | Yellow plastic bags, 10 pcs, XXL |  | 100 | [5 empty] | 15
|  | Black bags, 10 pcs, XXL |  | 100 | [5 empty] | 15
|  | Trash bin, yellow, 80L |  | 1800 | [5 empty] | 1
|  | Trash bin, yellow, 100L |  | 2000 | [5 empty] | 1
|  | Red biohazard plastic bag, 10 pcs |  | 300 | [5 empty] | 5
|  | Dust Remover, Sticky Floor Mat |  | 300 | [5 empty] | 12
|  | Floor Mop |  | 1200 | [5 empty] | 1
|  | Refrigerator, Two-door, 1 lot | 1 lot | 45000 | 45000 |  |  |  |  | 1
|  | Window-type Aircon, 1.5 Horse power | 1 lot | 35000 | 35000 |  |  |  |  | 1
|  | Airpurifier, 2 units | 1 lot | 30000 | 30000 |  |  |  |  | 1
(1): 50203990 00; (3): Other Supplies Expenses | 209090 | 250000
|  | 4 pieces Wired Headphones with Microphone Specifications Input Impedance: 32ohm Sensitivity (Headphone): 94dBV/Pa +/-3dB or equivalent or better Frequency Response (Headset): 20Hz to 20kHz or equivalent or better USB Port (Type A port or Adapter) Color: Black | 1 lot | 3000 | 31000 | Shopping |  |  | 4 | 4
|  | 3 pieces External and Portable Hard Drive for Windows Specifications: Storage: 1TB or equivalent or better Color: Silver/Black |  | 5000 |  |  |  |  | 3 | 3
|  | 4 pieces Flashdrive Storage: 64GB or equivalent or better Color: Black |  | 1000 |  |  |  |  | 4 | 4
|  | 16 pieces Safety hard hat, adjustable chin strap and forehead cotton lining, white | 1 lot | 900 | 35200 | Shopping |  |  | 16 | 16
|  | 16 pieces Mesh safety reflective vest |  | 500 |  |  |  |  | 16 | 16
|  | 16 pieces Whistle, plastic |  | 300 |  |  |  |  | 16 | 16
|  | 16 pieces Flashlight, 100 lumens, rechargeable LIT battery |  | 500 |  |  |  |  | 16 | 16
|  | 10 pieces Universal Adaptor Plug | 1 lot | 800 | 15500 | Shopping |  |  |  | 10
|  | 10 pieces Universal Outlet Extension Cord Power Cable with individual switches 6 gang |  | 750 | [5 empty] | 10
|  | First Aid Box with Medical Supplies | 2 sets | 4500 | 9000 | Small Value Procurement | 15-30 working days | 2 |  | 2
|  | Fire Extinguisher | 2 units | 1500 | 3000 | Shopping |  | 2 |  | 2
|  | All-in-one Printer Specifications: - Print Resolution: Black: up to 1200 x 600 rendered dpi - Print Resolution: Color: up to 4800 x 1200 optimized dpi color - USB, Wireless, Wi-Fi - Copy Speed, Black: 480 pages - Copy Speed, Color: 150 pages - Scan Resolution: up to 1200 dpi - Scan Size Maximum: 216 x 297 mm - Monthly Usage Volume: up to 1000 pages | 2 units | 10000 | 20000 | Shopping |  | 2 |  | 2
|  | 20 pieces Customized Certificate Holder | 1 lot | 500 | 10000 | Shopping |  | 20 |  | 20
|  | 10 boxes Mask | 1 lot | 200 | 32500 | Shopping |  | 10 |  | 10
|  | Paper Towels, interfolded, 2 ply 30 packs/box |  | 2000 |  |  |  | 10 |  | 10
|  | 10 packs Ziplock (Small) |  | 150 |  |  |  | 10 |  | 10
|  | 10 packs Ziplock (Medium) |  | 200 |  |  |  | 10 |  | 10
|  | 10 packs Ziplock (Large) |  | 300 |  |  |  | 10 |  | 10
|  | 10 packs Ziplock (Extra Large) |  | 400 |  |  |  | 10 |  | 10
|  | 18 bottles Isopropyl Alcohol with moisturizer, 70%,500ml | 18 bottles | 280 | 5040 |  |  |  | 18 | 18
|  | 3 cans Disinfectant spray, 500 ml | 3 cans | 950 | 2850 |  |  |  | 3 | 3
Long table (for aides)
|  | 15 pieces Ink Toner 001 Black | 1 lot | 750 | 11250 | Small Value Procurement |  | 15 |  | 15
|  | 15 pieces Ink Toner 001 Magenta |  | 750 | 11250 | Small Value Procurement |  | 15 |  | 15
|  | 15 pieces Ink Toner 001 Cyan |  | 750 | 11250 | Small Value Procurement |  | 15 |  | 15
|  | 15 pieces Ink Toner 001 Yellow |  | 750 | 11250 | Small Value Procurement |  | 15 |  | 15
(1): 50211990 00; (3): Other Professional Services | 150500 | 600000
|  | Customized Corporate Polo Shirt with Logo Embroidery - Material: Honeycomb - Color: Purple/Violet - Logo Embroidery: BIOMEDTEX Logo, DOST Logo and PTRI Logo | 35 pieces | 900 | 31500 | Shopping |  | 35 |  | 35
|  | Customized Reversible Corporate Jacket with Detachable Hood Material: Brush twill, Microfiber - with Handloom woven bamboo fabric on lapped zipper - Color: Purple and Dark Navy Blue - Logo Embroidery: BIOMEDTEX Program Logo, DOST Logo, PTRI Logo | 35 pieces | 3400 | 119000 | Shopping |  | 35 |  | 35
50203010 01 |  | Supplies and Materials Expenses ( Indirect Cost) (FAD-BTS)
|  | 10 boxes Stapler, standard type | 1 lot | 150 | 18310 | Shopping |  |  | 10
|  | 10 boxes Staple wire No.35 |  | 150 |  |  |  |  | 10
|  | 5 boxes Sign pen - blue |  | 300 |  |  |  |  | 5
|  | 30 boxes Fastener, metal |  | 100 |  |  |  |  | 30
|  | 2 boxes Rubber Band |  | 150 |  |  |  |  | 2
|  | 3 Jars GLUE, All Purpose |  | 70 |  |  |  |  | 3
|  | 3 packs Pink Paper A4 |  | 300 |  |  |  |  | 3
|  | 1 pieces Self Inking Stamp (PAID) |  | 1000 |  |  |  |  | 1
|  | 1 pieces Self Inking Stamp (8 Digit Numbers) |  | 1000 |  |  |  |  | 1
|  | 1 pieces Self Inking Stamp (Date Stamp 12 years) |  | 1000 |  |  |  |  | 1
|  | 20 pieces Eraser, Plastic/Rubber |  | 20 |  |  |  |  | 20
|  | 20 boxes Interfolded Paper Towels, 2 ply, 100 pulls,per box |  | 100 |  |  |  |  | 20
|  | 5 packsTissue Paper, 3 ply, 24 rolls per pack |  | 800 |  |  |  |  | 5
50205020 01 |  | Telephone Expenses – Mobile
|  | Mobile Load Card | 26 pieces | 150 | 7800 | Shopping |  |  | 26 | 26
(1): 50604050 14; (3): Technical & Scientific Equipment - Equipment Outlay | 4875000
|  | Medical Braiding Machine | 1 lot | 3500000 | 3500000 | Public Bidding |  |  | 1 | 1
|  | PC Computer with accessories | 3 lots | 125000 | 375000 | Negotiated Procurement/Shopping |  |  | 3 | 3
|  | Microscope with imaging software | 1 lot | 1000000 | 1000000 | Negotiated Procurement |  |  |  | 1
TOTAL APPROVED BUDGET: |  |  | 6678690
+ 10% Provision for Inflation |  |  | 667869
+ 10% Contingency |  |  | 667869
TOTAL ESTIMATED BUDGET: |  |  | 8014428
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
JULIUS L. LEAÑO JR., Ph.D. |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: ______________________ |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________

## Q3 Draft - Silktures
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 3rd Quarter of CY 2024
END-USER/UNIT: RDD-NFUS
Charged to: Biofunctional and Sustainable Silk-Based Sutures (BioSilktures)
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Jul | Aug | Sep | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
(1): 50203010 02; (3): Office Supplies Expenses | 141570 | 147686
|  | 50 pieces Kraft expanding envelope with elastic band, legal size | 1 lot | 80 | 4000 | Small Value Procurement | 15-30 working days | 50 | 50
|  | 5 pieces Metal file organizer rack, 3-layer |  | 850 | 4250 | Small Value Procurement |  | 5 | 5
|  | 5 pieces Stand file organizer box, blue |  | 450 | 2250 | Small Value Procurement |  | 5 | 5
|  | 50 pieces Sign Pen, blue, liquid/gel ink, 0.5mm tip |  | 80 | 4000 | Small Value Procurement |  | 50 | 50
|  | 15 reams Paper, Multi-purpose, A4 size, 70gsm |  | 300 | 4500 | Small Value Procurement |  | 15 | 15
|  | 15 reams Paper, Multi-purpose, Legal size, 70gsm |  | 350 | 5250 | Small Value Procurement |  | 15 | 15
|  | 15 reams Paper, Pink, A4 size, 70gsm |  | 500 | 7500 | Small Value Procurement |  | 15 | 15
|  | 8 books Record Book, 300 pages, size: 214mm x 278mm (min) |  | 350 | 2800 | Small Value Procurement |  | 8 | 8
|  | 4 trolley 6-drawers Multi-purpose Storage Organizer Trolley |  | 2000 | 6000 | Small Value Procurement |  | 3 | 3
|  | 8 pieces Standard Scissors |  | 50 | 400 | Small Value Procurement |  | 8 | 8
|  | 8 pieces Glue stick |  | 80 | 640 | Small Value Procurement |  | 8 | 8
|  | Paper Clips, Material: Steel, color: Silver 50mm 100pcs/box | 25 boxes | 120 | 3000 | Shopping |  | 25
|  | 8 pcs Notebook, steno, ≥60 leaves | 8 pieces | 60 | 480 | Shopping |  | 8
|  | Page flags/Marker, assorted colors Size: 1.2 x 4.5 cm, 100 flags/pack | 10 packs | 200 | 2000 | Shopping |  | 10 | 10
|  | 3 Office Partition | 1 lot | 28000 | 84000 | Shopping |  | 3
|  | 3 Office Mesh Chair |  | 3500 | 10500 | Shopping |  | 3
(1): 50203080 00; (3): Medical, Dental Laboratory Supplies Expenses | 1276420 | 3000000
|  | Hot Plate with Magnetic Stirring Specifications: 280 mm x 280 mm or equivalent or better 200 - 1500 C temperature range, 1 increment or equivalent or better 100 - 1500 rpm speed or equivalent or better Ceramic Plate | 2 units | 40000 | 80000 | Negotiated Procurement-Small Value Procurement | 30-45 working days | 2
|  | Tabletop Desiccator, 210mm diameter or equivalent or better | 3 lots | 5000 | 15000 | Shopping | 30-45 working days | 3 | 3
|  | 5 packs PH Indicator Strip, 0-14 100's per pack | 1 lot | 2500 | 12500 | Negotiated Procurement-Small Value Procurement | 30-45 working days | 5 | 5
|  | 25mL Silver, dispersion nanoparticles, 40nm particle size (TEM), 0.02 mg/ml in aqueous buffer, contains sodium citrate as stabilizer, Sigma-Aldrich CAT# 730807 |  | 22000 | 22000 |  | 30-45 working days | 1 | 1
|  | 500g Silver Nitrate AR, TPC India 33088 |  | 21000 | 42000 |  | 30-45 working days | 2 | 2
|  | 1g Silk Fibroin average mol wt. 100 kDa (water soluble) Sigma Aldrich CAT#925802 |  | 15000 | 15000 |  | 30-45 working days | 1 | 1
|  | 2 boxes Filter nPaper #4, 125mm, Whatman, box of 100's |  | 2100 | 4200 |  | 30-45 working days | 2 | 2
|  | 500g Lithium Bromide (LiBr) | 1 bottle | 15000 | 15000 | Negotiated Procurement-Small Value Procurement | 30-45 working days | 1 | 1
|  | 5 bottles Sulfuric Acid (H2SO4), ≥98%≥98% Analytical Reagent (AR) Volume: 2.5 L/bottle | 5 bottles | 2500 | 12500 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 5
|  | 8 pairs Heat Resistant and Slide Resistant Gloves | 8 pairs | 1000 | 8000 | Shopping |  | 8 | 8
|  | 8 pieces Rectangular High-Density Polyethylene (HDPE) with handle Laboratory Basket | 8 pieces | 90 | 720 | Shopping | 30-45 working days | 8 | 8
|  | 10 boxes Nitrile Gloves (Medium) | 1 lot | 300 | 12000 | Shopping |  | 10 | 10
|  | 10 boxes Nitrile Gloves (Large) |  | 300 |  |  |  | 10 | 10
|  | 6 pieces Labgown (Medium) |  | 500 |  |  |  | 6 | 6
|  | 6 pieces Labgown (Large) |  | 500 |  |  |  | 6 | 6
|  | 20 pieces Beakers, borosilicate glass, 2L | 1 lot | 1300 | 155750 | Negotiated Procurement-Small Value Procurement |  | 20 | 20
|  | 15 pieces Beakers, borosilicate glass, 1L |  | 800 |  |  |  | 15 | 15
|  | 15 pieces Beakers, borosilicate glass, 500 mL |  | 250 |  |  |  | 15 | 15
|  | 10 pieces Graduated cylinder, borosilicate glass, 1L |  | 2400 |  |  |  | 10 | 10
|  | 10 pieces Graduated cylinder, borosilicate glass, 500 mL |  | 2000 |  |  |  | 10 | 10
|  | 10 pieces Graduated cylinder, borosilicate glass, 100 mL |  | 1000 |  |  |  | 10 | 10
|  | 24 pieces Gooch Glass Filter |  | 2500 |  |  |  | 24 | 24
|  | Nunc EasYFlask, Filtered 55-mL cell culture flask, surface area = 175 cm2, 30 cases | 1 lot | 7000 | 352000 |  |  | 6
|  | Nunc™ Cell-Culture Treated Multidishes, 24-well multidishes, 150 pcs |  | 24000 |  |  |  | 2
|  | Dulbecco's Modified Eagle's Medium (DMEM), 10 x 500 mL |  | 21000 |  |  |  | 2
|  | Gibco™ 10% fetal bovine serum |  | 50000 |  |  |  | 1
|  | Gibco™, Phosphate Buffer Solution (PBS) without Ca2+ or Mg2+, 10 x 500 mL |  | 20000 |  |  |  | 2
|  | Trypsin-EDTA (0.25%), phenol red, 20 x 100mL |  | 24000 |  |  |  | 2
|  | Trypsin Neutralizing Solution, 100mL |  | 2300 |  |  |  | 20
|  | Sterile conical tubes |  | 30 |  |  |  | 200
|  | Nunc™ MicroWell™ 96-Well Microplates, 160 cases |  | 15000 |  |  |  | 2
|  | Resazurin, 1g | 1 lot | 9000 | 84500 |  |  | 4
|  | 0.22µm Membrane Syringe Filters, 1 box |  | 7500 |  |  |  | 4
|  | Terumo, 20mL Luer Lock Syringe, 50pcs |  | 2000 |  |  |  | 3
|  | Pyrex, Beaker, 1000mL |  | 1000 |  |  |  | 5 | 5
|  | Pyrex, Beaker, 500 mL |  | 750 |  |  |  | 5 | 5
|  | Petri dish, Sterile, Disposable, With Cover,25 pcs |  | 750 |  |  |  | 5 | 5
|  | BioPette™ A P3960-2A (0.1-2 µL) | 1 lot | 13000 | 219000 |  |  | 1 | 1
|  | BioPette™ A P3960-10A (0.5-10 µL) |  | 13000 |  |  |  | 1 | 1
|  | BioPette™ A P3960-20A (2-20 µL) |  | 13000 |  |  |  | 1 | 1
|  | BioPette™ A P3960-100A (10-100 µL) |  | 13000 |  |  |  | 1 | 1
|  | BioPette™ A P3960-200A (20-200 µL) |  | 13000 |  |  |  | 1 | 1
|  | BioPette™ A P3960-1000A (100-1000 µL) |  | 13000 |  |  |  | 1 | 1
|  | 2 µL filtered pipette tips |  | 2000 |  |  |  | 10 | 10
|  | 10 uL filtered pipette tips |  | 2000 |  |  |  | 10 | 10
|  | 20 µL filtered pipette tips |  | 2000 |  |  |  | 10 | 10
|  | 200 µL filtered pipette tips |  | 2000 |  |  |  | 10 | 10
|  | 1000 µL filtered pipette tips |  | 2000 |  |  |  | 10 | 10
|  | Multichannel pipettor 200 uL |  | 35000 |  |  |  | 1 | 1
|  | Multichannel pipette reservoir, 50 mL, disposable reagent reservoir, nonsterile |  | 6000 |  |  |  | 1 | 1
|  | 1L PYREX Reagent Bottle Media Bottle Glass | 5 pieces | 1200 | 6000 |  |  | 5 | 5
|  | 500mL PYREX Reagent Bottle Media Bottle Glass | 5 pieces | 1000 | 5000 |  |  | 5 | 5
|  | 250mL PYREX Reagent Bottle Media Bottle Glass | 5 pieces | 1000 | 5000 |  |  | 5 | 5
|  | Lysol No Rinse, 4x1 gal | 1 lot | 7000 | 100250 |  |  | 2
|  | 70% Isopropanol, 1 carboy |  | 3000 |  |  |  | 10
|  | Household bleach, 1 gal |  | 1000 |  |  |  | 5
|  | Paper towels, 30 packs |  | 1500 |  |  |  | 10
|  | Hairnet, 100 pcs |  | 170 |  |  |  | 5
|  | Mask, 50 pcs |  | 180 |  |  |  | 25
|  | Gloves, 100 pcs |  | 250 |  |  |  | 25
|  | Laboratory Gown with cuff, Free size |  | 950 |  |  |  | 6
|  | Laboratory Shoes, Free size |  | 600 |  |  |  | 6
|  | Shoe covers, 100 pcs |  | 150 |  |  |  | 5
|  | Yellow plastic bags, 10 pcs, Medium |  | 100 |  |  |  | 15
|  | Yellow plastic bags, 10 pcs, XXL |  | 100 |  |  |  | 15
|  | Black bags, 10 pcs, XXL |  | 100 |  |  |  | 15
|  | Trash bin, yellow, 80L |  | 1800 |  |  |  | 1
|  | Trash bin, yellow, 100L |  | 2000 |  |  |  | 1
|  | Red biohazard plastic bag, 10 pcs |  | 300 |  |  |  | 5
|  | Dust Remover, Sticky Floor Mat |  | 300 |  |  |  | 12
|  | Floor Mop |  | 1200 |  |  |  | 1
|  | Refrigerator, Two-door, 1 lot | 1 lot | 45000 | 45000 |  |  | 1
|  | Window-type Aircon, 1.5 Horse power | 1 lot | 35000 | 35000 |  |  | 1
|  | Airpurifier, 2 units | 1 lot | 30000 | 30000 |  |  | 1
(1): 50203990 00; (3): Other Supplies Expenses | 214090 | 250000
|  | 4 pieces Wired Headphones with Microphone Specifications Input Impedance: 32ohm Sensitivity (Headphone): 94dBV/Pa +/-3dB or equivalent or better Frequency Response (Headset): 20Hz to 20kHz or equivalent or better USB Port (Type A port or Adapter) Color: Black | 1 lot | 3000 | 31000 | Shopping |  | 4 | 4
|  | 3 pieces External and Portable Hard Drive for Windows Specifications: Storage: 1TB or equivalent or better Color: Silver/Black |  | 5000 |  |  |  | 3 | 3
|  | 4 pieces Flashdrive Storage: 64GB or equivalent or better Color: Black |  | 1000 |  |  |  | 4 | 4
|  | 16 pieces Safety hard hat, adjustable chin strap and forehead cotton lining, white | 1 lot | 900 | 35200 | Shopping |  | 16 | 16
|  | 16 pieces Mesh safety reflective vest |  | 500 |  |  |  | 16 | 16
|  | 16 pieces Whistle, plastic |  | 300 |  |  |  | 16 | 16
|  | 16 pieces Flashlight, 100 lumens, rechargeable LIT battery |  | 500 |  |  |  | 16 | 16
|  | 10 pieces Universal Adaptor Plug | 1 lot | 800 | 15500 | Shopping |  | 10
|  | 10 pieces Universal Outlet Extension Cord Power Cable with individual switches 6 gang |  | 750 |  |  |  | 10
|  | First Aid Box with Medical Supplies | 2 sets | 4500 | 9000 | Small Value Procurement | 15-30 working days | 2
|  | Fire Extinguisher | 2 units | 1500 | 3000 | Shopping |  | 2
|  | All-in-one Printer Specifications: - Print Resolution: Black: up to 1200 x 600 rendered dpi - Print Resolution: Color: up to 4800 x 1200 optimized dpi color - USB, Wireless, Wi-Fi - Copy Speed, Black: 480 pages - Copy Speed, Color: 150 pages - Scan Resolution: up to 1200 dpi - Scan Size Maximum: 216 x 297 mm - Monthly Usage Volume: up to 1000 pages | 2 units | 10000 | 20000 | Shopping |  | 2
|  | 20 pieces Customized Certificate Holder | 1 lot | 500 | 10000 | Shopping |  | 20
|  | 10 boxes Mask | 1 lot | 200 | 32500 | Shopping |  | 10
|  | Paper Towels, interfolded, 2 ply 30 packs/box |  | 2000 |  |  |  | 10
|  | 10 packs Ziplock (Small) |  | 150 |  |  |  | 10
|  | 10 packs Ziplock (Medium) |  | 200 |  |  |  | 10
|  | 10 packs Ziplock (Large) |  | 300 |  |  |  | 10
|  | 10 packs Ziplock (Extra Large) |  | 400 |  |  |  | 10
|  | 18 bottles Isopropyl Alcohol with moisturizer, 70%,500ml | 18 bottles | 280 | 5040 |  |  | 18 | 18
|  | 3 cans Disinfectant spray, 500 ml | 3 cans | 950 | 2850 |  |  | 3 | 3
|  | Long table | 1 lot | 5000 | 5000 | Small Value Procurement |  | 1
|  | 15 pieces Ink Toner 001 Black | 1 lot | 750 | 11250 | Small Value Procurement |  | 15
|  | 15 pieces Ink Toner 001 Magenta |  | 750 | 11250 | Small Value Procurement |  | 15
|  | 15 pieces Ink Toner 001 Cyan |  | 750 | 11250 | Small Value Procurement |  | 15
|  | 15 pieces Ink Toner 001 Yellow |  | 750 | 11250 | Small Value Procurement |  | 15
(1): 50211990 00; (3): Other Professional Services | 150500 | 600000
|  | Customized Corporate Polo Shirt with Logo Embroidery - Material: Honeycomb - Color: Purple/Violet - Logo Embroidery: BIOMEDTEX Logo, DOST Logo and PTRI Logo | 35 pieces | 900 | 31500 | Shopping |  | 35
|  | Customized Reversible Corporate Jacket with Detachable Hood Material: Brush twill, Microfiber - with Handloom woven bamboo fabric on lapped zipper - Color: Purple and Dark Navy Blue - Logo Embroidery: BIOMEDTEX Program Logo, DOST Logo, PTRI Logo | 35 pieces | 3400 | 119000 | Shopping |  | 35
50203010 01 |  | Supplies and Materials Expenses ( Indirect Cost) (FAD-BTS)
|  | 10 boxes Stapler, standard type | 1 lot | 150 | 18310 | Shopping |  | 10 | 10
|  | 10 boxes Staple wire No.35 |  | 150 |  |  |  | 10 | 10
|  | 5 boxes Sign pen - blue |  | 300 |  |  |  | 5 | 5
|  | 30 boxes Fastener, metal |  | 100 |  |  |  | 30 | 30
|  | 2 boxes Rubber Band |  | 150 |  |  |  | 2 | 2
|  | 3 Jars GLUE, All Purpose |  | 70 |  |  |  | 3 | 3
|  | 3 packs Pink Paper A4 |  | 300 |  |  |  | 3 | 3
|  | 1 pieces Self Inking Stamp (PAID) |  | 1000 |  |  |  | 1 | 1
|  | 1 pieces Self Inking Stamp (8 Digit Numbers) |  | 1000 |  |  |  | 1 | 1
|  | 1 pieces Self Inking Stamp (Date Stamp 12 years) |  | 1000 |  |  |  | 1 | 1
|  | 20 pieces Eraser, Plastic/Rubber |  | 20 |  |  |  | 20 | 20
|  | 20 boxes Interfolded Paper Towels, 2 ply, 100 pulls,per box |  | 100 |  |  |  | 20 | 20
|  | 5 packsTissue Paper, 3 ply, 24 rolls per pack |  | 800 |  |  |  | 5 | 5
50205020 01 |  | Telephone Expenses – Mobile
|  | Mobile Load Card | 26 pieces | 150 | 3900 | Shopping |  | 26 | 26
(1): 50604050 14; (3): Technical & Scientific Equipment - Equipment Outlay | 4875000
|  | Medical Braiding Machine | 1 lot | 3500000 | 3500000 | Public Bidding |  | 1 | 1
|  | PC Computer with accessories | 3 lots | 125000 | 375000 | Negotiated Procurement/Shopping |  | 3 | 3
|  | Microscope with imaging software | 1 lot | 1000000 | 1000000 | Negotiated Procurement |  | 1
TOTAL APPROVED BUDGET: |  |  | 6679790
+ 10% Provision for Inflation |  |  | 667979
+ 10% Contingency |  |  | 667979
TOTAL ESTIMATED BUDGET: |  |  | 8015748
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
JULIUS L. LEAÑO JR., Ph.D. |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: ______________________ |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________

## Q3 - Silktures
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 3rd Quarter of CY 2024
END-USER/UNIT: RDD-NFUS
Charged to: Biofunctional and Sustainable Silk-Based Sutures (BioSilktures)
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Jun | Jul | Aug | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
50213050 02 |  | Repair and Maintenance – Office Equipment
(1): 50203010 02; (3): Office Supplies Expenses | 145420 | 147686
|  | 50 pieces Kraft expanding envelope with elastic band, legal size | 50 pieces | 80 | 41440 | Shopping |  |  | 50
|  | 5 pieces Metal file organizer rack, 3-layer | 5 pieces | 850 |  |  |  |  | 5
|  | 5 pieces Stand file organizer box, blue | 5 pieces | 450 |  |  |  |  | 5
|  | 10 boxes Sign Pen, blue, liquid/gel ink, 0.5mm tip | 10 boxes | 300 |  |  |  |  | 10
|  | Paper, Multi-purpose, A4 size, 70gsm | 2 boxes | 2000 |  |  |  |  | 2
|  | Paper, Multi-purpose, Legal size, 70gsm | 2 boxes | 2500 |  |  |  |  | 2
|  | 15 reams Paper, Pink, A4 size, 70gsm | 15 reams | 500 |  |  |  |  | 15
|  | 8 books Record Book, 300 pages, size: 214mm x 278mm (min) | 8 pieces | 350 |  |  |  |  | 8
|  | 4 trolley 6-drawers Multi-purpose Storage Organizer Trolley | 4 units | 2000 |  |  |  |  | 4
|  | 8 pieces Standard Scissors | 8 pieces | 50 |  |  |  |  | 8
|  | 8 pieces Glue stick | 8 pieces | 30 |  |  |  |  | 8
|  | Paper Clips, Material: Steel, color: Silver 50mm 100pcs/box | 25 boxes | 120 | 3000 | Shopping |  | 25
|  | Office Partition | 8 lots | 11000 | 88000 | Shopping |  | 8
|  | 8 pcs Notebook, steno, ≥60 leaves | 8 pieces | 60 | 480 | Shopping |  | 8
|  | Office Mesh Chair | 3 lots | 3500 | 10500 | Shopping |  | 3
|  | Page flags/Marker, assorted colors Size: 1.2 x 4.5 cm, 100 flags/pack | 10 packs | 200 | 2000 | Shopping |  |  | 10
(1): 50203080 00; (3): Medical, Dental Laboratory Supplies Expenses | 1193120 | 3000000
|  | Hot Plate with Magnetic Stirring Specifications: 280 mm x 280 mm or equivalent or better 200 - 1500 C temperature range, 1 increment or equivalent or better 100 - 1500 rpm speed or equivalent or better Ceramic Plate | 2 units | 40000 | 80000 | Negotiated Procurement-Small Value Procurement | 30-45 working days | 2
|  | Tabletop Desiccator, 210mm diameter or equivalent or better | 3 lots | 5000 | 15000 | Shopping | 30-45 working days |  | 3
|  | 5 packs PH Indicator Strip, 0-14 100's per pack | 5 packs | 2500 | 12500 | Shopping |  |  | 5
|  | 500g Lithium Bromide (LiBr) | 1 bottle | 15000 | 15000 | Negotiated Procurement-Small Value Procurement | 30-45 working days |  | 1
Milli-Q Water
|  | 1g Standard Silk Fibroin | 1 bottle | 17000
Standard PLA
Sodium Bicarbonate (NaHCO3)
Formic Acid CAS No. 64-18-6
Dichloromethane (DCM)
Ethanol
|  | 5 bottles Sulfuric Acid (H2SO4), ≥98%≥98% Analytical Reagent (AR) Volume: 2.5 L/bottle | 5 bottles | 2500 | 12500 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 5
|  | 8 pairs Heat Resistant and Slide Resistant Gloves | 8 pairs | 1000 | 8000 | Shopping |  |  | 8
|  | 8 pieces Rectangular High-Density Polyethylene (HDPE) with handle Laboratory Basket | 8 pieces | 90 | 720 | Shopping | 30-45 working days |  | 8
|  | 10 pieces Magnetic Stirrer (Spin Bar) 8mm x 28mm | 10 pieces | 210 | 3900 | Shopping |  |  |  | 10
|  | 10 pieces Magnetic Stirrer (Spin Bar) 9mm x 35mm | 10 pieces | 180 | [5 empty] | 10
|  | 10 boxes Nitrile Gloves (Medium) | 10 boxes | 300 | 8000 | Shopping |  |  | 10
|  | 10 boxes Nitrile Gloves (Large) | 10 boxes | 300 |  |  |  |  | 10
|  | 6 pieces Labgown (Medium) | 6 pieces | 500 |  |  |  |  | 2
|  | 6 pieces Labgown (Large) | 6 pieces | 500 |  |  |  |  | 2
|  | 20 pieces Beakers, borosilicate glass, 2L | 20 pieces | 1300 | 155750 | Negotiated Procurement-Small Value Procurement |  |  | 20
|  | 15 pieces Beakers, borosilicate glass, 1L | 15 pieces | 800 |  |  |  |  | 15
|  | 15 pieces Beakers, borosilicate glass, 500 mL | 15 pieces | 250 |  |  |  |  | 15
|  | 10 pieces Graduated cylinder, borosilicate glass, 1L | 10 pieces | 2400 |  |  |  |  | 10
|  | 10 pieces Graduated cylinder, borosilicate glass, 500 mL | 10 pieces | 2000 |  |  |  |  | 10
|  | 10 pieces Graduated cylinder, borosilicate glass, 100 mL | 10 pieces | 1000 |  |  |  |  | 10
|  | 24 pieces Gooch Glass Filter | 24 pieces | 2500 |  |  |  |  | 24
Standard Silver Nanoparticles (AgNPs)
Whatman #4
Silver Nitrate (AgNO3) CAS: 7761-88-8
pH 7 Tris Buffer
Polyglycolic Acid (PGA)
|  | Nunc EasYFlask, Filtered 55-mL cell culture flask, surface area = 175 cm2, 30 cases | 6 lots | 7000 | 352000 |  |  | 6
|  | Nunc™ Cell-Culture Treated Multidishes, 24-well multidishes, 150 pcs | 2 lots | 24000 |  |  |  | 2
|  | Dulbecco's Modified Eagle's Medium (DMEM), 10 x 500 mL | 2 lots | 21000 |  |  |  | 2
|  | Gibco™ 10% fetal bovine serum | 1 lot | 50000 |  |  |  | 1
|  | Gibco™, Phosphate Buffer Solution (PBS) without Ca2+ or Mg2+, 10 x 500 mL | 2 lot | 20000 |  |  |  | 2
|  | Trypsin-EDTA (0.25%), phenol red, 20 x 100mL | 2 lots | 24000 |  |  |  | 2
|  | Trypsin Neutralizing Solution, 100mL | 20 bottles | 2300 |  |  |  | 20
|  | Sterile conical tubes | 200 pcs | 30 |  |  |  | 200
|  | Nunc™ MicroWell™ 96-Well Microplates, 160 cases | 2 lots | 15000 |  |  |  | 2
|  | Resazurin, 1g | 4 bottles | 9000 | 84500 |  |  | 4
|  | 0.22µm Membrane Syringe Filters, 1 box | 4 boxes | 7500 |  |  |  | 4
|  | Terumo, 20mL Luer Lock Syringe, 50pcs | 3 lots | 2000 |  |  |  | 3
|  | Pyrex, Beaker, 1000mL | 5 pcs | 1000 |  |  |  |  | 5
|  | Pyrex, Beaker, 500 mL | 5 pcs | 750 |  |  |  |  | 5
|  | Petri dish, Sterile, Disposable, With Cover,25 pcs | 5 lots | 750 |  |  |  |  | 5
|  | BioPette™ A P3960-2A (0.1-2 µL) | 1 piece | 13000 | 219000 |  |  |  | 1
|  | BioPette™ A P3960-10A (0.5-10 µL) | 1 piece | 13000 |  |  |  |  | 1
|  | BioPette™ A P3960-20A (2-20 µL) | 1 piece | 13000 |  |  |  |  | 1
|  | BioPette™ A P3960-100A (10-100 µL) | 1 piece | 13000 |  |  |  |  | 1
|  | BioPette™ A P3960-200A (20-200 µL) | 1 piece | 13000 |  |  |  |  | 1
|  | BioPette™ A P3960-1000A (100-1000 µL) | 1 piece | 13000 |  |  |  |  | 1
|  | 2 µL filtered pipette tips | 10 pieces | 2000 |  |  |  |  | 10
|  | 10 uL filtered pipette tips | 10 pieces | 2000 |  |  |  |  | 10
|  | 20 µL filtered pipette tips | 10 pieces | 2000 |  |  |  |  | 10
|  | 200 µL filtered pipette tips | 10 pieces | 2000 |  |  |  |  | 10
|  | 1000 µL filtered pipette tips | 10 pieces | 2000 |  |  |  |  | 10
|  | Multichannel pipettor 200 uL | 1 piece | 35000 |  |  |  |  | 1
|  | Multichannel pipette reservoir, 50 mL, disposable reagent reservoir, nonsterile | 2 piece | 6000 |  |  |  |  | 1
|  | 1L PYREX Reagent Bottle Media Bottle Glass | 5 pieces | 1200 | 6000 |  |  |  | 5
|  | 500mL PYREX Reagent Bottle Media Bottle Glass | 5 pieces | 1000 | 5000 |  |  |  | 5
|  | 250mL PYREX Reagent Bottle Media Bottle Glass | 5 pieces | 1000 | 5000 |  |  |  | 5
|  | Lysol No Rinse, 4x1 gal | 2 lots | 7000 | 100250 |  |  |  |  | 2
|  | 70% Isopropanol, 1 carboy | 10 carboys | 3000 | [5 empty] | 10
|  | Household bleach, 1 gal | 5 lots | 1000 | [5 empty] | 5
|  | Paper towels, 30 packs | 10 lots | 1500 | [5 empty] | 10
|  | Hairnet, 100 pcs | 5 packs | 170 | [5 empty] | 5
|  | Mask, 50 pcs | 25 boxes | 180 | [5 empty] | 25
|  | Gloves, 100 pcs | 25 boxes | 250 | [5 empty] | 25
|  | Laboratory Gown with cuff, Free size | 6 pieces | 950 | [5 empty] | 6
|  | Laboratory Shoes, Free size | 6 pieces | 600 | [5 empty] | 6
|  | Shoe covers, 100 pcs | 5 packs | 150 | [5 empty] | 5
|  | Yellow plastic bags, 10 pcs, Medium | 15 packs | 100 | [5 empty] | 15
|  | Yellow plastic bags, 10 pcs, XXL | 15 packs | 100 | [5 empty] | 15
|  | Black bags, 10 pcs, XXL | 15 packs | 100 | [5 empty] | 15
|  | Trash bin, yellow, 80L | 1 piece | 1800 | [5 empty] | 1
|  | Trash bin, yellow, 100L | 1 piece | 2000 | [5 empty] | 1
|  | Red biohazard plastic bag, 10 pcs | 5 packs | 300 | [5 empty] | 5
|  | Dust Remover, Sticky Floor Mat | 12 lots | 300 | [5 empty] | 12
|  | Floor Mop | 1 piece | 1200 | [5 empty] | 1
|  | Refrigerator, Two-door, 1 lot | 1 lot | 45000 | 45000 |  |  |  |  | 1
|  | Window-type Aircon, 1.5 Horse power | 1 lot | 35000 | 35000 |  |  |  |  | 1
|  | Airpurifier, 2 units | 1 lot | 30000 | 30000 |  |  |  |  | 1
(1): 50203990 00; (3): Other Supplies Expenses | 222740 | 250000
|  | 4 pieces Wired Headphones with Microphone Specifications Input Impedance: 32ohm Sensitivity (Headphone): 94dBV/Pa +/-3dB or equivalent or better Frequency Response (Headset): 20Hz to 20kHz or equivalent or better USB Port (Type A port or Adapter) Color: Black | 1 lot | 3000 | 31000 | Shopping |  |  | 4
|  | 3 pieces External and Portable Hard Drive for Windows Specifications: Storage: 1TB or equivalent or better Color: Silver/Black |  | 5000 |  |  |  |  | 3
|  | 4 pieces Flashdrive Storage: 64GB or equivalent or better Color: Black |  | 1000 |  |  |  |  | 4
|  | 16 pieces Safety hard hat, adjustable chin strap and forehead cotton lining, white | 1 lot | 900 | 35200 | Shopping |  |  | 16
|  | 16 pieces Mesh safety reflective vest |  | 500 |  |  |  |  | 16
|  | 16 pieces Whistle, plastic |  | 300 |  |  |  |  | 16
|  | 16 pieces Flashlight, 100 lumens, rechargeable LIT battery |  | 500 |  |  |  |  | 16
|  | 10 pieces Universal Adaptor Plug | 10 pieces | 800 | 8300 | Shopping |  |  |  | 1
|  | 5 pieces Universal Outlet Extension Cord Power Cable with individual switches 6 gang | 10 pieces | 750 | [5 empty] | 10
|  | First Aid Box with Medical Supplies | 7 sets | 4500 | 31500 | Small Value Procurement | 15-30 working days | 7
|  | Fire Extinguisher | 2 units | 1500 | 3000 | Shopping |  | 2
|  | All-in-one Printer Specifications: - Print Resolution: Black: up to 1200 x 600 rendered dpi - Print Resolution: Color: up to 4800 x 1200 optimized dpi color - USB, Wireless, Wi-Fi - Copy Speed, Black: 480 pages - Copy Speed, Color: 150 pages - Scan Resolution: up to 1200 dpi - Scan Size Maximum: 216 x 297 mm - Monthly Usage Volume: up to 1000 pages | 2 units | 10000 | 20000 | Shopping |  | 2
|  | 20 pieces Customized Certificate Holder | 1 lot | 500 | 10000 | Shopping |  | 20
|  | 10 boxes Mask | 1 lot | 200 | 32500 | Shopping |  | 10
|  | Paper Towels, interfolded, 2 ply 30 packs/box |  | 2000 |  |  |  | 10
|  | 10 packs Ziplock (Small) |  | 150 |  |  |  | 10
|  | 10 packs Ziplock (Medium) |  | 200 |  |  |  | 10
|  | 10 packs Ziplock (Large) |  | 300 |  |  |  | 10
|  | 10 packs Ziplock (Extra Large) |  | 400 |  |  |  | 10
|  | Office Mesh Chair | 3 lots | 3500 | 10500 | Shopping |  | 3
|  | 18 bottles Isopropyl Alcohol with moisturizer, 70%,500ml | 18 bottles | 280 | 5040 |  |  |  | 18
|  | 3 cans Disinfectant spray, 500 ml | 3 cans | 950 | 2850 |  |  |  | 3
|  | 8 Steel mobile pedestal cabinet | 8 lots | 3500 | 28000 | Shopping |  | 8
|  | White or Acrylic Dry Erase Board (60cm×90cm) | 5 pieces | 650 | 3250 | Shopping |  |  | 5
|  | White Board Marker | 2 boxes | 800 | 1600 | Cash Advance |  |  | 2
(1): 50211990 00; (3): Other Professional Services | 469550 | 600000
|  | Customized Corporate Polo Shirt with Logo Embroidery - Material: Honeycomb - Color: Purple/Violet - Logo Embroidery: BIOMEDTEX Logo, DOST Logo and PTRI Logo - Sizes(S - ?, M - ?, L - ?, XL - ?, XXL - ?) | 15 pieces | 900 | 13500 | Shopping |  | 15
|  | Customized Reversible Corporate Jacket with Detachable Hood Material: Brush twill, Microfiber - with Handloom woven bamboo fabric on lapped zipper - Color: Beige and Dark Navy Blue - Logo Embroidery: BIOMEDTEX Program Logo, DOST Logo, PTRI Logo - Size: M - ? ; L - ? ; XL - ? ; XXL - ? | 15 pieces | 2950 | 50150 | Shopping |  | 17
|  | FESEM Imaging | 25 samples | 8000 | 200000 | Agency to Agency |  |  | 25
|  | Thermogravimetric Analysis | 25 samples | 3500 | 87500 | Agency to Agency |  |  | 25
|  | Differential Scanning Calorimetry | 25 samples | 3000 | 75000 | Agency to Agency |  |  | 25
|  | Breaking Strength and Elongation | 6 samples | 2000 | 12000 | Agency-to-Agency/Negotiated Procurement-Small Value Procurement | per schedule |  |  | 6
|  | Tensile Strength | 6 samples | 1700 | 10200 | Agency-to-Agency/Negotiated Procurement-Small Value Procurement | per schedule |  |  | 6
|  | Authentication Fee Jose Vera Memorial Herbarium of Institute of Biology at University of the Philippines - Diliman | 3 samples | 300 | 10200 | Agency-to-Agency/Negotiated Procurement-Small Value Procurement | per schedule |  |  | 3
|  | Customs Importation Duties and Taxes Collectible - Polylactic Acid from HiSun |  | 11000 | 11000
(1): 50299020 00; (3): Printing and Publication Expenses | 20000 | 20000
|  | Journal Article | 1 unit | 20000 | 20000 | Negotiated Procurement/Shopping |  | 1
50205020 01 |  | Telephone Expenses – Mobile
|  | Mobile Load Card | 26 pc | 150 | 3900 | Shopping |  |  | 13 | 13
50299040 00 |  | Subscription Expenses
|  | Creative Cloud Apps Annual Subscription | 1 license | 4850 | 4850 | Petty Cash Fund / Direct Retail |  |  |  | 1
(1): 50604050 14; (3): Technical & Scientific Equipment - Equipment Outlay | 4875000
|  | Medical Braiding Machine | 1 lot | 3500000 | 3500000 | Public Bidding |  |  | 1
|  | PC Computer with accessories | 3 lots | 125000 | 375000 | Negotiated Procurement/Shopping |  |  | 3
|  | Microscope with imaging software | 1 lot | 1000000 | 1000000 | Public Bidding |  |  |  | 1
TOTAL APPROVED BUDGET: |  |  | 6934580
+ 10% Provision for Inflation |  |  | 693458
+ 10% Contingency |  |  | 693458
TOTAL ESTIMATED BUDGET: |  |  | 8321496
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
JULIUS L. LEAÑO JR., Ph.D. |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: ______________________ |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________