## Q1-Scaffolds
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
END-USER/UNIT: RDD-NFUS
Charged to: Biocompatible Electrospun Nanofiber-based Scaffolds for Drug Delivery and Wound Healing (BioNanoScaffolds)
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Apr | May | Jun | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
50213050 02 |  | Repair and Maintenance – Office Equipment
|  | Repair of FTIR | 1 lot | 25000 | 25000 | Negotiated Procurement-Small Value Procurement |  |  |  | 1
|  | Repair of Split Type Wall Mounted Inverter Airconditioner | 4 lot | 8000 | 32000 | Negotiated Procurement-Small Value Procurement |  | 2 |  | 2
|  | Preventive Maintenance of Split Type Wall Mounted Inverter Airconditioner | 2 unit | 8000 | 16000 | Negotiated ProcurementSmall Value Procurement |  | 1 |  | 1
50203010 02 |  | Office Supplies Expenses
|  | 100 pieces Kraft expanding envelope with elastic band, legal size | 1 lot | 80 | 79000 | Shopping |  |  | 100
|  | 10 pieces Metal file organizer rack, 3-layer |  | 850 |  |  |  |  | 10
|  | 10 pieces Stand file organizer box, blue |  | 450 |  |  |  |  | 10
| OS-122 | 100 pieces Sign Pen, blue, liquid/gel ink, 0.5mm tip |  | 80 |  |  |  |  | 100
| OS-182 | 25 reams Paper, Multi-purpose, A4 size, 70gsm |  | 300 |  |  |  |  | 25
| OS-183 | 25 reams Paper, Multi-purpose, Legal size, 70gsm |  | 350 |  |  |  |  | 25
| OS-074 | 25 reams Paper, Pink, A4 size, 70gsm |  | 500 |  |  |  |  | 5
|  | 10 books Record Book, 300 pages, size: 214mm x 278mm (min) |  | 350 |  |  |  |  | 10
|  | 100 pieces 4 trolley 6-drawers Multi-purpose Storage Organizer Trolley |  | 6000 |  |  |  |  | 4
|  | 10 pieces Standard Scissors |  | 50 |  |  |  |  | 10
| OS-217 | 5 pieces Tailor Scissors |  | 150 |  |  |  |  | 5
|  | 5 pieces Sewing Scissors |  | 180 |  |  |  |  | 5
|  | 20 pieces Glue stick |  | 80 |  |  |  |  | 20
|  | 4 pieces Presentation Clicker | 1 lot | 9000 | 111000 | Shopping |  |  |  | 4
|  | 6 boxes Wireless HDMI Transmitter and Reciever |  | 2500 | [5 empty] | 6
|  | 20 pieces Ink Toner 001 Black |  | 750 | [5 empty] | 20
|  | 20 pieces Ink Toner 001 Magenta |  | 750 | [5 empty] | 20
|  | 20 pieces Ink Toner 001 Cyan |  | 750 | [5 empty] | 20
|  | 20 pieces Ink Toner 001 Yellow |  | 750 | [5 empty] | 20
50203080 00 |  | Medical, Dental Laboratory Supplies Expenses
| MDL-080 | 2 bottles Absolute Ethanol, CAS No. 64-17-5, AR Grade, ≥98.5%, 2.5L | 1 lot | 3750 | 145600 | Negotiated Procurement-Small Value Procurement |  |  | 2
|  | 1 bottle Aluminum Oxide Pellets, 3mm, CAS No. 1344-28-1, 95%, 250g |  | 11900 |  |  |  |  | 1
|  | 1 bottle Barium Chloride Dihydrate,10361-37-2, ≥99%, 1kg |  | 8500 |  |  |  |  | 1
|  | 1 bottle Barium Sulfate, CAS No. 7727-43-7, ≥99%, 1kg |  | 20000 |  |  |  |  | 1
|  | 1 bottle Chitosan, CAS No.9012-76-4, ≥75% deacetylation, 250g |  | 40000 |  |  |  |  | 1
|  | 5 bottles Curcumin, CAS No. 458-37-7, ≥ 95%, 10g |  | 4740 |  |  |  |  | 5
|  | 1 bottle Cyrene, CAS No. 53716-82-8, AR Grade, ≥ 98.5%, 100mL |  | 14000 |  |  |  |  | 1
|  | 1 bottle Dimethylformamide, CAS No. 68-12-2, AR Grade, ≥99.8%, 2.5L |  | 10000 |  |  |  |  | 1
|  | 1 bottle Dimethylsulfoxide, CAS No. 67-68-5, AR Grade, ≥99.9%, 2.5L |  | 10000 |  |  |  |  | 1
|  | 1 bottle Ethyl Acetate, CAS No.141-78-6, AR Grade, ≥99.8%, 2.5L | 1 lot | 10000 | 139425 | Negotiated Procurement-Small Value Procurement |  |  | 1
|  | 1 bottle Europium (III) Oxide, CAS No.1308-96-9, ≥ 99.5%, 25g |  | 43200 |  |  |  |  | 1
|  | 1 bottle Fluorescein Sodium Salt,518-47-8, ≥95%, 50g |  | 10000 |  |  |  |  | 1
|  | 1 bottle Hexane, CAS No. 110-54-3, AR Grade, ≥98.5%, 4L |  | 5325 |  |  |  |  | 1
|  | 1 bottle I-Carrageenan, CAS No. 9062-07-1, Commercial Grade, 100g |  | 6000 |  |  |  |  | 1
|  | 2 bottles Lithium Carbonate, CAS No. 554-13-2, ≥99.99%,50g |  | 23000 |  |  |  |  | 2
|  | 1 bottle PDDA, CAS No. 26062-79-3, Mw 200,000-350,000, 1kg |  | 4500 |  |  |  |  | 1
|  | 2 bottles Poly (4-stryneresulfonic acid), 100g |  | 7200 |  |  |  |  | 2
|  | 4 bottles Quinine Sulfate, CAS No.207671-44-1, ≥99%, 25g | 1 lot | 9000 | 164180 | Negotiated Procurement-Small Value Procurement |  |  | 4
|  | 4 bottles Silicon Dioxide, CAS No. 60676-86-0, ≥ 99.9%,25g |  | 7800 |  |  |  |  | 4
|  | 1 bottle Terbium (III, IV) Oxide, CAS No. 12037-01-3, 99.9% trace metals basis, 10g |  | 45480 |  |  |  |  | 1
|  | 2 bottles Urea, CAS No.57-13-6, ACS Grade, ≥95%, 500g |  | 4000 |  |  |  |  | 2
|  | 1 bottle Zinc Chloride, CAS No. 7646-85-7, ≥97%, 1kg |  | 16500 |  |  |  |  | 1
|  | 1 bottle λ-Carrageenan, CAS No. 9064-57-7, ≥90%, 25g, 50g |  | 27000 |  |  |  |  | 1
| MDL-178 | 2 bottles Glacial Acetic Acid, CAS No. 64-19-7, AR Grade, ≥99.8%, 2.5L | 1 lot | 3750 | 96200 | Negotiated Procurement-Small Value Procurement |  |  | 2
|  | 10 carbouys Sodium Hydroxide, 48% Purity, Technical Grade, 30kg |  | 2500 |  |  |  |  | 10
|  | 1 bottle Sodium Lauryl Sulfate, CAS No. 151-21-3, ≥95%, 500g |  | 7200 |  |  |  |  | 1
|  | 1 bottle Sodium Phosphate Dibasic, CAS No. 7558-79-4, 1kg |  | 21000 |  |  |  |  | 1
|  | 1 bottle Sodium Selenite, CAS No. 10102-18-8, 100 g |  | 20000 |  |  |  |  | 1
|  | 1 bottle Sodium Sulfate, CAS No. 7757-82-6, ≥99%, 1 kg |  | 9500 |  |  |  |  | 1
| MDL-228 | 20 bottles Glacial Acetic Acid, Technical Grade, 1 Liter |  | 300 |  |  |  |  | 20
|  | Agate Mortar and Pestle | 1 unit | 49000 | 49000 | Shopping |  |  | 1
50203990 00 |  | Other Supplies Expenses
|  | Banana Fibers | 17.25 kg | 400 | 6900 | Negotiated Procurement/Shopping |  |  | 17.25
|  | Ginned Cotton Fibers | 300 kg | 300 | 90000 | Negotiated Procurement-Small Value Procurement |  |  |  | 300
|  | 13 pieces Safety hard hat, adjustable chin strap and forehead cotton lining, white | 1 lot | 1500 | 40300 | Shopping |  |  | 13
|  | 13 pieces Mesh safety reflective vest |  | 800 |  |  |  |  | 13
|  | 13 pieces Whistle, plastic |  | 300 |  |  |  |  | 13
|  | 13 pieces Flashlight, 100 lumens, rechargeable LIT battery |  | 500 |  |  |  |  | 13
|  | 10 pieces Universal Adaptor Plug | 1 lot | 1000 | 40000 | Shopping |  |  |  | 10
|  | 5 pieces Universal Outlet Extension Cord Power Cable 10 Gang |  | 3000 | [5 empty] | 5
|  | 5 pieces Universal Extension Wheel Cord Power , 10 or 15 meters |  | 3000 | [5 empty] | 5
|  | 1 set Flash Speed Light | 1 lot | 8000 | 11000 | Shopping |  |  |  | 1
|  | 1 set Camera Battery |  | 3000 | [5 empty] | 1
|  | 2 units Lavatory Faucet | 1 lot | 7000 | 18000 | Shopping |  |  | 2
|  | 2 units Wash Basin Connection Pipe |  | 2000 |  | Shopping |  |  | 2
50203010 01 |  | Supplies and Materials Expenses ( Indirect Cost) (FAD-BTS)
|  | 20 Reams Paper, Multi-purpose, Legal, 70 gsm | 1 lot | 300 | 26000 | Shopping |  |  | 20
|  | 40 Reams Paper, Multi-purpose, A4, 70 gsm |  | 300 |  |  |  |  | 40
|  | 2 packs White folder, legal size |  | 1000 |  |  |  |  | 2
|  | 3 packs White folder, A4 |  | 1000 |  |  |  |  | 3
|  | 10 pads Note pad, stick on, yellow, (2"x3") min |  | 100 |  |  |  |  | 10
|  | 10 pads Note pad, stick on, green, (1.5"x2") min |  | 100 |  |  |  |  | 10
|  | 10 pads Note pad, stick on, pink, (3"x3") min |  | 100 |  |  |  |  | 10
50211990 00 |  | Other Professional Services
|  | Weaving Services | 1 lot | 2500 | 2500 | Negotiated Procurement-Small Value Procurement/Cash Advance |  | 1
|  | Cultural Performance (PHWC) | 1 lot | 40000 | 40000 | Negotiated Procurement-Small Value Procurement/Cash Advance
50299020 00 |  | Printing and Publication Expenses
|  | Journal Article | 1 unit | 41443.4 | 41443.4 | Negotiated Procurement/Shopping |  | 1
50205020 01 |  | Telephone Expenses – Mobile
|  | Mobile Load Card | 26 pc | 150 | 3900 | Shopping |  |  | 13 | 13
50299040 00 |  | Transportation and Delivery Expense
|  | Bus Rental for Weavers and Digitalization Staff (PHWC) | 1 lot | 70000 | 70000 | Shopping |  |  | 1
|  | Trucking Services (PHWC) | 1 lot | 30000 | 30000 | Shopping |  |  | 1
50299040 00 |  | Subscription Expenses
|  | Creative Cloud Apps Annual Subscription | 1 license | 4850 | 4850 | Petty Cash Fund / Direct Retail |  |  |  | 1
50604050 14 |  | Technical & Scientific Equipment - Equipment Outlay
|  | Automated Electrospinning Machine | 1 lot | 4000000 | 4000000 | Public Bidding |  |  | 1
|  | Laptop | 2 lots | 120000 | 240000 | Negotiated Procurement/Shopping |  |  | 2
|  | Biosafety cabinet | 1 lot | 1500000 | 1500000 | Public Bidding |  |  |  | 1
TOTAL APPROVED BUDGET: |  |  | 5282298.4
+ 10% Provision for Inflation |  |  | 528229.84
+ 10% Contingency |  |  | 528229.84
TOTAL ESTIMATED BUDGET: |  |  | 6338758.08
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
JULIUS L. LEAÑO JR., Ph.D. |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: ______________________ |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________

## Q2 - Scaffolds
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
END-USER/UNIT: RDD-NFUS
Charged to: Biocompatible Electrospun Nanofiber-based Scaffolds for Drug Delivery and Wound Healing (BioNanoScaffolds)
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Apr | May | Jun | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
(1): 50203010 02; (3): Office Supplies Expenses | 197250 | 200000
|  | 50 pieces Kraft expanding envelope with elastic band, legal size | 1 lot | 80 | 4000 | Small Value Procurement | 15-30 working days |  | 50 | 50
|  | 5 pieces Metal file organizer rack, 3-layer |  | 850 | 4250 | Small Value Procurement |  |  | 5 | 5
|  | 5 pieces Stand file organizer box, blue |  | 450 | 2250 | Small Value Procurement |  |  | 5 | 5
|  | 50 pieces Sign Pen, blue, liquid/gel ink, 0.5mm tip |  | 80 | 4000 | Small Value Procurement |  |  | 50 | 50
|  | 15 reams Paper, Multi-purpose, A4 size, 70gsm |  | 300 | 4500 | Small Value Procurement |  |  | 15 | 15
|  | 15 reams Paper, Multi-purpose, Legal size, 70gsm |  | 350 | 5250 | Small Value Procurement |  |  | 15 | 15
|  | 15 reams Paper, Pink, A4 size, 70gsm |  | 500 | 7500 | Small Value Procurement |  |  | 15 | 15
|  | 8 books Record Book, 300 pages, size: 214mm x 278mm (min) |  | 350 | 2800 | Small Value Procurement |  |  | 8 | 8
|  | 4 trolley 6-drawers Multi-purpose Storage Organizer Trolley |  | 2000 | 6000 | Small Value Procurement |  |  | 3 | 3
|  | 8 pieces Standard Scissors |  | 50 | 400 | Small Value Procurement |  |  | 8 | 8
|  | 8 pieces Glue stick |  | 80 | 640 | Small Value Procurement |  |  | 8 | 8
|  | White or Acrylic Dry Erase Board (60cm×90cm) | 4 pieces | 650 | 2600 | Small Value Procurement |  |  | 4 | 4
|  | White Board Marker | 2 boxes | 800 | 1600 | Cash Advance |  |  | 2 | 2
|  | 4 Office Partition | 1 lot | 28000 | 112000 | Negotiated Procurement-Small Value Procurement |  | 4 |  | 4
|  | 4 Office Mesh Chair |  | 3500 | 14000 | Negotiated Procurement-Small Value Procurement |  | 4 |  | 4
|  | 16 pcs Notebook, steno, ≥60 leaves | 16 pieces | 60 | 960 | Shopping |  | 16 |  | 16
|  | 7 Steel mobile pedestal cabinet | 1 lot | 3500 | 24500 | Shopping |  | 7 |  | 7
(1): 50203080 00; (3): Medical, Dental Laboratory Supplies Expenses | 551550 | 1050000
|  | Hot Plate with Magnetic Stirring Specifications: 280 mm x 280 mm or equivalent or better 200 - 1500 C temperature range, 1 increment or equivalent or better 100 - 1500 rpm speed or equivalent or better Ceramic Plate | 2 units | 40000 | 80000 | Negotiated Procurement-Small Value Procurement | 30-45 working days | 2 |  | 2
|  | Tabletop Desiccator, 210mm diameter or equivalent or better | 3 lots | 5000 | 15000 | Shopping | 30-45 working days |  | 3 | 3
|  | 5 packs PH Indicator Strip, 0-14 100's per pack | 5 packs | 2500 | 12500 | Shopping | 30-45 working days |  | 5 | 5
|  | 25 carboys Sodium Hydroxide (NaOH), Concentration: 48% or equivalent or better Volume: 40 L/carboy | 1 lot | 3500 | 125000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 25 |  | 25
|  | 15 bottles Sodium Hydroxide (NaOH), Micropearls Pellets |  | 2500 |  |  | 30-45 working days | 15 |  | 15
|  | 5 carboys Acetic Acid (CH3COOH), Concentration: 99.85% or equivalent or better Volume: 40 L/carboy | 5 carboys | 5000 | 25000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 5 |  | 5
|  | 3 bottles Acetic Acid (CH3COOH), Concentration: ≥99% or equivalent or better Volume: 2.5 L Analytical Reagent (AR) | 3 bottles | 3000 | 9000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 3 |  | 3
|  | 3 bottles Sodium Sulphite (Na2SO3), Anhydrous ≥99% or equivalent or better Analytical Reagent (AR) 500 g per bottle | 1 lot | 3000 | 89000 | Negotiated Procurement-Small Value Procurement | 30-45 working days | 3 |  | 3
|  | 5 bottles Cleanmate (Liquid Detergent), 1 gallon |  | 1000 |  |  |  | 5 |  | 5
|  | 5 gallons Sodium Silicate, Neutral Solution, pure |  | 2500 |  |  |  | 5 |  | 5
|  | 5 carboys Hydrogen Peroxide (H2O2), 50% or equivalent or better, Volume: 30 kg |  | 5000 |  |  |  | 5 |  | 5
|  | 5 bottles Sulfuric Acid (H2SO4), ≥98%≥98% Analytical Reagent (AR) Volume: 2.5 L/bottle |  | 2500 |  |  |  | 5 |  | 5
|  | 5 bottles Sodium Metabisulfite, Technical Grade 97% or equivalent or better, 1kg per bottle |  | 5000 |  |  |  | 5 |  | 5
|  | 5 bottles Sodium Hypochlorite, Zonrox, 1L per bottle | 5 bottles | 60 | 300 | Shopping | 30-45 working days | 5 |  | 5
|  | 8 pairs Heat Resistant and Slide Resistant Gloves | 8 pairs | 1000 | 8000 | Shopping | 30-45 working days |  | 8 | 8
|  | 8 pieces Rectangular High-Density Polyethylene (HDPE) with handle Laboratory Basket | 8 pieces | 1000 | 8000 | Shopping | 30-45 working days |  | 8 | 8
|  | 10 pieces Magnetic Stirrer (Spin Bar) | 1 lot | 1000 | 16000 | Shopping | 30-45 working days |  |  | 10
|  | 3 pieces Magnetic Stirrer Stick |  | 2000 | [5 empty] | 3
|  | 10 boxes Nitrile Gloves (Medium) | 1 lot | 300 | 8000 | Shopping | 30-45 working days |  | 10 | 10
|  | 10 boxes Nitrile Gloves (Large) |  | 300 |  |  |  |  | 10 | 10
|  | 6 pieces Labgown (Medium) |  | 500 |  |  |  |  | 2 | 2
|  | 6 pieces Labgown (Large) |  | 500 |  |  |  |  | 2 | 2
|  | 20 pieces Beakers, borosilicate glass, 2L | 1 lot | 1300 | 155750 | Negotiated Procurement-Small Value Procurement | 30-45 working days |  | 20 | 20
|  | 15 pieces Beakers, borosilicate glass, 1L |  | 800 |  |  |  |  | 15 | 15
|  | 15 pieces Beakers, borosilicate glass, 500 mL |  | 250 |  |  |  |  | 15 | 15
|  | 10 pieces Graduated cylinder, borosilicate glass, 1L |  | 2400 |  |  |  |  | 10 | 10
|  | 10 pieces Graduated cylinder, borosilicate glass, 500 mL |  | 2000 |  |  |  |  | 10 | 10
|  | 10 pieces Graduated cylinder, borosilicate glass, 100 mL |  | 1000 |  |  |  |  | 10 | 10
|  | 24 pieces Gooch Glass Filter |  | 2500 |  |  |  |  | 24 | 24
(1): 50203990 00; (3): Other Supplies Expenses | 137775 | 150000
|  | 4 pieces Wired Headphones with Microphone Specifications Input Impedance: 32ohm Sensitivity (Headphone): 94dBV/Pa +/-3dB or equivalent or better Frequency Response (Headset): 20Hz to 20kHz or equivalent or better USB Port (Type A port or Adapter) Color: Black | 1 lot | 3000 | 36000 | Shopping | 15-30 working days |  | 4 | 4
|  | 4 pieces External and Portable Hard Drive for Windows Specifications: Storage: 1TB or equivalent or better Color: Silver/Black |  | 5000 |  |  |  |  | 4 | 4
|  | 4 pieces Flashdrive Storage: 64GB or equivalent or better Color: Black |  | 1000 |  |  |  |  | 4 | 4
|  | 8 pieces Universal Adaptor Plug | 1 lot | 1000 | 38000 | Shopping | 15-30 working days |  |  | 8
|  | 5 pieces Universal Outlet Extension Cord Power Cable 10 Gang |  | 3000 |  |  | 15-30 working days |  |  | 5
|  | 5 pieces Universal Extension Wheel Cord Power , 10 or 15 meters |  | 3000 |  |  | 15-30 working days |  |  | 5
|  | First Aid Box with Medical Supplies | 2 sets | 4500 | 9000 | Small Value Procurement | 15-30 working days | 2 |  | 2
|  | Fire Extinguisher | 1 unit | 3000 | 3000 | Shopping | 15-30 working days | 1 |  | 1
|  | 10 boxes Mask | 1 lot | 200 | 18000 | Shopping | 15-30 working days | 10 |  | 10
|  | 10 packs Facial Tissue |  | 200 |  |  |  | 10 |  | 10
|  | 10 packs Rolled Tissue |  | 200 |  |  |  | 10 |  | 10
|  | 10 packs Ziplock (Small) |  | 200 |  |  |  | 10 |  | 10
|  | 10 packs Ziplock (Medium) |  | 250 |  |  |  | 10 |  | 10
|  | 10 packs Ziplock (Large) |  | 350 |  |  |  | 10 |  | 10
|  | 10 packs Ziplock (Extra Large) |  | 400 |  |  |  | 10 |  | 10
|  | 25 boxes Binder Clips, 41mm | 1 lot | 125 | 6875 | Shopping | 15-30 working days | 25 |  | 25
|  | 25 boxes Binder Clips, 19mm |  | 75 |  |  |  | 25 |  | 25
|  | 25 boxes Binder Clips, 25mm |  | 75 |  |  |  | 25 |  | 25
|  | 10 packs Binder Clip 4 per pack black | 1 lot | 25 | 600 | Shopping | 15-30 working days | 10 |  | 10
|  | 10 packs Binder clip 2 per pack black |  | 20 |  |  |  | 10 |  | 10
|  | 5 packs Paper clip vinyl coated assorted 100s |  | 30 |  |  |  | 5 |  | 5
|  | 3 pieces Stapler | 3 pieces | 100 | 300 |  | 15-30 working days |  |  | 3
|  | Lateral Steel Office Cabinet | 2 pieces | 13000 | 26000 | Shopping | 15-30 working days |  |  | 2
50203010 01 |  | Supplies and Materials Expenses ( Indirect Cost) (FAD-BTS)
|  | 20 Reams Paper, Multi-purpose, Legal, 70 gsm | 1 lot | 300 | 26000 | Shopping |  |  |  | 20
|  | 40 Reams Paper, Multi-purpose, A4, 70 gsm |  | 300 | [5 empty] | 40
|  | 2 packs White folder, legal size |  | 1000 | [5 empty] | 2
|  | 3 packs White folder, A4 |  | 1000 | [5 empty] | 3
|  | 10 pads Note pad, stick on, yellow, (2"x3") min |  | 100 | [5 empty] | 10
|  | 10 pads Note pad, stick on, green, (1.5"x2") min |  | 100 | [5 empty] | 10
|  | 10 pads Note pad, stick on, pink, (3"x3") min |  | 100 | [5 empty] | 10
50205020 01 |  | Telephone Expenses – Mobile
|  | Mobile Load Card | 26 pc | 150 | 3900 | Shopping | 15-30 working days |  | 13 | 26
(1): 50604050 14; (3): Technical & Scientific Equipment - Equipment Outlay | 6740000
|  | Automated Electrospinning Machine | 1 lot | 5000000 | 5000000 | Public Bidding | 60-90 working days |  | 1 | 1
|  | Laptop | 2 lots | 120000 | 240000 | Negotiated Procurement/Shopping | 60-90 working days |  | 2 | 2
|  | Biosafety cabinet | 1 lot | 1500000 | 1500000 | Public Bidding | 60-90 working days |  |  | 1
TOTAL APPROVED BUDGET: |  |  | 7656475
+ 10% Provision for Inflation |  |  | 765647.5
+ 10% Contingency |  |  | 765647.5
TOTAL ESTIMATED BUDGET: |  |  | 9187770
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
JULIUS L. LEAÑO JR., Ph.D. |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: ______________________ |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________

## Q3 Draft - Scaffolds
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 3rd Quarter of CY 2024
END-USER/UNIT: RDD-NFUS
Charged to: Biocompatible Electrospun Nanofiber-based Scaffolds for Drug Delivery and Wound Healing (BioNanoScaffolds)
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Jul | Aug | Sep | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
(1): 50203010 02; (3): Office Supplies Expenses | 197250 | 200000
|  | 50 pieces Kraft expanding envelope with elastic band, legal size | 1 lot | 80 | 4000 | Small Value Procurement | 15-30 working days | 50 | 50
|  | 5 pieces Metal file organizer rack, 3-layer |  | 850 | 4250 | Small Value Procurement |  | 5 | 5
|  | 5 pieces Stand file organizer box, blue |  | 450 | 2250 | Small Value Procurement |  | 5 | 5
|  | 50 pieces Sign Pen, blue, liquid/gel ink, 0.5mm tip |  | 80 | 4000 | Small Value Procurement |  | 50 | 50
|  | 15 reams Paper, Multi-purpose, A4 size, 70gsm |  | 300 | 4500 | Small Value Procurement |  | 15 | 15
|  | 15 reams Paper, Multi-purpose, Legal size, 70gsm |  | 350 | 5250 | Small Value Procurement |  | 15 | 15
|  | 15 reams Paper, Pink, A4 size, 70gsm |  | 500 | 7500 | Small Value Procurement |  | 15 | 15
|  | 8 books Record Book, 300 pages, size: 214mm x 278mm (min) |  | 350 | 2800 | Small Value Procurement |  | 8 | 8
|  | 4 trolley 6-drawers Multi-purpose Storage Organizer Trolley |  | 2000 | 6000 | Small Value Procurement |  | 3 | 3
|  | 8 pieces Standard Scissors |  | 50 | 400 | Small Value Procurement |  | 8 | 8
|  | 8 pieces Glue stick |  | 80 | 640 | Small Value Procurement |  | 8 | 8
|  | White or Acrylic Dry Erase Board (60cm×90cm) | 4 pieces | 650 | 2600 | Small Value Procurement |  | 4 | 4
|  | White Board Marker | 2 boxes | 800 | 1600 | Cash Advance |  | 2 | 2
|  | 4 Office Partition | 1 lot | 28000 | 112000 | Negotiated Procurement-Small Value Procurement |  | 4
|  | 4 Office Mesh Chair |  | 3500 | 14000 | Negotiated Procurement-Small Value Procurement |  | 4
|  | 16 pcs Notebook, steno, ≥60 leaves | 16 pieces | 60 | 960 | Shopping |  | 16
|  | 7 Steel mobile pedestal cabinet | 1 lot | 3500 | 24500 | Shopping |  | 7
(1): 50203080 00; (3): Medical, Dental Laboratory Supplies Expenses | 555550 | 1050000
|  | Hot Plate with Magnetic Stirring Specifications: 280 mm x 280 mm or equivalent or better 200 - 1500 C temperature range, 1 increment or equivalent or better 100 - 1500 rpm speed or equivalent or better Ceramic Plate | 2 units | 40000 | 80000 | Negotiated Procurement-Small Value Procurement | 30-45 working days | 2
|  | Tabletop Desiccator, 210mm diameter or equivalent or better | 3 lots | 5000 | 15000 | Shopping | 30-45 working days | 3 | 3
|  | 5 packs PH Indicator Strip, 0-14 100's per pack | 5 packs | 2500 | 12500 | Shopping | 30-45 working days | 5 | 5
|  | 25 carboys Sodium Hydroxide (NaOH), Concentration: 48% or equivalent or better Volume: 40 L/carboy | 1 lot | 3500 | 87500 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 25
|  | 15 bottles Sodium Hydroxide (NaOH), Micropearls Pellets |  | 2500 | 37500 |  | 30-45 working days | 15
|  | 5 carboys Acetic Acid (CH3COOH), Concentration: 99.85% or equivalent or better Volume: 40 L/carboy | 5 carboys | 5000 | 25000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 5
|  | 3 bottles Acetic Acid (CH3COOH), Concentration: ≥99% or equivalent or better Volume: 2.5 L Analytical Reagent (AR) | 3 bottles | 3000 | 9000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 3
|  | 3 bottles Sodium Sulphite (Na2SO3), Anhydrous ≥99% or equivalent or better Analytical Reagent (AR) 500 g per bottle | 1 lot | 3000 | 9000 | Negotiated Procurement-Small Value Procurement | 30-45 working days | 3
|  | 5 bottles Cleanmate (Liquid Detergent), 1 gallon |  | 1000 | 5000 |  |  | 5
|  | 5 gallons Sodium Silicate, Neutral Solution, pure |  | 2500 | 12500 |  |  | 5
|  | 5 carboys Hydrogen Peroxide (H2O2), 50% or equivalent or better, Volume: 30 kg |  | 5000 | 25000 |  |  | 5
|  | 5 bottles Sulfuric Acid (H2SO4), ≥98%≥98% Analytical Reagent (AR) Volume: 2.5 L/bottle |  | 2500 | 12500 |  |  | 5
|  | 5 bottles Sodium Metabisulfite, Technical Grade 97% or equivalent or better, 1kg per bottle |  | 5000 | 25000 |  |  | 5
|  | 5 bottles Sodium Hypochlorite, Zonrox, 1L per bottle | 5 bottles | 60 | 300 | Shopping | 30-45 working days | 5
|  | 8 pairs Heat Resistant and Slide Resistant Gloves | 8 pairs | 1000 | 8000 | Shopping | 30-45 working days | 8 | 8
|  | 8 pieces Rectangular High-Density Polyethylene (HDPE) with handle Laboratory Basket | 8 pieces | 1000 | 8000 | Shopping | 30-45 working days | 8 | 8
|  | 10 pieces Magnetic Stirrer (Spin Bar) | 1 lot | 1000 | 10000 | Shopping | 30-45 working days | 10
|  | 3 pieces Magnetic Stirrer Stick |  | 2000 | 6000 |  |  | 3
|  | 10 boxes Nitrile Gloves (Medium) | 1 lot | 300 | 3000 | Shopping | 30-45 working days | 10 | 10
|  | 10 boxes Nitrile Gloves (Large) |  | 300 | 3000 |  |  | 10 | 10
|  | 6 pieces Labgown (Medium) |  | 500 | 3000 |  |  | 6 | 2
|  | 6 pieces Labgown (Large) |  | 500 | 3000 |  |  | 6 | 2
|  | 20 pieces Beakers, borosilicate glass, 2L | 1 lot | 1300 | 26000 | Negotiated Procurement-Small Value Procurement | 30-45 working days | 20 | 20
|  | 15 pieces Beakers, borosilicate glass, 1L |  | 800 | 12000 |  |  | 15 | 15
|  | 15 pieces Beakers, borosilicate glass, 500 mL |  | 250 | 3750 |  |  | 15 | 15
|  | 10 pieces Graduated cylinder, borosilicate glass, 1L |  | 2400 | 24000 |  |  | 10 | 10
|  | 10 pieces Graduated cylinder, borosilicate glass, 500 mL |  | 2000 | 20000 |  |  | 10 | 10
|  | 10 pieces Graduated cylinder, borosilicate glass, 100 mL |  | 1000 | 10000 |  |  | 10 | 10
|  | 24 pieces Gooch Glass Filter |  | 2500 | 60000 |  |  | 24 | 24
(1): 50203990 00; (3): Other Supplies Expenses | 137775 | 150000
|  | 4 pieces Wired Headphones with Microphone Specifications Input Impedance: 32ohm Sensitivity (Headphone): 94dBV/Pa +/-3dB or equivalent or better Frequency Response (Headset): 20Hz to 20kHz or equivalent or better USB Port (Type A port or Adapter) Color: Black | 1 lot | 3000 | 36000 | Shopping | 15-30 working days | 4 | 4
|  | 4 pieces External and Portable Hard Drive for Windows Specifications: Storage: 1TB or equivalent or better Color: Silver/Black |  | 5000 |  |  |  | 4 | 4
|  | 4 pieces Flashdrive Storage: 64GB or equivalent or better Color: Black |  | 1000 |  |  |  | 4 | 4
|  | 8 pieces Universal Adaptor Plug | 1 lot | 1000 | 38000 | Shopping | 15-30 working days | 8
|  | 5 pieces Universal Outlet Extension Cord Power Cable 10 Gang |  | 3000 |  |  | 15-30 working days | 5
|  | 5 pieces Universal Extension Wheel Cord Power , 10 or 15 meters |  | 3000 |  |  | 15-30 working days | 5
|  | First Aid Box with Medical Supplies | 2 sets | 4500 | 9000 | Small Value Procurement | 15-30 working days | 2
|  | Fire Extinguisher | 1 unit | 3000 | 3000 | Shopping | 15-30 working days | 1
|  | 10 boxes Mask | 1 lot | 200 | 18000 | Shopping | 15-30 working days | 10
|  | 10 packs Facial Tissue |  | 200 |  |  |  | 10
|  | 10 packs Rolled Tissue |  | 200 |  |  |  | 10
|  | 10 packs Ziplock (Small) |  | 200 |  |  |  | 10
|  | 10 packs Ziplock (Medium) |  | 250 |  |  |  | 10
|  | 10 packs Ziplock (Large) |  | 350 |  |  |  | 10
|  | 10 packs Ziplock (Extra Large) |  | 400 |  |  |  | 10
|  | 25 boxes Binder Clips, 41mm | 1 lot | 125 | 6875 | Shopping | 15-30 working days | 25
|  | 25 boxes Binder Clips, 19mm |  | 75 |  |  |  | 25
|  | 25 boxes Binder Clips, 25mm |  | 75 |  |  |  | 25
|  | 10 packs Binder Clip 4 per pack black | 1 lot | 25 | 600 | Shopping | 15-30 working days | 10
|  | 10 packs Binder clip 2 per pack black |  | 20 |  |  |  | 10
|  | 5 packs Paper clip vinyl coated assorted 100s |  | 30 |  |  |  | 5
|  | 3 pieces Stapler | 3 pieces | 100 | 300 |  | 15-30 working days | 3
|  | Lateral Steel Office Cabinet | 2 pieces | 13000 | 26000 | Shopping | 15-30 working days | 2
50203010 01 |  | Supplies and Materials Expenses ( Indirect Cost) (FAD-BTS)
|  | 20 Reams Paper, Multi-purpose, Legal, 70 gsm | 1 lot | 300 | 26000 | Shopping |  |  |  | 20
|  | 40 Reams Paper, Multi-purpose, A4, 70 gsm |  | 300 | [5 empty] | 40
|  | 2 packs White folder, legal size |  | 1000 | [5 empty] | 2
|  | 3 packs White folder, A4 |  | 1000 | [5 empty] | 3
|  | 10 pads Note pad, stick on, yellow, (2"x3") min |  | 100 | [5 empty] | 10
|  | 10 pads Note pad, stick on, green, (1.5"x2") min |  | 100 | [5 empty] | 10
|  | 10 pads Note pad, stick on, pink, (3"x3") min |  | 100 | [5 empty] | 10
50205020 01 |  | Telephone Expenses – Mobile
|  | Mobile Load Card | 26 pc | 150 | 3900 | Shopping | 15-30 working days |  | 13 | 26
(1): 50604050 14; (3): Technical & Scientific Equipment - Equipment Outlay | 6740000
|  | Automated Electrospinning Machine | 1 lot | 5000000 | 5000000 | Public Bidding | 60-90 working days |  | 1 | 1
|  | Laptop | 2 lots | 120000 | 240000 | Negotiated Procurement/Shopping | 60-90 working days |  | 2 | 2
|  | Biosafety cabinet | 1 lot | 1500000 | 1500000 | Public Bidding | 60-90 working days |  |  | 1
TOTAL APPROVED BUDGET: |  |  | 7660475
+ 10% Provision for Inflation |  |  | 766047.5
+ 10% Contingency |  |  | 766047.5
TOTAL ESTIMATED BUDGET: |  |  | 9192570
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
JULIUS L. LEAÑO JR., Ph.D. |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: ______________________ |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________

## Q3 - Scaffolds
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
END-USER/UNIT: RDD-NFUS
Charged to: Biocompatible Electrospun Nanofiber-based Scaffolds for Drug Delivery and Wound Healing (BioNanoScaffolds)
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Jun | Jul | Aug | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
50213050 02 |  | Repair and Maintenance – Office Equipment
(1): 50203010 02; (3): Office Supplies Expenses | 198750 | 200000
|  | 50 pieces Kraft expanding envelope with elastic band, legal size | 50 pieces | 80 | 41590 | Shopping |  |  | 50
|  | 5 pieces Metal file organizer rack, 3-layer | 5 pieces | 850 |  |  |  |  | 5
|  | 5 pieces Stand file organizer box, blue | 5 pieces | 450 |  |  |  |  | 5
|  | 50 pieces Sign Pen, blue, liquid/gel ink, 0.5mm tip | 50 pieces | 80 |  |  |  |  | 50
|  | 15 reams Paper, Multi-purpose, A4 size, 70gsm | 15 reams | 300 |  |  |  |  | 15
|  | 15 reams Paper, Multi-purpose, Legal size, 70gsm | 15 reams | 350 |  |  |  |  | 15
|  | 15 reams Paper, Pink, A4 size, 70gsm | 15 reams | 500 |  |  |  |  | 15
|  | 8 books Record Book, 300 pages, size: 214mm x 278mm (min) | 8 pieces | 350 |  |  |  |  | 8
|  | 4 trolley 6-drawers Multi-purpose Storage Organizer Trolley | 3 units | 2000 |  |  |  |  | 3
|  | 8 pieces Standard Scissors | 8 pieces | 50 |  |  |  |  | 8
|  | 8 pieces Glue stick | 8 pieces | 80 |  |  |  |  | 8
|  | 2 pieces Presentation Clicker | 2 pieces | 9000 | 25500 | Shopping |  |  |  | 2
|  | 3 boxes Wireless HDMI Transmitter and Reciever | 3 boxes | 2500 | [5 empty] | 3
|  | White or Acrylic Dry Erase Board (60cm×90cm) | 4 pieces | 650 | 2600 | Shopping |  |  | 4
|  | White Board Marker | 2 boxes | 800 | 1600 | Cash Advance |  |  | 2
|  | Office Partition | 8 lots | 11000 | 88000 | Shopping |  | 8
|  | 16 pcs Notebook, steno, ≥60 leaves | 16 pieces | 60 | 960 | Shopping |  | 16
|  | Office Mesh Chair | 8 lots | 3500 | 28000 | Shopping |  | 8
|  | 3 Steel mobile pedestal cabinet | 3 lots | 3500 | 10500 | Shopping |  | 3
(1): 50203080 00; (3): Medical, Dental Laboratory Supplies Expenses | 623550 | 1650000
|  | Hot Plate with Magnetic Stirring Specifications: 280 mm x 280 mm or equivalent or better 200 - 1500 C temperature range, 1 increment or equivalent or better 100 - 1500 rpm speed or equivalent or better Ceramic Plate | 2 units | 40000 | 80000 | Negotiated Procurement-Small Value Procurement | 30-45 working days | 2
|  | Tabletop Desiccator, 210mm diameter or equivalent or better | 3 lots | 5000 | 15000 | Shopping | 30-45 working days |  | 3
|  | 5 packs PH Indicator Strip, 0-14 100's per pack | 5 packs | 2500 | 12500 | Shopping |  |  | 5
|  | 25 carboys Sodium Hydroxide (NaOH), Concentration: 48% or equivalent or better Volume: 40 L/carboy | 25 carboys | 3500 | 125000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 25
|  | 15 bottles Sodium Hydroxide (NaOH), Micropearls Pellets | 15 bottles | 2500 |  |  |  | 15
|  | 5 carboys Acetic Acid (CH3COOH), Concentration: 99.85% or equivalent or better Volume: 40 L/carboy | 5 carboys | 5000 | 25000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 5
|  | 3 bottles Acetic Acid (CH3COOH), Concentration: ≥99% or equivalent or better Volume: 2.5 L Analytical Reagent (AR) | 3 bottles | 3000 | 9000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 3
|  | 3 bottles Sodium Sulphite (Na2SO3), Anhydrous ≥99% or equivalent or better Analytical Reagent (AR) 500 g per bottle | 3 bottles | 3000 | 89000 | Negotiated Procurement-Small Value Procurement | 60-90 working days | 3
|  | 5 bottles Cleanmate (Liquid Detergent), 1 gallon | 5 bottles | 1000 |  |  |  | 5
|  | 5 gallons Sodium Silicate, Neutral Solution, pure | 5 gallons | 2500 |  |  |  | 5
|  | 5 carboys Hydrogen Peroxide (H2O2), 50% or equivalent or better, Volume: 30 kg | 5 carboys | 5000 |  |  |  | 5
|  | 5 bottles Sulfuric Acid (H2SO4), ≥98%≥98% Analytical Reagent (AR) Volume: 2.5 L/bottle | 5 bottles | 2500 |  |  |  | 5
|  | 5 bottles Sodium Metabisulfite, Technical Grade 97% or equivalent or better, 1kg per bottle | 5 bottles | 5000 |  |  |  | 5
|  | 5 bottles Sodium Hypochlorite, Zonrox, 1L per bottle | 5 bottles | 60 | 300 | Shopping |  | 5
|  | 8 pairs Heat Resistant and Slide Resistant Gloves | 8 pairs | 1000 | 8000 | Shopping |  |  | 8
|  | 8 pieces Rectangular High-Density Polyethylene (HDPE) with handle Laboratory Basket | 8 pieces | 1000 | 8000 | Shopping | 30-45 working days |  | 8
|  | 10 pieces Magnetic Stirrer (Spin Bar) | 10 pieces | 1000 | 16000 | Shopping |  |  |  | 10
|  | 3 pieces Magnetic Stirrer Stick | 3 pieces | 2000 | [5 empty] | 3
|  | 4 sacks PLA (polylactic acid) resin | 4 lots | 12000 | 48000 | Negotiated Procurement-Small Value Procurement | 30-45 working days |  | 4
|  | 10 boxes Nitrile Gloves (Medium) | 10 boxes | 300 | 8000 | Shopping |  |  | 10
|  | 10 boxes Nitrile Gloves (Large) | 10 boxes | 300 |  |  |  |  | 10
|  | 6 pieces Labgown (Medium) | 6 pieces | 500 |  |  |  |  | 2
|  | 6 pieces Labgown (Large) | 6 pieces | 500 |  |  |  |  | 2
|  | 20 pieces Beakers, borosilicate glass, 2L | 20 pieces | 1300 | 155750 | Negotiated Procurement-Small Value Procurement |  |  | 20
|  | 15 pieces Beakers, borosilicate glass, 1L | 15 pieces | 800 |  |  |  |  | 15
|  | 15 pieces Beakers, borosilicate glass, 500 mL | 15 pieces | 250 |  |  |  |  | 15
|  | 10 pieces Graduated cylinder, borosilicate glass, 1L | 10 pieces | 2400 |  |  |  |  | 10
|  | 10 pieces Graduated cylinder, borosilicate glass, 500 mL | 10 pieces | 2000 |  |  |  |  | 10
|  | 10 pieces Graduated cylinder, borosilicate glass, 100 mL | 10 pieces | 1000 |  |  |  |  | 10
|  | 24 pieces Gooch Glass Filter | 24 pieces | 2500 |  |  |  |  | 24
|  | HP 678 Ink Cartridge HPCZ107AA Black (Original) | 20 pieces | 600 | 24000 | Shopping |  |  |  | 20
|  | HP 678 Ink Cartridge HPCZ108AA Colored (Tri-Color) (Original) | 20 pieces | 600 | [5 empty] | 20
(1): 50203990 00; (3): Other Supplies Expenses | 147775 | 150000
|  | 4 pieces Wired Headphones with Microphone Specifications Input Impedance: 32ohm Sensitivity (Headphone): 94dBV/Pa +/-3dB or equivalent or better Frequency Response (Headset): 20Hz to 20kHz or equivalent or better USB Port (Type A port or Adapter) Color: Black | 1 lot | 3000 | 36000 | Shopping |  |  | 4
|  | 4 pieces External and Portable Hard Drive for Windows Specifications: Storage: 1TB or equivalent or better Color: Silver/Black |  | 5000 |  |  |  |  | 4
|  | 4 pieces Flashdrive Storage: 64GB or equivalent or better Color: Black |  | 1000 |  |  |  |  | 4
|  | 8 pieces Universal Adaptor Plug | 1 lot | 1000 | 38000 | Shopping |  |  |  | 8
|  | 5 pieces Universal Outlet Extension Cord Power Cable 10 Gang |  | 3000 | [5 empty] | 5
|  | 5 pieces Universal Extension Wheel Cord Power , 10 or 15 meters |  | 3000 | [5 empty] | 5
|  | First Aid Box with Medical Supplies | 2 sets | 4500 | 9000 | Small Value Procurement | 15-30 working days | 2
|  | Fire Extinguisher | 1 unit | 3000 | 3000 | Shopping |  | 1
|  | 20 pieces Customized Certificate Holder | 1 lot | 500 | 10000 | Shopping |  | 20
|  | 10 boxes Mask | 1 lot | 200 | 18000 | Shopping |  | 10
|  | 10 packs Facial Tissue |  | 200 |  |  |  | 10
|  | 10 packs Rolled Tissue |  | 200 |  |  |  | 10
|  | 10 packs Ziplock (Small) |  | 200 |  |  |  | 10
|  | 10 packs Ziplock (Medium) |  | 250 |  |  |  | 10
|  | 10 packs Ziplock (Large) |  | 350 |  |  |  | 10
|  | 10 packs Ziplock (Extra Large) |  | 400 |  |  |  | 10
|  | 25 boxes Binder Clips, 41mm | 1 lot | 125 | 6875 | Shopping |  | 25
|  | 25 boxes Binder Clips, 19mm |  | 75 |  |  |  | 25
|  | 25 boxes Binder Clips, 25mm |  | 75 |  |  |  | 25
|  | 10 packs Binder Clip 4 per pack black | 1 lot | 25 | 600 | Shopping | 15-30 working days | 10
|  | 10 packs Binder clip 2 per pack black |  | 20 |  |  |  | 10
|  | 5 packs Paper clip vinyl coated assorted 100s |  | 30 |  |  |  | 5
|  | 3 pieces Stapler | 3 pieces | 100 | 300 |  |  |  |  | 3
|  | Lateral Steel Office Cabinet | 2 pieces | 13000 | 26000 | Shopping | 15-30 working days |  |  | 2
(1): 50211990 00; (3): Other Professional Services | 394500 | 846292
|  | Customized Corporate Polo Shirt with Logo Embroidery | 18 pieces | 800 | 32000 | Shopping |  | 18
|  | FESEM Imaging | 25 samples | 8000 | 200000 | Agency to Agency |  |  | 25
(3): Thermogravimetric Analysis; (4): 25 samples; (5): 3500; (6): 87500; (7): Agency to Agency; (10): 25 | 753708 | salary of OPS charged personnel
|  | Differential Scanning Calorimetry | 25 samples | 3000 | 75000 | Agency to Agency |  |  | 25
(1): 50299020 00; (3): Printing and Publication Expenses | 41443.4
|  | Journal Article | 1 unit | 41443.4 | 41443.4 | Negotiated Procurement/Shopping |  | 1
50205020 01 |  | Telephone Expenses – Mobile
|  | Mobile Load Card | 26 pc | 150 | 3900 | Shopping |  |  | 13 | 13
50299040 00 |  | Subscription Expenses
|  | Creative Cloud Apps Annual Subscription | 1 license | 4850 | 4850 | Petty Cash Fund / Direct Retail |  |  |  | 1
(1): 50604050 14; (3): Technical & Scientific Equipment - Equipment Outlay | 5740000
|  | Automated Electrospinning Machine | 1 lot | 4000000 | 4000000 | Public Bidding |  |  | 1
|  | Laptop | 2 lots | 120000 | 240000 | Negotiated Procurement/Shopping |  |  | 2
|  | Biosafety cabinet | 1 lot | 1500000 | 1500000 | Public Bidding |  |  |  | 1
TOTAL APPROVED BUDGET: |  |  | 7154768.4
+ 10% Provision for Inflation |  |  | 715476.84
+ 10% Contingency |  |  | 715476.84
TOTAL ESTIMATED BUDGET: |  |  | 8585722.08
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
JULIUS L. LEAÑO JR., Ph.D. |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: ______________________ |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________