## PPMP Sample 1 (2)
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
(Sample Only)
END-USER/UNIT: RDD-NFUS
Charged to: Digitalization of Philippine Textiles to Protect and Sustain the Handloom Weaving Sector
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE |  |  |  |  | Jan | Feb | Mar | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
Office Supplies
| 32gb OTG flashdrive | 80 pieces | 625 | 50000 | Small Value Procurement |  | 80
| 16GB microSD card | 5 pieces | 600 | 3000 | Small Value Procurement |  | 5
| Powerbank | 10 pieces | 1000 | 10000 | Small Value Procurement |  | 10
| External hard drive, 1TB | 10 pieces | 5000 | 50000 | Small Value Procurement |  | 10
| Wireless mouse | 5 pieces | 500 | 2500 | Small Value Procurement |  | 5
| Binder Clip 4 per pack black | 20 packs | 25 | 500 | Shopping |  | 20
| Binder clip 2 per pack black | 15 packs | 20 | 300 | Shopping |  | 15
| Paper clip vinyl coated assorted 100s | 5 packs | 30 | 150 | Shopping |  | 5
| Envelope document 5/pack | 10 packs | 30 | 300 | Shopping |  | 10
| Envelope expanding with elastic, legal | 30 packs | 10 | 300 | Shopping |  | 30
| Sticky flags | 20 packs | 100 | 2000 | Shopping |  | 20
| Highlighter (yellow) | 5 pieces | 15 | 75 | Shopping |  | 5
| Glue stick | 10 packs | 30 | 300 | Shopping |  | 10
| Long brown envelope | 50 packs | 20 | 1000 | Shopping |  | 50
| Clearbook, long | 15 pieces | 133.3333 | 2000 | Shopping |  | 15
| Spray paint | 1 piece | 1000 | 1000 | Small Value Procurement |  |  | 1
| All in one laser printer | 3 units | 10000 | 30000 | Small Value Procurement |  |  | 3
| Certificate paper | 100 pieces | 10 | 1000 | Shopping |  |  | 100
| ID and ID laces | 100 pieces | 20 | 2000 | Shopping |  |  | 100
| Manila paper | 50 pieces | 5 | 250 | Shopping |  |  | 50
| USB to VGA/HDMI adapter for Macbook | 3 units | 133.3333 | 400 | Small Value Procurement |  |  | 3
| USB to VGA/HDMI adapter for other laptops | 3 units | 133.3333 | 400 | Small Value Procurement |  |  | 3
| A4 paper/500 pcs/ream | 30 reams | 183.3333 | 5500 | Shopping |  |  | 30
| Paper shredder | 1 piece | 5000 | 5000 | Small Value Procurement |  |  | 1
| Black ink for printer | 8 carts | 400 | 3200 | Shopping |  |  | 8
| Colored ink for printer | 8 carts | 400 | 3200 | Shopping |  |  | 8
| Metal fasteners | 3 packs | 66.6667 | 200 | Shopping |  |  | 3
| Folder for A4 size documents, 10 pcs per pack | 20 packs | 50 | 1000 | Shopping |  |  |  | 20
| Blue sign pens | 20 pieces | 30 | 600 | Shopping |  |  |  | 20
| Regular pens | 100 pieces | 10 | 1000 | Shopping |  |  |  | 100
| Permanent markers | 50 pieces | 20 | 1000 | Shopping |  |  |  | 50
| Transparent tape | 20 pieces | 20 | 400 | Shopping |  |  |  | 20
| Stapler | 3 pieces | 100 | 300 | Shopping |  |  |  | 3
| Staple wires | 10 boxes | 50 | 500 | Shopping |  |  |  | 10
| Correction tape | 10 pieces | 30 | 300 | Shopping |  |  |  | 10
| Scissors | 10 pieces | 30 | 300 | Shopping |  |  |  | 10
Laboratory Supplies
| Machining of components H1 | 4 units | 1640 | 6560 | Small Value Procurement |  | 4
| Machining of components H2 | 4 units | 860 | 3440 | Small Value Procurement |  | 4
| Machining of component M | 8 units | 1000 | 8000 | Small Value Procurement |  | 8
| Disposable ABR electrodes | 300 units | 50 | 15000 | Small Value Procurement |  | 300
| Disposable snap electrodes | 100 units | 57 | 5700 | Small Value Procurement |  | 100
| Skin prep gel | 4 units | 1375 | 5500 | Small Value Procurement |  |  | 4
| Neurodiagnostic Conductive Electrode Paste | 4 units | 1800 | 7200 | Small Value Procurement |  |  | 4
| Gold/silver electrode | 6 units | 1333.3333 | 8000 | Small Value Procurement |  |  | 6
| 70% Isopropyl alcohol | 10 units | 28 | 280 | Small Value Procurement |  |  | 10
| Micropore tape 1in | 6 boxes | 350 | 2100 | Small Value Procurement |  |  |  | 6
| Sterile gauze, individually wrapped | 10 boxes | 300 | 3000 | Small Value Procurement |  |  |  | 10
| Alcohol swab | 6 boxes | 400 | 2400 | Small Value Procurement |  |  |  | 6
Office Equipment
Laboratory Equipment
<-- INSERT ROW IF NEEDED
TOTAL BUDGET: |  | 247155
+ 10% Provision for Inflation |  | 24715.5
+ 10% Contingency |  | 24715.5
TOTAL ESTIMATED BUDGET: |  | 296586
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  | Reviewed by: | [5 empty] | Recommending Approval: | [7 empty] | Approved by:
________________________ |  | MARILOU G. AGUSTIN | [5 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  | Head, Property, Procurement and General Services Section | [5 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  | Date: ______________________ | [5 empty] | Date: ______________________ | [7 empty] | Date: ______________________

## PPMP FRONTIER-NTFIH
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2025
For 1st Quarter of CY 2025
END-USER/UNIT: RDD-NFUS
Charged to: FRONTIER: Fostering the Revitalization of Nascent Textile Innovation Ecosystems in the Regions - Establishment of Natural Textile Fiber Innovation Hub (NTFIH)
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE |  |  |  |  | Jan | Feb | Mar | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
Office Supplies
| Laptop - | 4
| Hardrive atleast 2TB | 4 | 4500 | 18000
| Foldable Laptop Stand | 5 | 1000 | 5000
| 3 boxes - Permanent Marker, Black 12's per box | 1 lot | 350 | 1050 | Shopping | 15 working days |  | 5
| 3 boxes - Permanent Marker, Blue 12's per box |  | 350 | 1050 | Shopping |  |  | 5
| 3 boxes - Permanent Marker, Red 12's per box |  | 350 | 1050 | Shopping |  |  | 5
| 15 boxes -Ballpen Blue 0.5mm Hi-Techpoint Pen 12s/box |  | 380 | 5700 | Shopping |  |  | 15
| 15 boxes - Staple Wire No.35 |  | 150 | 1500 | Shopping |  |  | 10
| 15 boxes - Binder Clips, 32mm 12's |  | 50 | 750 | Shopping |  |  | 15
| 15 boxes - Binder Clips, 19mm 12's |  | 50 | 750 | Shopping |  |  | 15
| 1 box - Expanded Envelope (Legal, 100's) |  | 4000 | 4000 | Shopping |  |  | 1
| 5 boxes - Paper Clips, 50mm, 100's/box |  | 120 | 600 | Shopping |  |  | 5
| 5 boxes - Paper Clips, 33mm, 100's/box |  | 100 | 500 | Shopping |  |  | 5
| 30 pcs - Clear Packing Tape 48mm (2" width)x 100m |  | 100 | 3000 | Shopping |  |  | 30
| 30 pcs - Clear Packing Tape 24mm (1" width)x 100m |  | 80 | 2400 | Shopping |  |  | 30
| 50 pcs - Masking Tape, 1"inch |  | 50 | 2500 | Shopping |  |  | 30
| 10 packs - Specialty Boardpaper, 30's, 90gsm |  | 150 | 1500 | Shopping |  |  | 10
| 10 packs - Label Index Stickers, 5 colors |  | 60 | 600 | Shopping |  |  | 10
| 5 packs - White Folder A4 size, 25 pcs per pack |  | 300 | 1500 | Shopping |  |  | 5
| 5 packs - White Folder Legal Size, 25pcs per pack |  | 350 | 1750 | Shopping |  |  | 5
| 20 packs - Sticky Notes 3x3 inches, 100 sheets. Light Green |  | 50 | 1000 | Shopping |  |  | 20
| 10 packs - Vellum Board (A4, 10's/pack) |  | 150 | 1500 | Shopping |  |  | 10
| 10 packs - Sticker Paper, Matte (A4, 10's/pack) |  | 150 | 1500 | Shopping |  |  | 10
| 25 pcs Clear Acrylic Name Plate Holder for Conference; 3x8.5 inches for conference\ |  | 400 | 10000 | Shopping |  |  | 25
| 30 pcs - Steno Notebook 153x228mm, 60leaves |  | 80 | 2400 | Shopping |  |  | 30
| 30 pcs - Laboratory Notebook, 100 leaves, 216x280mm, blue cover |  | 300 | 9000 | Shopping |  |  | 30
| Computer Chair/Office Chair,/Ergonomic Chair With Armrest | 5 pcs | 10000 | 50000 | Shopping |  |  | 5
| Microsoft Office License - Lifetime 2021 version or better | 2 pcs | 6000 | 12000 | Shopping
Other Supplies
| Oil-Free Vacuum Pump | 1 unit |  | 0
| 50 packs - Pull-ups Tissue, 2 ply, 190pulls/pack | 1 lot | 250 | 12500 | Shopping | 30-45 working days |  | 50
| 30 bottles - Isopropyl Alcohol with moisturizer, 70%,500ml |  | 280 | 8400 | Shopping |  |  | 30
| 12 gallons - Liquid Detergent |  | 600 | 7200 | Shopping |  |  | 10
| 10 bottles - Liquid hand soap, Pump dispenser, 225ml |  | 230 |  | Shopping |  |  | 10
| 10 bottles - Dishwashing Liquid, Antibac, 475ml |  | 350 |  | Shopping |  |  | 10
| 12 gallons - Commercial Bleach (Liquid) - Sodium Hypochlorite |  | 1000 | 12000 | Shopping |  |  | 5
| 24 pcs - Paper Towel- standard specifications |  | 500 | 12000
| 5 boxes - Aluminum Foil - Standard Specification |  | 1000 | 5000 | Shopping
| 5 pcs Color LaserMFP 178nw Original Laser Toner Cartridge - Yellow | 1 lot | 2500 | 12500 | Shopping
| 5 pcs Color LaserMFP 178nw Original Laser Toner Cartridge - Cyan |  | 2500 | 12500 | Shopping
| 5 pcs Color LaserMFP 178nw Original Laser Toner Cartridge - Magenta |  | 2500 | 12500 | Shopping
| 5 pcs Color LaserMFP 178nw Original Laser Toner Cartridge - Black |  | 2500 | 12500 | Shopping
Laboratory Supplies
| 20 boxes - Lint freeTissue 1 ply 4.3x8.4 inches |  | 350 | 7000
| Thimbles - Double Thickness, 33mm x 80 mm, 25pcs per box | 2 box | 3000 | 6000
| Stainless Strainer - minimum of 12 inches diameter and minimum of 6 inches depth | 3 pcs | 2000 | 6000
| Stainless Steel Cooking Barrel - 50 Liter capacity | 1 | 3000 | 3000 | 42100
| Stainless Steel Cooking Barrel - 20 L capacity | 2 pcs | 2500 | 5000 | 7500
| Stainless Steel Cooking Barrel - 10L to12 L capacity | 2 pcs | 2000 | 4000
| Gooch Crucibles - Borosilicate glass, 50 mL | 20 pcs | 3500 | 70000
| Glass Laboratory Thermometer - Glass Thermometer: 25 mm Immersion, -10 to 250C, Glass, Mineral Spirit-Filled Model: CG-3508-N-02 | 3 pcs | 2000 | 6000
| Beaker - Borosilicate glass, 50 mL | 5 pcs | 1000 | 5000
| Beaker - Borosilicate glass, 100 mL | 5 pcs | 1500 | 7500
| Beaker - Borosilicate glass, 500 mL | 5 pcs | 2000 | 10000
| Beaker - Borosilicate glass, 1000 mL | 5 pcs | 3000 | 15000
| Erlenmeyer flask - Borosilicate glass, 250 mL | 10 pcs | 2000 | 5000
| Erlenmeyer flask - Borosilicate glass, 500 mL | 10 pcs | 2000 | 20000
| Stirring Rod - Glass, 200 mm | 5pcs | 1000 | 5000
| Spatula - Stainless, Standard size | 3 pcs | 1000 | 3000
| Volumetric Flask - Borosilicate glass, 1000 mL | 5pcs | 3000 | 15000
| Volumetric Flask - Borosilicate glass, 2000 mL | 5pcs | 5000 | 25000
| Magnetic Stirrer Bar - 30 mm / 1.18 inches | 18 pcs | 1000 | 18000
| Micropipette 5ml | 1 pc | 5000 | 5000
| Micropipette 10ml | 1 pc | 10000 | 10000
| Latex rubber tube, Bleed Elastic Hose, 6mmx9mm | 10 meters | 250 | 2500
| Latex rubber tube, Bleed Elastic Hose, 8mmx12mm | 10 meters | 250 | 2500
| Micropipette tips Plastic 5ml | 1 box | 5000 | 5000
| Desiccator - Borosilicate glass, 210 mm | 2 pc | 20000 | 40000
| Crucible Tongs - Stainless Steel, 230 mm | 5 pcs | 1000 | 5000
| Forceps - Standard specifications | 3 pcs | 1000 | 3000
| Test tube Brush Small | 5 pcs | 500 | 2500
| Test tube Brush Medium | 5 pcs | 800 | 4000
| Test tube Brush Large | 5 pcs | 1000 | 5000
| Glass Dessicator - 9.4 inch inner diameter; 12 inch outer diameter; 13 inch height - with porcelain plate and knob cover | 3 pcs | 20000 | 60000
| 20 boxes - Nitrile Gloves - Medium | 1 lot | 400 | 8000 | Shopping
| 30 boxes - Face Mask, 3 ply, Earloop, 50pcs/box |  | 300 | 9000
| 10 pcs - Gas Masks, N95 grade 3M |  | 150 | 1500
| 5 pcs - Parafilm, 4" x 125 ft |  | 3000 | 15000
| 5 pcs - Non-Slip Lab Shoes (Medium/Size 8) |  | 600 | 3000
| Emrgency Spray Eyewash and Emergency Shower | 1 unit | 50000 | 50000
| Sodium Hydroxide (NaOH) Liquid - Analytical grade 49% purity - 30 kg/cby | 10 carboys | 3800 | 38000 | Small Value Procurement | 60 Working Days |  | 10
| Sodium Hydroxide (NaOH) Micro Pellets -Analytical grade 97-99% purity - 1kg/btl | 10 bottles | 3000 | 30000 | Small Value Procurement |  |  | 100
12 | Acetone (Liquid) -Analytical grade 99% purity, 2.5 L/bottle | 12 bottles | 3500 | 42000 | Small Value Procurement |  |  | 12
| Hydrochloric Acid (Liquid) -Analytical grade 37% purity, 2.5 L/bottle | 12 bottles | 5000 | 60000 | Small Value Procurement |  |  | 12
| Acetic Acid (Liquid) -Analytical grade 99% purity, 40L/carboy | 10 carboys | 5000 | 50000 | Small Value Procurement |  |  | 10
| Hydrogen Peroxide (Liquid) -Analytical grade 99% purity | 5 gallons | 8000 | 40000 | Small Value Procurement |  |  | 5
Hydrogen Peroxide - Aqueous Solution (50%) 35kg/cby
5 | Sodium Chlorite (Powder) -Analytical grade 80% purity | 5 bottles | 2000 | 10000 | Small Value Procurement |  |  | 5
12 | Sulfuric acid (Liquid) - Analytical grade 98% purity, 2.5 L/bottle | 12 bottles | 4000 | 48000 | Small Value Procurement
| Sodium metabisulfite -Technical grade, 97% purity, 1kg/bottle | 5 bottles | 1000 | 5000 | Small Value Procurement |  |  | 5
| Sodium silicate -Neutral solution, pure | 5 gallons | 1000 | 5000 | Small Value Procurement |  |  | 5
| Fabric Softener (Flakes) |  |  |  | Small Value Procurement
| Xylanase Enzyme - Activity: ~200-250 U/m | 10 Liters | 5000 | 50000 | Small Value Procurement | 60 working days |  | 5 | 5
| Pectinase Enzyme - Activity: ~200-250 U/m | 10 Liters | 5000 | 50000 | Small Value Procurement |  |  | 5 | 5
| Laccase -Laccase from Trametes versicolor powder, light brown, ≥ 0.5 U/mg, Sigma cat#38429 | 5 bottles | 120000 | 600000 | Small Value Procurement
Other MOOE
| Bamboo Lei for MOA Signing and Launching of NTFIH in Laguna, Leyte , Davao, Isabela, Catanduanes, and Mindoro | 60pcs | 500 | 30000 | Shopping | 30 working days |  | 60
Cash Advances
| Banana Fiber Decorticated/Raw, Variety: Cavendish Source: Catanduanes | 1kg | 1000 | 1000 | Cash Advances | per schedule |  |  | 1
| Pineapple Fiber Decorticated, Variety : Formossa Source: Catanduanes | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Variety: Cavendish Source: Isabela | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Formossa Source: Isabela | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw Variety: Cavendish, Source: Mindoro | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : FormossaSource: Mindoro | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Variety: Cavendish Source: Northern Samar | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Formossa Source: Northern Samar | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Source: Catanduanes | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Hawaian Source: Catanduanes | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Source: Isabela | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Hawaian Source: Isabela | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Source: Mindoro | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Hawaian Source: Mindoro | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Source: Northern Samar | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Hawaian Source: Northern Samar | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Bakong Raw Fibers - Decorticated | 2kg | 500 | 1000 | Cash Advances
| Bakong Stem | 1kg | 500 | 500 | Cash Advances
Repairs and Maintenance Expenses
| Renovation of NTFIH Isabela | 1 lot | 1200000 | 1200000 | Competitive Bidding (Public Bidding) | 60 working days |  | 1
| Renovation of NTFIH Mindoro | 1 lot | 1266666.67 | 1266666.67 | Competitive Bidding (Public Bidding) |  |  | 1
| Renovation of NTFIH Catanduanes | 1 lot | 1266666.67 | 1266666.67 | Competitive Bidding (Public Bidding) |  |  | 1
| Renovation of NTFIH Leyte | 1 lot | 1266666.67 | 1266666.67 | Competitive Bidding (Public Bidding) |  |  | 1
Other Professional Services (OPS)
| FESEM Imaging Sample: Raw and treated textile fiber - Surface morphology - Cross-sectional imaging - VAT inclusive - Turnaround time: 7-10 working days upon receipt of sample | 30 Samples | 9000 | 180000 | Agency to Agency | per schedule |  | 20
| Fiber fineness, cut middle method - sample raw and treated bamboo fibers - includes raw data of results - turnaround time: 7-10 working days upon receipt of sample | 20 samples | 2500 | 50000 | Agency to Agency | per schedule |  | 20
Capital Outlay (Equipment)
| Decorticating machine | 6 lots | 250000 | 1500000 | Public Bidding (Competitive Bidding) |  | 6
| Mechanical Softening Machine | 3 lots | 1500000 | 4500000 | Public Bidding (Competitive Bidding) |  | 3
| Bench Scale Degumming Equipment | 6 lots | 600000 | 3600000 | Public Bidding (Competitive Bidding) |  | 6
| Fiber Cutting Machine | 3 lots | 800000 | 2400000 | Public Bidding (Competitive Bidding) |  | 3
| Hard Fiber Opener | 3 lots | 800000 | 2400000 | Public Bidding (Competitive Bidding) |  | 3
Office Equipment
Laboratory Equipment
| Hydro Extractor Machine | 3 lots | 105000 | 315000 | Public Bidding (Competitive Bidding) |  |  |  | 3
<-- INSERT ROW IF NEEDED
TOTAL BUDGET: |  | 21419700.01
+ 10% Provision for Inflation |  | 2141970.001
+ 10% Contingency |  | 2141970.001
TOTAL ESTIMATED BUDGET: |  | 25703640.01
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  | Reviewed by: | [5 empty] | Recommending Approval: | [7 empty] | Approved by:
ENGR. KARL MARX LENNIN A. FLORANTE |  | MARILOU G. AGUSTIN | [5 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  | Head, Property, Procurement and General Services Section | [5 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  | Date: ______________________ | [5 empty] | Date: ______________________ | [7 empty] | Date: ______________________

## PPMP FRONTIER-NTFIH Q2
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2025
For 1st Quarter of CY 2025
END-USER/UNIT: RDD-NFUS
Charged to: FRONTIER: Fostering the Revitalization of Nascent Textile Innovation Ecosystems in the Regions - Establishment of Natural Textile Fiber Innovation Hub (NTFIH)
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE |  |  |  |  | April | May | June | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
Office Supplies
| Laptop - | 4 | 49999 | 199996 | Small Vallue Procurement |  | 4
| Hardrive atleast 2TB | 4 | 4500 | 18000 | Shopping |  | 4
| Foldable Laptop Stand | 5 | 1000 | 5000 | Shopping |  | 5
| 3 boxes - Permanent Marker, Black 12's per box | 1 lot | 350 | 1050 | Shopping | 15 working days | 5
| 3 boxes - Permanent Marker, Blue 12's per box |  | 350 | 1050 | Shopping |  | 5
| 3 boxes - Permanent Marker, Red 12's per box |  | 350 | 1050 | Shopping |  | 5
| 15 boxes -Ballpen Blue 0.5mm Hi-Techpoint Pen 12s/box |  | 380 | 5700 | Shopping |  | 15
| 15 boxes - Staple Wire No.35 |  | 150 | 1500 | Shopping |  | 10
| 15 boxes - Binder Clips, 32mm 12's |  | 50 | 750 | Shopping |  | 15
| 15 boxes - Binder Clips, 19mm 12's |  | 50 | 750 | Shopping |  | 15
| 1 box - Expanded Envelope (Legal, 100's) |  | 4000 | 4000 | Shopping |  | 1
| 5 boxes - Paper Clips, 50mm, 100's/box |  | 120 | 600 | Shopping |  | 5
| 5 boxes - Paper Clips, 33mm, 100's/box |  | 100 | 500 | Shopping |  | 5
| 30 pcs - Clear Packing Tape 48mm (2" width)x 100m |  | 100 | 3000 | Shopping |  | 30
| 30 pcs - Clear Packing Tape 24mm (1" width)x 100m |  | 80 | 2400 | Shopping |  | 30
| 50 pcs - Masking Tape, 1"inch |  | 50 | 2500 | Shopping |  | 30
| 10 packs - Specialty Boardpaper, 30's, 90gsm |  | 150 | 1500 | Shopping |  | 10
| 10 packs - Label Index Stickers, 5 colors |  | 60 | 600 | Shopping |  | 10
| 5 packs - White Folder A4 size, 25 pcs per pack |  | 300 | 1500 | Shopping |  | 5
| 5 packs - White Folder Legal Size, 25pcs per pack |  | 350 | 1750 | Shopping |  | 5
| 20 packs - Sticky Notes 3x3 inches, 100 sheets. Light Green |  | 50 | 1000 | Shopping |  | 20
| 10 packs - Vellum Board (A4, 10's/pack) |  | 150 | 1500 | Shopping |  | 10
| 10 packs - Sticker Paper, Matte (A4, 10's/pack) |  | 150 | 1500 | Shopping |  | 10
| 25 pcs Clear Acrylic Name Plate Holder for Conference; 3x8.5 inches for conference\ |  | 400 | 10000 | Shopping |  | 25
| 30 pcs - Steno Notebook 153x228mm, 60leaves |  | 80 | 2400 | Shopping |  | 30
| 30 pcs - Laboratory Notebook, 100 leaves, 216x280mm, blue cover |  | 300 | 9000 | Shopping |  | 30
| Computer Chair/Office Chair,/Ergonomic Chair With Armrest | 5 pcs | 10000 | 50000 | Shopping |  | 5
| Microsoft Office License - Lifetime 2021 version or better | 2 pcs | 6000 | 12000 | Shopping |  | 2
Other Supplies
| Oil-Free Vacuum Pump | 1 unit | 49990 | 49990 | Shopping |  | 1
| 50 packs - Pull-ups Tissue, 2 ply, 190pulls/pack | 1 lot | 250 | 12500 | Shopping | 30-45 working days | 50
| 30 bottles - Isopropyl Alcohol with moisturizer, 70%,500ml |  | 280 | 8400 | Shopping |  | 30
| 12 gallons - Liquid Detergent |  | 600 | 7200 | Shopping |  | 10
| 10 bottles - Liquid hand soap, Pump dispenser, 225ml |  | 230 |  | Shopping |  | 10
| 10 bottles - Dishwashing Liquid, Antibac, 475ml |  | 350 |  | Shopping |  | 10
| 12 gallons - Commercial Bleach (Liquid) - Sodium Hypochlorite |  | 1000 | 12000 | Shopping |  | 5
| 24 pcs - Paper Towel- standard specifications |  | 500 | 12000 |  |  | 24
| 5 boxes - Aluminum Foil - Standard Specification |  | 1000 | 5000 | Shopping |  | 5
| 5 pcs Color LaserMFP 178nw Original Laser Toner Cartridge - Yellow | 1 lot | 1500 | 7500 | Shopping |  | 5
| 5 pcs Color LaserMFP 178nw Original Laser Toner Cartridge - Cyan |  | 1500 | 7500 | Shopping |  | 5
| 5 pcs Color LaserMFP 178nw Original Laser Toner Cartridge - Magenta |  | 1500 | 7500 | Shopping |  | 5
| 5 pcs Color LaserMFP 178nw Original Laser Toner Cartridge - Black |  | 2000 | 10000 | Shopping |  | 5
Laboratory Supplies
| 20 boxes - Lint freeTissue 1 ply 4.3x8.4 inches | 20 | 350 | 7000 | Shopping |  | 20
| Thimbles - Double Thickness, 33mm x 80 mm, 25pcs per box | 2 box | 3000 | 6000 | Shopping |  | 2
| Stainless Strainer - minimum of 12 inches diameter and minimum of 6 inches depth | 3 pcs | 2000 | 6000 | Shopping |  | 3
| Stainless Steel Cooking Barrel - 50 Liter capacity | 1 | 3000 | 3000 | Shopping |  | 1
| Stainless Steel Cooking Barrel - 20 L capacity | 2 pcs | 2500 | 5000 | Shopping |  | 2
| Stainless Steel Cooking Barrel - 10L to12 L capacity | 2 pcs | 2000 | 4000 | Shopping |  | 2
| Gooch Crucibles - Borosilicate glass, 50 mL | 20 pcs | 3500 | 70000 | SVP |  | 20
| Glass Laboratory Thermometer - Glass Thermometer: 25 mm Immersion, -10 to 250C, Glass, Mineral Spirit-Filled Model: CG-3508-N-02 | 3 pcs | 2000 | 6000 | Shopping |  | 3
| Beaker - Borosilicate glass, 50 mL | 5 pcs | 1000 | 5000 | Shopping |  | 5
| Beaker - Borosilicate glass, 100 mL | 5 pcs | 1500 | 7500 | Shopping |  | 5
| Beaker - Borosilicate glass, 500 mL | 5 pcs | 2000 | 10000 | Shopping |  | 5
| Beaker - Borosilicate glass, 1000 mL | 5 pcs | 3000 | 15000 | Shopping |  | 5
| Erlenmeyer flask - Borosilicate glass, 250 mL | 10 pcs | 2000 | 5000 | Shopping |  | 10
| Erlenmeyer flask - Borosilicate glass, 500 mL | 10 pcs | 2000 | 20000 | Shopping |  | 10
| Stirring Rod - Glass, 200 mm | 5pcs | 1000 | 5000 | Shopping |  | 5
| Spatula - Stainless, Standard size | 3 pcs | 1000 | 3000 | Shopping |  | 3
| Volumetric Flask - Borosilicate glass, 1000 mL | 5pcs | 3000 | 15000 | Shopping |  | 5
| Volumetric Flask - Borosilicate glass, 2000 mL | 5pcs | 5000 | 25000 | Shopping |  | 5
| Magnetic Stirrer Bar - 30 mm / 1.18 inches | 18 pcs | 1000 | 18000 | Shopping |  | 18
| Micropipette 5ml | 1 pc | 5000 | 5000 | Shopping |  | 1
| Micropipette 10ml | 1 pc | 10000 | 10000 | Shopping |  | 1
| Latex rubber tube, Bleed Elastic Hose, 6mmx9mm | 10 meters | 250 | 2500 | Shopping |  | 10
| Latex rubber tube, Bleed Elastic Hose, 8mmx12mm | 10 meters | 250 | 2500 | Shopping |  | 10
| Micropipette tips Plastic 5ml | 1 box | 5000 | 5000 | Shopping |  | 1
| Desiccator - Borosilicate glass, 210 mm | 2 pc | 20000 | 40000 | Shopping |  | 2
| Crucible Tongs - Stainless Steel, 230 mm | 5 pcs | 1000 | 5000 | Shopping |  | 5
| Forceps - Standard specifications | 3 pcs | 1000 | 3000 | Shopping |  | 3
| Test tube Brush Small | 5 pcs | 500 | 2500 | Shopping |  | 5
| Test tube Brush Medium | 5 pcs | 800 | 4000 | Shopping |  | 5
| Test tube Brush Large | 5 pcs | 1000 | 5000 | Shopping |  | 5
| Glass Dessicator - 9.4 inch inner diameter; 12 inch outer diameter; 13 inch height - with porcelain plate and knob cover | 3 pcs | 20000 | 60000 | SVP |  | 3
| 20 boxes - Nitrile Gloves - Medium | 1 lot | 400 | 8000 | Shopping |  | 20
| 30 boxes - Face Mask, 3 ply, Earloop, 50pcs/box |  | 300 | 9000 | Shopping |  | 30
| 10 pcs - Gas Masks, N95 grade 3M |  | 150 | 1500 | Shopping |  | 10
| 5 pcs - Parafilm, 4" x 125 ft |  | 3000 | 15000 | Shopping |  | 5
| 5 pcs - Non-Slip Lab Shoes (Medium/Size 8) |  | 600 | 3000 | Shopping |  | 5
| Emrgency Spray Eyewash and Emergency Shower | 1 unit | 50000 | 50000 | SVP |  | 1
| Sodium Hydroxide (NaOH) Liquid - Analytical grade 49% purity - 30 kg/cby | 10 carboys | 3800 | 38000 | Small Value Procurement | 60 Working Days | 10
| Sodium Hydroxide (NaOH) Micro Pellets -Analytical grade 97-99% purity - 1kg/btl | 10 bottles | 3000 | 30000 | Small Value Procurement |  | 100
| Acetone (Liquid) -Analytical grade 99% purity, 2.5 L/bottle | 12 bottles | 3500 | 42000 | Small Value Procurement |  | 12
| Hydrochloric Acid (Liquid) -Analytical grade 37% purity, 2.5 L/bottle | 12 bottles | 5000 | 60000 | Small Value Procurement |  | 12
| Acetic Acid (Liquid) -Analytical grade 99% purity, 40L/carboy | 10 carboys | 5000 | 50000 | Small Value Procurement |  | 10
| Hydrogen Peroxide (Liquid) -Analytical grade 99% purity | 5 gallons | 8000 | 40000 | Small Value Procurement |  | 5
Hydrogen Peroxide - Aqueous Solution (50%) 35kg/cby
| Sodium Chlorite (Powder) -Analytical grade 80% purity | 5 bottles | 2000 | 10000 | Small Value Procurement |  | 5
| Sulfuric acid (Liquid) - Analytical grade 98% purity, 2.5 L/bottle | 12 bottles | 4000 | 48000 | Small Value Procurement
| Sodium metabisulfite -Technical grade, 97% purity, 1kg/bottle | 5 bottles | 1000 | 5000 | Small Value Procurement |  | 5
| Sodium silicate -Neutral solution, pure | 5 gallons | 1000 | 5000 | Small Value Procurement |  | 5
| Fabric Softener (Flakes) |  |  |  | Small Value Procurement
| Xylanase Enzyme - Activity: ~200-250 U/m | 10 Liters | 5000 | 50000 | Small Value Procurement | 60 working days | 10
| Pectinase Enzyme - Activity: ~200-250 U/m | 10 Liters | 5000 | 50000 | Small Value Procurement |  | 10
| Laccase -Laccase from Trametes versicolor powder, light brown, ≥ 0.5 U/mg, Sigma cat#38429 | 5 bottles | 120000 | 600000 | Small Value Procurement
Other MOOE
| Bamboo Lei for MOA Signing and Launching of NTFIH in Laguna, Leyte , Davao, Isabela, Catanduanes, and Mindoro | 60pcs | 500 | 30000 | Shopping | 30 working days | 60
| Full Fabric notebook as Tokens | 60 pcs | 600 | 36000 | Shopping | 15 CD | 60
| Tokens Packaging Box | 60 pcs | 350 | 21000 | Shopping | 15CD | 60
Cash Advances
| Banana Fiber Decorticated/Raw, Variety: Cavendish Source: Catanduanes | 1kg | 1000 | 1000 | Cash Advances | per schedule |  |  | 1
| Pineapple Fiber Decorticated, Variety : Formossa Source: Catanduanes | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Variety: Cavendish Source: Isabela | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Formossa Source: Isabela | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw Variety: Cavendish, Source: Mindoro | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : FormossaSource: Mindoro | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Variety: Cavendish Source: Northern Samar | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Formossa Source: Northern Samar | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Source: Catanduanes | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Hawaian Source: Catanduanes | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Source: Isabela | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Hawaian Source: Isabela | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Source: Mindoro | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Hawaian Source: Mindoro | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Source: Northern Samar | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Hawaian Source: Northern Samar | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Bakong Raw Fibers - Decorticated | 2kg | 500 | 1000 | Cash Advances |  |  |  | 2
| Bakong Stem | 1kg | 500 | 500 | Cash Advances |  |  |  | 1
| Abaca Fiber Decorticated/Raw, Source: Catanduanes | 2kg | 500 | 1000 | Cash Advances |  |  |  | 2
Repairs and Maintenance Expenses
| Renovation of NTFIH Isabela | 1 lot | 1200000 | 1200000 | Competitive Bidding (Public Bidding) | 60 working days |  | 1
| Renovation of NTFIH Mindoro | 1 lot | 1266666.67 | 1266666.67 | Competitive Bidding (Public Bidding) |  |  | 1
| Renovation of NTFIH Catanduanes | 1 lot | 1266666.67 | 1266666.67 | Competitive Bidding (Public Bidding) |  |  | 1
| Renovation of NTFIH Leyte | 1 lot | 1266666.67 | 1266666.67 | Competitive Bidding (Public Bidding) |  |  | 1
Other Professional Services (OPS)
| FESEM Imaging Sample: Raw and treated textile fiber - Surface morphology - Cross-sectional imaging - VAT inclusive - Turnaround time: 7-10 working days upon receipt of sample | 30 Samples | 9000 | 180000 | Agency to Agency | per schedule |  | 20
| Fiber fineness, cut middle method - sample raw and treated bamboo fibers - includes raw data of results - turnaround time: 7-10 working days upon receipt of sample | 20 samples | 2500 | 50000 | Agency to Agency | per schedule |  | 20
Capital Outlay (Equipment)
| Decorticating machine | 6 lots | 250000 | 1500000 | Public Bidding (Competitive Bidding) |  | 6
| Mechanical Softening Machine | 3 lots | 1500000 | 4500000 | Public Bidding (Competitive Bidding) |  | 3
| Bench Scale Degumming Equipment | 6 lots | 600000 | 3600000 | Public Bidding (Competitive Bidding) |  | 6
| Fiber Cutting Machine | 3 lots | 800000 | 2400000 | Public Bidding (Competitive Bidding) |  | 3
| Hard Fiber Opener | 3 lots | 800000 | 2400000 | Public Bidding (Competitive Bidding) |  | 3
Office Equipment
Laboratory Equipment
| Hydro Extractor Machine | 3 lots | 105000 | 315000 | Public Bidding (Competitive Bidding) |  |  |  | 3
<-- INSERT ROW IF NEEDED
TOTAL BUDGET: |  | 21710186.01
+ 10% Provision for Inflation |  | 2171018.601
+ 10% Contingency |  | 2171018.601
TOTAL ESTIMATED BUDGET: |  | 26052223.21
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  | Reviewed by: | [5 empty] | Recommending Approval: | [7 empty] | Approved by:
ENGR. KARL MARX LENNIN A. FLORANTE |  | MARILOU G. AGUSTIN | [5 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  | Head, Property, Procurement and General Services Section | [5 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  | Date: ______________________ | [5 empty] | Date: ______________________ | [7 empty] | Date: ______________________

## PPMP FRONTIER-NTFIH Q1
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2025
For 1st Quarter of CY 2025
END-USER/UNIT: RDD-NFUS
Charged to: FRONTIER: Fostering the Revitalization of Nascent Textile Innovation Ecosystems in the Regions - Establishment of Natural Textile Fiber Innovation Hub (NTFIH)
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE |  |  |  |  | Jan | Feb | Mar | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
Office Supplies
| 3 boxes - Permanent Marker, Black 12's per box | 1 lot | 350 | 1050 | Shopping | 15 working days |  | 5
| 3 boxes - Permanent Marker, Blue 12's per box |  | 350 | 1050 | Shopping |  |  | 5
| 3 boxes - Permanent Marker, Red 12's per box |  | 350 | 1050 | Shopping |  |  | 5
| 15 boxes -Ballpen Blue 0.5mm Hi-Techpoint Pen 12s/box |  | 380 | 5700 | Shopping |  |  | 15
| 15 boxes - Staple Wire No.35 |  | 150 | 1500 | Shopping |  |  | 10
| 15 boxes - Binder Clips, 32mm 12's |  | 50 | 750 | Shopping |  |  | 15
| 15 boxes - Binder Clips, 19mm 12's |  | 50 | 750 | Shopping |  |  | 15
| 1 box - Expanded Envelope (Legal, 100's) |  | 4000 | 4000 | Shopping |  |  | 1
| 5 boxes - Paper Clips, 50mm, 100's/box |  | 120 | 600 | Shopping |  |  | 5
| 5 boxes - Paper Clips, 33mm, 100's/box |  | 100 | 500 | Shopping |  |  | 5
| 30 pcs - Clear Packing Tape 48mm (2" width)x 100m |  | 100 | 3000 | Shopping |  |  | 30
| 30 pcs - Clear Packing Tape 24mm (1" width)x 100m |  | 80 | 2400 | Shopping |  |  | 30
| 50 pcs - Masking Tape, 1"inch |  | 50 | 2500 | Shopping |  |  | 30
| 10 packs - Specialty Boardpaper, 30's, 90gsm |  | 150 | 1500 | Shopping |  |  | 10
| 10 packs - Label Index Stickers, 5 colors |  | 60 | 600 | Shopping |  |  | 10
| 5 packs - White Folder A4 size, 25 pcs per pack |  | 300 | 1500 | Shopping |  |  | 5
| 5 packs - White Folder Legal Size, 25pcs per pack |  | 350 | 1750 | Shopping |  |  | 5
| 20 packs - Sticky Notes 3x3 inches, 100 sheets. Light Green |  | 50 | 1000 | Shopping |  |  | 20
| 10 packs - Vellum Board (A4, 10's/pack) |  | 150 | 1500 | Shopping |  |  | 10
| 10 packs - Sticker Paper, Matte (A4, 10's/pack) |  | 150 | 1500 | Shopping |  |  | 10
| 25 pcs Clear Acrylic Name Plate Holder for Conference; 3x8.5 inches for conference\ |  | 400 | 10000 | Shopping |  |  | 25
| 30 pcs - Steno Notebook 153x228mm, 60leaves |  | 80 | 2400 | Shopping |  |  | 30
| 30 pcs - Laboratory Notebook, 100 leaves, 216x280mm, blue cover |  | 300 | 9000 | Shopping |  |  | 30
| Computer Chair/Office Chair,/Ergonomic Chair With Armrest | 5 pcs | 10000 | 50000 | Shopping |  |  | 5
| Microsoft Office License - Lifetime 2021 version or better | 2 pcs | 6000 | 12000 | Shopping
Other Supplies
| 50 packs - Pull-ups Tissue, 2 ply, 190pulls/pack | 1 lot | 250 | 12500 | Shopping | 30-45 working days |  | 50
| 30 bottles - Isopropyl Alcohol with moisturizer, 70%,500ml |  | 280 | 8400 | Shopping |  |  | 30
| 12 gallons - Liquid Detergent |  | 600 | 7200 | Shopping |  |  | 10
| 10 bottles - Liquid hand soap, Pump dispenser, 225ml |  | 230 |  | Shopping |  |  | 10
| 10 bottles - Dishwashing Liquid, Antibac, 475ml |  | 350 |  | Shopping |  |  | 10
| 12 gallons - Commercial Bleach (Liquid) - Sodium Hypochlorite |  | 1000 | 12000 | Shopping |  |  | 5
| 24 pcs - Paper Towel- standard specifications |  | 500 | 12000
| 2 boxes - Aluminum Foil - Standard Specification |  | 1000 | 2000 | Shopping
| 5 pcs Color LaserMFP 178nw Original Laser Toner Cartridge - Yellow | 1 lot | 1500 | 7500 | Shopping
| 5 pcs Color LaserMFP 178nw Original Laser Toner Cartridge - Cyan |  | 1500 | 7500 | Shopping
| 5 pcs Color LaserMFP 178nw Original Laser Toner Cartridge - Magenta |  | 1500 | 7500 | Shopping
| 5 pcs Color LaserMFP 178nw Original Laser Toner Cartridge - Black |  | 2000 | 10000 | Shopping
Laboratory Supplies
| 30 boxes - Face Mask, 3 ply, Earloop, 50pcs/box | 1 lot | 300 | 9000 | Shopping | 15 working days |  | 30
| 20 boxes - Lint freeTissue 1 ply 4.3x8.4 inches |  | 350 | 7000
| Thimbles - Double Thickness, 33mm x 80 mm, 25pcs per box | 2 box | 3000
| Stainless Strainer - minimum of 12 inches diameter and minimum of 6 inches depth | 3 pcs | 1500 | 4500
| Stainless Steel Cooking Barrel - 50 Liter capacity | 1 | 3000 | 3000
| Stainless Steel Cooking Barrel - 20 L capacity | 2 pcs | 2000 | 4000
| Stainless Steel Cooking Barrel - 10L to12 L capacity | 2 pcs | 2000 | 4000
| Gooch Crucibles - Borosilicate glass, 50 mL | 20 pcs | 3500 | 70000
| Glass Laboratory Thermometer - Glass Thermometer: 25 mm Immersion, -10 to 250C, Glass, Mineral Spirit-Filled Model: CG-3508-N-02 | 3 pcs | 1000 | 3000
| Nitrile Gloves - Medium | 15 box | 400 | 6000
| Beaker - Borosilicate glass, 50 mL | 5 pcs | 1000 | 5000
| Beaker - Borosilicate glass, 100 mL | 5 pcs | 1500 | 7500
| Beaker - Borosilicate glass, 500 mL | 5 pcs | 2000 | 10000
| Beaker - Borosilicate glass, 1000 mL | 5 pcs | 3000 | 15000
| Erlenmeyer flask - Borosilicate glass, 250 mL | 10 pcs | 2000 | 5000
| Erlenmeyer flask - Borosilicate glass, 500 mL | 10 pcs | 2000 | 20000
| Stirring Rod - Glass, 200 mm | 5pcs | 1000 | 5000
| Spatula - Stainless, Standard size | 3 pcs | 1000 | 900
| Volumetric Flask - Borosilicate glass, 1000 mL | 5pcs | 1500 | 7500
| Magnetic Stirrer Bar - 30 mm / 1.18 inches | 18 pcs | 1000 | 18000
| Micropipette 5ml | 1 pc | 5000 | 5000
| Micropipette tips Plastic 5ml | 1 box | 5000 | 5000
| Desiccator - Borosilicate glass, 210 mm | 2 pc | 20000 | 40000
| Crucible Tongs - Stainless Steel, 230 mm | 5 pcs | 1000 | 5000
| Forceps - Standard specifications | 3 pcs | 1000 | 3000
| Gas Masks, N95 grade 3M | 10 pcs | 150 | 1500
| Test tube Brush Small | 5 pcs | 500 | 2500
| Test tube Brush Medium | 5 pcs | 500 | 2500
| Test tube Brush Large | 5 pcs | 800 | 4000
| Parafilm, 4" x 125 ft | 3 pcs | 3000 | 9000
| Glass Dessicator - 9.4 inch inner diameter; 12 inch outer diameter; 13 inch height - with porcelain plate and knob cover | 3 pcs | 15000 | 45000
| Non-Slip Lab Shoes (Medium/Size 8) | 5 pcs | 600 | 3000
| Emrgency Spray Eyewash and Emergency Shower | 1 unit | 50000 | 50000
| Sodium Hydroxide (NaOH) Liquid - Analytical grade 49% purity - 30 kg/cby | 10 carboys | 3800 | 38000 | Small Value Procurement | 60 Working Days |  | 10
| Sodium Hydroxide (NaOH) Micro Pellets -Analytical grade 97-99% purity - 1kg/btl | 10 bottles | 3000 | 30000 | Small Value Procurement |  |  | 100
12 | Acetone (Liquid) -Analytical grade 99% purity, 2.5 L/bottle | 12 bottles | 3500 | 42000 | Small Value Procurement |  |  | 12
| Hydrochloric Acid (Liquid) -Analytical grade 37% purity, 2.5 L/bottle | 12 bottles | 5000 | 60000 | Small Value Procurement |  |  | 12
| Acetic Acid (Liquid) -Analytical grade 99% purity, 40L/carboy | 10 carboys | 5000 | 50000 | Small Value Procurement |  |  | 10
| Hydrogen Peroxide (Liquid) -Analytical grade 99% purity | 5 gallons | 8000 | 40000 | Small Value Procurement |  |  | 5
5 | Sodium Chlorite (Powder) -Analytical grade 80% purity | 5 bottles | 2000 | 10000 | Small Value Procurement |  |  | 5
12 | Sulfuric acid (Liquid) - Analytical grade 98% purity, 2.5 L/bottle | 12 bottles | 4000 | 48000 | Small Value Procurement
| Sodium metabisulfite -Technical grade, 97% purity, 1kg/bottle | 5 bottles | 1000 | 5000 | Small Value Procurement |  |  | 5
| Sodium silicate -Neutral solution, pure | 5 gallons | 1000 | 5000 | Small Value Procurement |  |  | 5
| Fabric Softener (Flakes) |  |  |  | Small Value Procurement
| Xylanase Enzyme - Activity: ~200-250 U/m | 10 Liters | 5000 | 50000 | Small Value Procurement | 60 working days |  | 5 | 5
| Pectinase Enzyme - Activity: ~200-250 U/m | 10 Liters | 5000 | 50000 | Small Value Procurement |  |  | 5 | 5
| Laccase -Laccase from Trametes versicolor powder, light brown, ≥ 0.5 U/mg, Sigma cat#38429 | 5 bottles | 120000 | 600000 | Small Value Procurement
Other MOOE
| Bamboo Lei for MOA Signing and Launching of NTFIH in Laguna, Leyte , Davao, Isabela, Catanduanes, and Mindoro | 60pcs | 500 | 30000 | Shopping | 30 working days |  | 60
Cash Advances
| Banana Fiber Decorticated/Raw, Variety: Cavendish Source: Catanduanes | 1kg | 1000 | 1000 | Cash Advances | per schedule |  |  | 1
| Pineapple Fiber Decorticated, Variety : Formossa Source: Catanduanes | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Variety: Cavendish Source: Isabela | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Formossa Source: Isabela | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw Variety: Cavendish, Source: Mindoro | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : FormossaSource: Mindoro | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Variety: Cavendish Source: Northern Samar | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Formossa Source: Northern Samar | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Source: Catanduanes | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Hawaian Source: Catanduanes | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Source: Isabela | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Hawaian Source: Isabela | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Source: Mindoro | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Hawaian Source: Mindoro | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Banana Fiber Decorticated/Raw, Source: Northern Samar | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
| Pineapple Fiber Decorticated, Variety : Hawaian Source: Northern Samar | 1kg | 1000 | 1000 | Cash Advances |  |  |  | 1
Repairs and Maintenance Expenses
| Renovation of NTFIH Isabela | 1 lot | 1200000 | 1200000 | Competitive Bidding (Public Bidding) | 60 working days |  | 1
| Renovation of NTFIH Mindoro | 1 lot | 1266666.67 | 1266666.67 | Competitive Bidding (Public Bidding) |  |  | 1
| Renovation of NTFIH Catanduanes | 1 lot | 1266666.67 | 1266666.67 | Competitive Bidding (Public Bidding) |  |  | 1
| Renovation of NTFIH Leyte | 1 lot | 1266666.67 | 1266666.67 | Competitive Bidding (Public Bidding) |  |  | 1
Other Professional Services (OPS)
| FESEM Imaging Sample: Raw and treated textile fiber - Surface morphology - Cross-sectional imaging - VAT inclusive - Turnaround time: 7-10 working days upon receipt of sample | 20 Samples | 9000 | 180000 | Agency to Agency | per schedule |  | 20
| Fiber fineness, cut middle method - sample raw and treated bamboo fibers - includes raw data of results - turnaround time: 7-10 working days upon receipt of sample | 20 samples | 2500 | 50000 | Agency to Agency | per schedule |  | 20
Capital Outlay (Equipment)
| Decorticating machine | 6 lots | 250000 | 1500000 | Public Bidding (Competitive Bidding) |  | 6
| Mechanical Softening Machine | 3 lots | 1500000 | 4500000 | Public Bidding (Competitive Bidding) |  | 3
| Bench Scale Degumming Equipment | 6 lots | 600000 | 3600000 | Public Bidding (Competitive Bidding) |  | 6
| Fiber Cutting Machine | 3 lots | 800000 | 2400000 | Public Bidding (Competitive Bidding) |  | 3
| Hard Fiber Opener | 3 lots | 800000 | 2400000 | Public Bidding (Competitive Bidding) |  | 3
Office Equipment
Laboratory Equipment
| Hydro Extractor Machine | 3 lots | 105000 | 315000 | Public Bidding (Competitive Bidding) |  |  |  | 3
<-- INSERT ROW IF NEEDED
TOTAL BUDGET: |  | 21288100.01
+ 10% Provision for Inflation |  | 2128810.001
+ 10% Contingency |  | 2128810.001
TOTAL ESTIMATED BUDGET: |  | 25545720.01
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  | Reviewed by: | [5 empty] | Recommending Approval: | [7 empty] | Approved by:
ENGR. KARL MARX LENNIN A. FLORANTE |  | MARILOU G. AGUSTIN | [5 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  | Head, Property, Procurement and General Services Section | [5 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  | Date: ______________________ | [5 empty] | Date: ______________________ | [7 empty] | Date: ______________________

## Sheet1
Acetone (Liquid) -Analytical grade 99% purity, 2.5 L/bottle | 12 bottles | 3500 | 42000
Sodium Chlorite (Powder) -Analytical grade 80% purity | 5 bottles | 3000 | 15000
Sulfuric acid (Liquid) - Analytical grade 98% purity, 2.5 L/bottle | 12 bottles | 4000 | 48000
105000
Xylanase Enzyme - Activity: ~200-250 U/m | 10 Liters | 5000 | 50000
Pectinase Enzyme - Activity: ~200-250 U/m | 10 Liters | 5000 | 50000
100000
Laccase -Laccase from Trametes versicolor powder, light brown, ≥ 0.5 U/mg, Sigma cat#38429 | 5 bottles | 40000 | 200000
Sodium Hydroxide (NaOH) Liquid - Analytical grade 49% purity - 30 kg/cby | 10 carboys | 3800 | 38000
Sodium Hydroxide (NaOH) Micro Pellets -Analytical grade 97-99% purity - 1kg/btl | 10 bottles | 3000 | 30000
Hydrochloric Acid (Liquid) -Analytical grade 37% purity, 2.5 L/bottle | 12 bottles | 5000 | 60000
Acetic Acid (Liquid) -Analytical grade 99% purity, 40L/carboy | 10 carboys | 5000 | 50000
Hydrogen Peroxide (Liquid) -Analytical grade 99% purity | 5 gallons | 8000 | 40000
Sodium metabisulfite -Technical grade, 97% purity, 1kg/bottle | 5 bottles | 1000 | 5000
Sodium silicate -Neutral solution, pure | 5 gallons | 1000 | 5000