## GAA-CICA FRONTIER Stakeholders
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
END-USER/UNIT: OD-TIPS
Charged to: GAA-CICA project entitled "FRONTIER: Fostering the Revitalization of Nascent Textile Innovation Ecosystems in the Regions - Stakeholders Conference (Textile Gallery)"
Projects, Programs and Activities (PAPs)
| Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Apr | May | Jun | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
50203010 02 |  | Office Supplies Expenses
|  | A4 size | 1 ream | 250 | 250 | Shopping | 15 working days | 1 | 0 | 0
|  | Specialty Paper | 5 packs | 100 | 500 | Shopping | 15 working days | 5 | 0 | 0
|  | Ballpoint, ballpen, blue, 12 pcs/box | 3 box | 300 | 900 | Shopping | 15 working days | 3 | 0 | 0
|  | 20 packs "SIGN HERE" Page Markers, 5 colors, 150 sheets/pack | 5 packs | 70 | 350 | Shopping | 15 working days | 5 | 0 | 0
50203990 00 |  | Other Supplies Expenses
|  | Tokens/Prizes, 270 pcs | 1 lot | 15120 | 15120 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 0 | 0
|  | Various Groceries | 1 lot | 2000 | 2000 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Raffia | 1 lot | 5000 | 5000 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Natural dye sources and implements and shirt | 1 lot | 5000 | 5000 | Cash Advance | Per schedule | 1 | 0 | 0
|  | HDMI Adapter Connection: Mini DP male to HDMI Female Thunderbolt 2.0 Video Res: 4Kx2K Compatibility: Apple Macbook, Macbook Pro, MacBook Air, iMAc, Mac mini, Mac Pro Wire & Port specs: Pure copper Mini DP Port Corrosio-resistant, Copper coated, ABS shell | 1 pc | 900 | 900 | Cash Advance | Per schedule | 1 | 0 | 0
|  | Conference System Main Unit Specs: Power source: AC220V-240V 50Hz Input : MIC, Auxiliary Output :8P mic unit portX3, monitor, recording Frequency response: 50-16000Hz Size : 420x175x65MM Weight: 3.7kg Attachment: 8P DIN extension cable 10Mx1 Color : black | 1 unit | 8000 | 8000 | Shopping | 15 working days | 1 | 0 | 0
|  | Delegate's Unit Conference Mic Specs: - Mic ON/OFF Buttons - Built - in 2W Speaker - Volume Control - Unidirectional condenser mic - Red Light Indicate when mic is On | 12 pcs | 3000 | 36000 | Shopping | 15 working days | 12 | 0 | 0
Printing and Binding Expenses
|  | Brochures | 3 lots | 7200 | 21600 | Shopping | 15 working days | 1 | 1 | 1
|  | Sintra Boards | 3 lots | 2800 | 8400 | Shopping | 15 working days | 1 | 1 | 1
|  | Printing of PTC Proceedings | 1 lot | 400000 | 400000 | Negotiated Procurement - Small Value Procurement | 30 working days | 1 | 0 | 0
50211990 00 |  | Other Professional Services
|  | Laundry Services | 3 lots | 30000 | 90000 | Negotiated Procurement - Small Value Procurement | 15 working days | 1 | 1 | 1
|  | General Provision for Services | 5 lots | 10000 | 50000 | Negotiated Procurement - Small Value Procurement | 15 working days | 5 | 0 | 0
50299040 00 |  | Delivery and Transportation Expenses
|  | Delivery expense, from DOST-PTRI to communities, partners, and stakeholders | 30 lots | 1000 | 30000 | Cash Advance | Per schedule | 10 | 10 | 10
|  | Transportation expense, from DOST-PTRI to communities, partners, and stakeholders | 30 lots | 1000 | 30000 | Cash Advance | Per schedule | 10 | 10 | 10
Local Travel Expenses
|  | Local Travel to Bohol | 1 lot | 214000 | 214000 | Negotiated Procurement - Small Value Procurement | Per schedule | 1 | 0 | 0
50299030 00 |  | Representation Expenses
|  | Meals and snacks for meetings and events | 15 lots | 15000 | 225000 | Negotiated Procurement - Small Value Procurement | Per schedule | 5 | 5 | 5
50604050 14 |  | Capital Outlay - Technical & Scientific Equipment
|  | Lights System in the Gallery | 1 lot | 500000 | 2000000 | Negotiated Procurement - Small Value Procurement | 60 working days | 1 | 0 | 0
TOTAL APPROVED BUDGET: |  |  | 1143020
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
JENNELI E. CAYA |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Officer-in-Charge, Research and Development Division |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Revision Date: 17 April 2024 |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________