## Sustainable Meltblown
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
END-USER/UNIT: RDD-CDABUS
Charged to: Sustainable Meltblown Nonwoven Textiles for Mask Filters and Packaging Applications
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | Jan | Feb | Mar | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
50213050 14 |  | Repair and Maintenance – Technical and Scientific Equipment
|  | Repair and Maintenance of pre-spinning machine | 1 lot | 900000 | 900000 | Negotiated Procurement-Small Value Procurement |  | 1
50203010 02 |  | Office Supplies Expenses
| OS-026 | 5 boxes A4 Bond paper 70 gsm- 5 ream/box | 1 lot | 2000 | 14350 | Shopping |  | 5
| OS-057 | 5 boxes Legal bond paper 70 gsm- 5 ream/box |  | 2000 |  |  |  | 5
| OS-261 | 10 pieces Sticky notes yellow 3 x 3 |  | 80 |  |  |  | 10
| OS-243 | 5 reams Pink paper, Legal size |  | 650 |  |  |  | 5
| OS-260 | 3 boxes Ballpen |  | 100 |  |  |  | 3
|  | Fabric Scissors | 6 pcs | 330 | 1980 | Cash Advance |  | 6
|  | Ribbon | 1 roll | 500 | 500 | Cash Advance |  | 1
|  | Duct tape (50 x 50 mm) | 1 roll | 1100 | 1100 | Cash Advance |  | 1
|  | White Board (60cm×90cm) | 1 pc | 650 | 650 | Cash Advance |  |  | 1
|  | White Board Marker | 1 box | 800 | 800 | Cash Advance |  |  | 1
50203080 00 |  | Medical, Dental Laboratory Supplies Expenses
|  | 5 pieces Laboratory Gown | 1 lot | 1000 | 86500 | Negotiated Procurement-Small Value Procurement / Shopping |  | 5
|  | 5 pieces Half Facepiece Respirator |  | 2000 |  |  |  | 5
|  | 5 sets Respirator Filter Cartridges |  | 2000 |  |  |  | 5
|  | 6 boxes Disposable Particulate Respirator |  | 1500 |  |  |  | 6
| MDL-250 | 5 pieces Safety Protective Goggles |  | 500 |  |  |  | 5
|  | 30 pieces Gloves |  | 1500 |  |  |  | 30
|  | 5 pieces Nitrile Grip Rubber Protective Work Gloves |  | 300 |  |  |  | 5
|  | 5 pieces Silicon Shoe Cover |  | 600 |  |  |  | 5
|  | 5 pieces Hair Net |  | 100 |  |  |  | 5
| MDL-048 | Homopolymer Polypropylene Resin | 13 bags | 15000 | 195000 | Negotiated Procurement-Small Value Procurement |  | 13
| MDL-048 | 4 bags Homopolymer Polypropylene Resin | 1 lot | 10000 | 88000 | Negotiated Procurement-Small Value Procurement |  |  | 4
| MDL-048 | 4 sacks PLA (polylactic acid) resin |  | 12000 |  |  |  |  | 4
|  | Melt Flow Index (MFI) modifier masterbatch additive | 4 sacks | 10000 | 40000 | Shopping |  |  | 4
|  | 2 sacks Blue color masterbatch modifier | 1 lot | 10000 | 40000 | Shopping |  |  | 2
|  | 2 sacks Black color masterbatch modifier |  | 10000 |  |  |  |  | 2
|  | 1 lot Poly(butylene succinate) | 1 lot | 40000 | 146000 | Negotiated Procurement-Small Value Procurement |  |  |  | 1
|  | 1 lot Poly(ethylene glycol) 400g/mol |  | 15000 | [5 empty] | 3
|  | 1 lot Tributyl acetyl citrate |  | 10000 | [5 empty] | 1
|  | 1 lot Polymer antioxidant |  | 15000 | [5 empty] | 2
|  | 1 lot Polymer UV stabilizer |  | 7000 | [5 empty] | 3
50203990 00 |  | Other Supplies Expenses - Direct Cost
|  | Fire Extinguisher | 3 units | 3000 | 9000 | Shopping |  | 3
|  | Rotary Heater | 1 lot | 49999 | 49999 | Shopping |  | 1
|  | All-in-one Printer | 2 units | 14999 | 29998 | Shopping |  | 2
|  | 25 m Air compressor pneumatic tubing 2 pcs Pneumatic tube fitting | 1 lot | 3875 | 3875 | Shopping |  | 1
|  | Mobile Load Card for Communication | 50 pcs | 150 | 7500 | Shopping |  |  | 50
|  | 1 unit Basic Hand Tool Set | 1 lot | 12000 | 14550 | Shopping |  |  | 1
|  | 1 piece Cutter |  | 200 |  |  |  |  | 1
|  | 1 piece Philips Screwdriver |  | 200 |  |  |  |  | 1
|  | 1 piece Flat Screwdriver |  | 200 |  |  |  |  | 1
|  | 1 roll Tape measure |  | 200 |  |  |  |  | 1
|  | 1 piece Meter stick |  | 200 |  |  |  |  | 1
|  | 1 piece Steel measuring tape |  | 200 |  |  |  |  | 1
|  | 1 piece Long Nose Pliers |  | 250 |  |  |  |  | 1
|  | 1 piece Wire cutter |  | 250 |  |  |  |  | 1
|  | 1 piece Adjustable wrench (10 inch) |  | 250 |  |  |  |  | 1
|  | 1 set Allen wrench set |  | 300 |  |  |  |  | 1
|  | 3 pieces Paint brush (1 inch, 2 inch, 3 inch) |  | 100 |  |  |  |  | 3
|  | 1 box Pnuematic regulator for Meltblowing Air Heater | 1 lot | 5000 | 10500 | Cash Advance |  | 1
|  | 25 meters Air compressor pneumatic tubing |  | 200 |  |  |  | 25
|  | 1 piece Pneumatic tube fitting |  | 500 |  |  |  | 1
|  | Spray Ahesive | 2 bottles | 600 | 1200 | Cash Advance |  | 2
|  | Flower Arrangement | 1 lot | 10000 | 10000 | Cash Advance |  | 1
|  | 1 lot Tarpaulin Printing (8ft x 3ft) | 1 lot | 1000 | 3200 | Cash Advance |  | 1
|  | 5 pieces Sintra Board Printing (8.5in x 13in) |  | 300 |  |  |  | 5
|  | 1 piece Sintra Board Printing (1ft x 4ft) |  | 700 |  |  |  | 1
50203990 00 |  | Other Supplies Expenses - Indirect Cost
|  | Laptop | 1 unit | 49999 | 49999 | Shopping |  | 1
50299030 00 |  | Representation Expenses
|  | Meals and Snacks for Inagauration of Meltblown Line | 1 lot (30 pax) | 30000 | 30000 | Shopping |  | 30
50211990 00 |  | Other Professional Services
|  | Customized Polo Shirt with Logo Embroidery | 20 pcs | 900 | 18000 | Shopping |  |  | 20
|  | Flammability (medtex) | 16 samples | 1300 | 20800 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  | 16
|  | Air Permeability | 16 samples | 700 | 11200 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  | 16
|  | Thickness | 16 samples | 550 | 8800 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  | 16
|  | Weight/Mass Per Unit Area | 16 samples | 450 | 7200 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  | 16
|  | Softness/Stiffness | 16 samples | 1000 | 16000 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  | 16
|  | Abrasion Resistance | 16 samples | 900 | 14400 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  | 16
|  | Tensile Grab Strength (Breaking Strength (Grab)) | 16 samples | 900 | 14400 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  | 16
|  | Tearing Strength (Tongue) | 16 samples | 1700 | 27200 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  | 16
|  | Water Absorption/Absorbency | 16 samples | 300 | 4800 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  | 16
|  | Differential Pressure | 11 samples | 2470 | 27170 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  |  | 11
|  | Particle Filtration Efficiency - NaCl | 11 samples | 6490 | 71390 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  |  | 11
|  | Bacterial Filtration Efficiency | 11 samples | 10080 | 110880 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  |  | 11
|  | Synthetic Blood Penetration Resistance | 12 samples | 8400 | 100800 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  |  | 12
|  | Water Pressure: Hydrostatic Pressure | 11 samples | 2000 | 22000 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  |  | 11
|  | Molecular Weight -GPC | 16 samples | 5000 | 80000 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  |  | 16
|  | DSC | 16 samples | 3000 | 48000 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  |  | 16
|  | TGA | 16 samples | 3000 | 48000 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  |  | 16
|  | SEM | 11 samples | 7500 | 82500 | Negotiated Procurement-Small Value Procurement / Agency-to-Agency |  |  | 11
TOTAL APPROVED BUDGET: |  |  | 2468241
+ 10% Provision for Inflation |  |  | 246824.1
+ 10% Contingency |  |  | 246824.1
TOTAL ESTIMATED BUDGET: |  |  | 2961889.2
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
AUDRIC ZURIEL C. CRUZ |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: 15 January 2024 |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________