## PPMP FRONTIER-NTFIH
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 2nd Quarter of CY 2024
END-USER/UNIT: RDD-NFUS
Charged to: FRONTIER: Fostering the Revitalization of Nascent Textile Innovation Ecosystems in the Regions - Establishment of Natural Textile Fiber Innovation Hub (NTFIH)
Projects, Programs and Activities (PAPs)
UACS CODE | Stock No. | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  |  | SIZE |  |  |  |  | April | May | June | PR No. and Date | RFQ No. and Date | PhilGEPS Reference No. and Date | PhilGEPS Closing Date | AOC No. and Date | PO No. and Date | Name of Payee | BURS/ORS Amount | Budget Utilization Rate | Conforme of PO Date | COA Received of PO Date | NTP Date | Contract Effectivity Date | End of Contract | Extended End of Contract | Delivery Date | IAR No. and Date | ICS/PAR No. and Date | RIS No. and Date | RSMI No. and Date | DV Release Date | DV Amount | Disbursement Rate | REMARKS
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (35)
50203010 02 |  | Supplies and Materials Expenses
|  | 10 pcs Original HL T4000 DW Inks 108ml - BTD60 - BK | lot | 1000 | 10000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 10
|  | 10 pcs Original HL T4000 DW Inks 108ml- BT5000 - Magenta |  | 1000 | 10000 |  |  | 5
|  | 10 pcs Original HL T4000 DW Inks 108ml - BT5000 - Cyan |  | 1000 | 10000 |  |  | 5
|  | 10 pcs Original HL T4000 DW Inks 108ml- BT5000 - Yellow |  | 1000 | 10000 |  |  | 5
|  | 10 pcs Original Epson L5290 Ink - 65 ml BK 003 | lot | 800 | 8000 |  |  | 10
|  | 5 pcs Original Epson L5290 Ink - 65 ml Magenta 003 |  | 800 | 4000 |  |  | 5
|  | 5 pcs Original Epson L5290 Ink - 65 ml Cyan 003 |  | 800 | 4000 |  |  | 5
|  | 5 pcs Original Epson L5290 Ink - 65 ml Yellow 003 |  | 800 | 4000 |  |  | 5
|  | 5 pcs Original Brother MFC-L3770DW Cartridge, (Black) | lot | 2000 | 10000 |  |  | 5
|  | 5 pcs Original Brother MFC-L3770DW Cartridge, (Yellow) |  | 2000 | 10000 |  |  | 5
|  | 5 pcs OriginalBrother MFC-L3770DW Cartridge, (Cyan) |  | 2000 | 10000 |  |  | 5
|  | 5 pcs Original Brother MFC-L3770DW Cartridge, (Magenta) |  | 2000 | 10000 |  |  | 5
|  | 10 pcs Black Kyocera TK-1124 Toner Cartridge | pcs | 1500 | 15000 |  |  | 5
| x | 20 pcs Durable Office/Desk Stapler with staple remover | lot | 300 | 6000 | Shopping | 15-30 working days | 20
|  | 50 pcs Spiral Notebook 216x280MM 100s(leaves) |  | 300 | 15000 |  |  | 50
|  | 50 pcs Spiral Notebook 153x228MM 60s(leaves) |  | 150 | 7500 |  |  | 50
|  | 10 reams - Bond Paper Color Green, A4 70gsm |  | 500 | 5000 |  |  | 10
| x | 5 pcs 3 Layer Desk File Organizer Document Paper Tray |  | 1000 | 5000 |  |  | 5
|  | 25 pcs Clear Acrylic Name Plate Holder for Conference; 3x8.5 inches |  | 450 | 11250 |  |  | 25
|  | WiFi Printer and Scanner | 2 lots | 30000 | 60000 | Shopping | 15 working days | 2
|  | Computer Chair/Office Chair,/Ergonomic Chair With Armrest | 10 pcs | 10000 | 100000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 10
|  | Office Table Partition | 10 pcs | 20000 | 200000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 4 | 6
50203990 00 |  | Other Maintenance and Operating Expenses
|  | Certificate Holder; -A4 size; Materials: Gina fabric cover with indigenous accent Tinalak Accent; -For MOA Signing and Launching of NTFIH in Laguna, Leyte and Davao | 50 pcs | 500 | 25000 | Shopping | 15-30 working days |  | 50
|  | Certificate Holder; -Legal size; Materials: Gina fabric cover with indigenous accent Tinalak Accent; -For MOA Signing and Launching of NTFIH in Laguna, Leyte and Davao | 50 pcs | 500 | 25000 | Shopping | 15-30 working days |  | 50
|  | Token Packaging Box; -Size:7.25"W x 9.25H x 1.5"Thickness -Material: Hamuti Abaca and Chipboard -For MOA Signing and Launching of NTFIH in Laguna, Leyte and Davao | 60 pcs | 450 | 27000 | Shopping | 15-30 working days |  | 60
|  | Full Fabric Notebook as Tokens -Size:6.5"W x 8.75H -Material: Indiginous Accent: Binakol and T'nalak with magnetic lock, Inclusive of Bamboo Pen (Blue Ink) -For MOA Signing and Launching of NTFIH in Laguna, Leyte and Davao | 60 pcs | 1000 | 60000 | Shopping | 15-30 working days |  | 60
|  | Bamboo Lei for MOA Signing and Launching of NTFIH in Laguna, Leyte and Davao | 60 pcs | 500 | 30000 | Shopping | 30 calendar days
|  | Development of Carbon Dioxide (CO2) Emission Assessment Tool | 1 lot | 350000 | 350000 | Negotiated Procurement-Small Value Procurement | 45 calendar days | 1
|  | Split Type Wall Mounted Inverter Airconditioner (for CDBUS Laboratory Use) | 2 lots | 49990 | 99980 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 2
|  | Pineapple fibers - unbrushed/decorticated , Source: Laguna | 1 lot | 180000 | 120000 | Negotiated Procurement-Small Value Procurement | 60 working days | 1
|  | Banana fibers - unbrushed/decorticated , Source: Laguna | 1 lot | 120000 | 120000 | Negotiated Procurement-Small Value Procurement | 60 working days |  | 1
|  | Pineapple fibers - unbrushed/decorticated, Source: Davao | 1 lot | 120000 | 120000 | Negotiated Procurement-Small Value Procurement | 60 working days |  | 1
|  | Raw Bandala Fibers, Source Catanduanes | 50 kgs | 500 | 25000 | Negotiated Procurement-Small Value Procurement | 30 working days |  | 50
|  | Raw Bandala Fibers , Source Laguna | 20 kgs | 500 | 10000 | Negotiated Procurement-Small Value Procurement | 30 working days |  | 20
|  | Oil-free vacuum pump - max. vacuum: 99 mbar abs. - max. flow rate: 37 L/min @ 60 Hz or 34 L/min @ 50 Hz - hose bard: ID8 - noise level: 52 dB - net weight: 5.2 kg - 220 V, 50/60 Hz - max. power: 80W (1/6 HP) - max. current: 0.4 A - with overheat protection - equipped with vacuum regulator and overflow protection / filter cartridge | 1 lot | 49999 | 49999 | Shopping | 15-30 working days |  | 1
50203080 00 |  | Medical, Dental Laboratory Supplies Expenses
|  | Hydrogen Peroxide - Technical grade, ≥48% purity - 35 kg/cby | 40 cby | 8000 | 320000 | Negotiated Procurement-Small Value Procurement | 60 working days | 40
|  | Acetone, technical grade, 5L | 20 bottles | 6500 | 130000 | Negotiated Procurement-Small Value Procurement | 60 working days | 20
|  | Sulfuric Acid, -95-98%, AR Grade | 20 bottles | 2000 | 40000 | Negotiated Procurement-Small Value Procurement | 60 working days | 20
|  | 30 liters Xylanase Enzyme | 1 lot | 3500 | 105000 | Agency to Agency | per schedule |  | 30
|  | 30 liters Pectinase Enzyme |  | 3500 | 105000 |  |  |  | 30
|  | 20 pcs pH Testing strips | 1 lot | 2000 | 40000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 20
|  | 20 pairs Non-Slip Laboratory Shoes (Medium Size) |  | 500 | 7500 |  |  | 20
|  | 24 gallons Bleach, unscented, 3.8-4.0/ gallon |  | 500 | 12000 |  |  | 24
|  | 12 gallons Alcohol 70% Solution, Antiseptic Disinfectant 4L/Gallon |  | 2500 | 30000 |  |  | 12
|  | 50 packs Pull-ups Tissue, 2 ply, 190pulls/pack |  | 300 | 15000 |  |  | 50
|  | 50 box Face Mask, 3 ply, Earloop, 50pcs/box |  | 300 | 15000 |  |  | 50
|  | 15 pcs Polyethyene plastic bag, transparent, 0.002 in (thickness), 40in x 60in, 50 pcs/pack |  | 1000 | 15000 |  |  | 10
|  | 15 pcs Polyethyene plastic bag, transparent, 0.002 in (thickness), 20in x 30in, 50 pcs/pack |  | 500 | 7500 |  |  | 10
|  | 10 pcs Ziplock bag, transparent, 8cm x 12cm, 100 pcs/pack |  | 200 | 2000 |  |  | 10
|  | 10 pcs Ziplock bag, transparent, 14cm x 20cm, 100 pcs/pack |  | 300 | 3000 |  |  | 10
|  | 10 pcs Ziplock bag, transparent, 24cm x 34cm, 100 pcs/pack |  | 400 | 4000 |  |  | 10
|  | 100 pcs Particulate Filter N95 |  | 500 | 50000 |  |  | 100
|  | 50 pcs Laboratory Gown, 3/4 Sleeves, White, Medium |  | 500 | 25000 |  |  | 50
|  | 10 pcs Reusable Respirator, Respiratory Protection |  | 2000 | 20000 |  |  | 10
|  | 50 pcs Lint-free tissue, 1 ply, 4.3 in x 8.4 in, 280 pcs/box |  | 400 | 20000 |  |  | 50
|  | 25 pcs Safety Eye Laboratory Goggles |  | 500 | 12500 |  |  | 25
|  | 5 pcs Parafilm, 4" x 125 ft |  | 4000 | 20000 |  |  | 5
|  | 3 pcs Electronic Laboratorty Timer |  | 2000 | 6000 |  |  | 3
|  | Stainless Steel Emergency spray eyewash and Emergency Shower Specification: | 1 unit | 40000 | 40000 | Shopping | 15-30 working days | 1
|  | 1 unit Laboratory Glasswares Drying Rack (Vinyl-Coated Steel Wire Construction, Self-Standing), 90 pegs, 46.2 x 18.2 x 52.5 cm | 1 lot | 10000 | 10000 | Negotiated Procurement-Small Value Procurement | 15-30 working days | 1
|  | 10 pcs Magnetic Stirrer Bar |  | 1500 | 15000 |  |  | 5
|  | 10 pcs Fritted Glass Extraction Thimbles, 10mm |  | 4000 | 40000 |  |  | 10
|  | 8 pcs Glass Extraction Thimbles |  | 3000 | 24000 |  |  | 8
|  | 30 pcs Glass filter crucibles, 30 mL, 40-60 microns |  | 3500 | 105000 |  |  | 30
|  | 5 pcs Erlenmeyer Flask 250 ml |  | 1500 | 7500 |  |  | 5
|  | 5 pcs Erlenmeyer Flask 50 ml |  | 1000 | 5000 |  |  | 5
|  | 3 pcs Desiccator |  | 10000 | 30000 |  |  | 3
|  | 1 unit Desiccator cabinet |  | 30000 | 30000 |  | 15-30 working days | 1
|  | 3 units Hot Plate with Magnetic Stirring Specifications: 280 mm x 280 mm or equivalent or better 200 - 1500 C temperature range, 1 increment or equivalent or better 100 - 1500 rpm speed or equivalent or better Ceramic Plate | 3 units | 40000 | 120000 | Negotiated Procurement-Small Value Procurement | 30 working days | 3
50211990 00 |  | Other Professional Services
|  | Yarn Strength and Elongation (Single Strand) ASTM D 2256 | 15 samples | 650 | 9750 | Agency to Agency | 3 weeks upon receipt of samples |  | 15
|  | Yarn Number (Single) ASTM D 1059 | 15 samples | 600 | 9000 | Agency to Agency |  |  | 15
|  | Yarn Evenness, ASTM D 1425 | 15 samples | 1100 | 16500 | Agency to Agency |  |  | 15
|  | Yarn Twist ASTM D1423/D1423M-16 | 15 samples | 650 | 9750 | Agency to Agency |  |  | 15
|  | Yarn Hairiness, ASTM D 5647 | 15 samples | 1100 | 16500 | Agency to Agency |  |  | 15
|  | Fiber Composition AATCC | 15 samples | 3000 | 45000 | Agency to Agency | 3 weeks upon receipt of samples |  | 15
|  | Fiber fineness, cut middle method - sample raw and treated bamboo fibers - includes raw data of results - turnaround time: 7-10 working days upon receipt of sample | 20 samples | 2500 | 50000 | Agency to Agency | 3 weeks upon receipt of samples |  | 20
|  | Worksheet Copy (request of Raw Data) | 1 lot | 2000 | 2000 | Agency to Agency | 3 weeks upon receipt of samples |  | 1
|  | X-Ray Diffraction Analysis | 1 lot | 30000 | 30000 | Agency to Agency | 3 weeks upon receipt of samples |  | 1
|  | Microscopical View (Longitudinal) | 15 samples | 500 | 7500 | Agency to Agency | 3 weeks upon receipt of samples |  | 15
|  | Microscopical View (Cross-Sectional) | 15 samples | 500 | 7500 | Agency to Agency | 3 weeks upon receipt of samples |  | 15
|  | Non Woven ( Needle Punching) Production Services | 104 m | 200 | 20800 | Shopping | 30 working days | 104
Representation Expenses
|  | Meals and snacks for meetings, trainings and events | 3 lots | 15000 | 45000 | Negotiated Procurement-Small Value Procurement | per schedule | 1 | 1 | 1
|  | Printing Services - Tarpaulin, Sintra Board etc | 3 lots | 2000 | 6000 | Cash Advance | per schedule | 1 | 1 | 1
Repairs and Maintenance Expenses
|  | Office of the Director Schematic Design Concept | 1 lot | 150000 | 150000 | Negotiated Procurement-Small Value Procurement | 15-30 working days |  | 1
TOTAL APPROVED BUDGET: |  |  | 3443029
+ 10% Provision for Inflation |  |  | 344302.9
+ 10% Contingency |  |  | 344302.9
TOTAL ESTIMATED BUDGET: |  |  | 4131634.8
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  |  | Reviewed by: |  |  | Certified Funds Available: |  |  | Approved by:
ENGR. KARL MARX LENNIN A. FLORANTE |  |  | MARILOU G. AGUSTIN |  |  | MERLITA R. ODI |  |  | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  |  | Head, FAD-PPGSS |  |  | Head, FAD-BTS |  |  | Director IV
Date: ______________________ |  |  | Date: _____________ |  |  | Date: _____________ |  |  | Date: _____________

## PPMP Sample 1 (2)
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) 2024
For 1st Quarter of CY 2024
(Sample Only)
END-USER/UNIT: RDD-NFUS
Charged to: Digitalization of Philippine Textiles to Protect and Sustain the Handloom Weaving Sector
Projects, Programs and Activities (PAPs)
CODE | GENERAL DESCRIPTION | QUANTITY/ | UNIT PRICE | ESTIMATED BUDGET | Mode of Procurement | DELIVERY TERM | SCHEDULE/MILESTONE OF ACTIVITIES
|  | SIZE |  |  |  |  | Jan | Feb | Mar | PR No. | RFQ No. | PhilGEPS Reference No. | AOC No. | PO No. | COA Received Date | NTP No. | IAR No. | ICS/PAR No. | RIS/RSMI No. | REMARKS | REMARKS
Office Supplies
| 32gb OTG flashdrive | 80 pieces | 625 | 50000 | Small Value Procurement |  | 80
| 16GB microSD card | 5 pieces | 600 | 3000 | Small Value Procurement |  | 5
| Powerbank | 10 pieces | 1000 | 10000 | Small Value Procurement |  | 10
| External hard drive, 1TB | 10 pieces | 5000 | 50000 | Small Value Procurement |  | 10
| Wireless mouse | 5 pieces | 500 | 2500 | Small Value Procurement |  | 5
| Binder Clip 4 per pack black | 20 packs | 25 | 500 | Shopping |  | 20
| Binder clip 2 per pack black | 15 packs | 20 | 300 | Shopping |  | 15
| Paper clip vinyl coated assorted 100s | 5 packs | 30 | 150 | Shopping |  | 5
| Envelope document 5/pack | 10 packs | 30 | 300 | Shopping |  | 10
| Envelope expanding with elastic, legal | 30 packs | 10 | 300 | Shopping |  | 30
| Sticky flags | 20 packs | 100 | 2000 | Shopping |  | 20
| Highlighter (yellow) | 5 pieces | 15 | 75 | Shopping |  | 5
| Glue stick | 10 packs | 30 | 300 | Shopping |  | 10
| Long brown envelope | 50 packs | 20 | 1000 | Shopping |  | 50
| Clearbook, long | 15 pieces | 133.3333 | 2000 | Shopping |  | 15
| Spray paint | 1 piece | 1000 | 1000 | Small Value Procurement |  |  | 1
| All in one laser printer | 3 units | 10000 | 30000 | Small Value Procurement |  |  | 3
| Certificate paper | 100 pieces | 10 | 1000 | Shopping |  |  | 100
| ID and ID laces | 100 pieces | 20 | 2000 | Shopping |  |  | 100
| Manila paper | 50 pieces | 5 | 250 | Shopping |  |  | 50
| USB to VGA/HDMI adapter for Macbook | 3 units | 133.3333 | 400 | Small Value Procurement |  |  | 3
| USB to VGA/HDMI adapter for other laptops | 3 units | 133.3333 | 400 | Small Value Procurement |  |  | 3
| A4 paper/500 pcs/ream | 30 reams | 183.3333 | 5500 | Shopping |  |  | 30
| Paper shredder | 1 piece | 5000 | 5000 | Small Value Procurement |  |  | 1
| Black ink for printer | 8 carts | 400 | 3200 | Shopping |  |  | 8
| Colored ink for printer | 8 carts | 400 | 3200 | Shopping |  |  | 8
| Metal fasteners | 3 packs | 66.6667 | 200 | Shopping |  |  | 3
| Folder for A4 size documents, 10 pcs per pack | 20 packs | 50 | 1000 | Shopping |  |  |  | 20
| Blue sign pens | 20 pieces | 30 | 600 | Shopping |  |  |  | 20
| Regular pens | 100 pieces | 10 | 1000 | Shopping |  |  |  | 100
| Permanent markers | 50 pieces | 20 | 1000 | Shopping |  |  |  | 50
| Transparent tape | 20 pieces | 20 | 400 | Shopping |  |  |  | 20
| Stapler | 3 pieces | 100 | 300 | Shopping |  |  |  | 3
| Staple wires | 10 boxes | 50 | 500 | Shopping |  |  |  | 10
| Correction tape | 10 pieces | 30 | 300 | Shopping |  |  |  | 10
| Scissors | 10 pieces | 30 | 300 | Shopping |  |  |  | 10
Laboratory Supplies
| Machining of components H1 | 4 units | 1640 | 6560 | Small Value Procurement |  | 4
| Machining of components H2 | 4 units | 860 | 3440 | Small Value Procurement |  | 4
| Machining of component M | 8 units | 1000 | 8000 | Small Value Procurement |  | 8
| Disposable ABR electrodes | 300 units | 50 | 15000 | Small Value Procurement |  | 300
| Disposable snap electrodes | 100 units | 57 | 5700 | Small Value Procurement |  | 100
| Skin prep gel | 4 units | 1375 | 5500 | Small Value Procurement |  |  | 4
| Neurodiagnostic Conductive Electrode Paste | 4 units | 1800 | 7200 | Small Value Procurement |  |  | 4
| Gold/silver electrode | 6 units | 1333.3333 | 8000 | Small Value Procurement |  |  | 6
| 70% Isopropyl alcohol | 10 units | 28 | 280 | Small Value Procurement |  |  | 10
| Micropore tape 1in | 6 boxes | 350 | 2100 | Small Value Procurement |  |  |  | 6
| Sterile gauze, individually wrapped | 10 boxes | 300 | 3000 | Small Value Procurement |  |  |  | 10
| Alcohol swab | 6 boxes | 400 | 2400 | Small Value Procurement |  |  |  | 6
Office Equipment
Laboratory Equipment
<-- INSERT ROW IF NEEDED
TOTAL BUDGET: |  | 247155
+ 10% Provision for Inflation |  | 24715.5
+ 10% Contingency |  | 24715.5
TOTAL ESTIMATED BUDGET: |  | 296586
NOTE: Technical Specifications for each Item/Project being proposed shall be submitted as part of the PPMP
Prepared by: |  | Reviewed by: | [5 empty] | Recommending Approval: | [7 empty] | Approved by:
________________________ |  | MARILOU G. AGUSTIN | [5 empty] | MERLITA R. ODI | [7 empty] | JULIUS L. LEAÑO JR., Ph.D.
Project Leader |  | Head, Property, Procurement and General Services Section | [5 empty] | Head, Budget and Treasury Section | [7 empty] | Director IV
Date: ______________________ |  | Date: ______________________ | [5 empty] | Date: ______________________ | [7 empty] | Date: ______________________